# THE GOVERNMENT OF THE SYRIAN ARAB REPUBLIC

&

# THE UNITED NATIONS DEVELOPMENT PROGRAMME

# Project Title:

# “Support to the Establishment of the Academy of Police Sciences in Syria"

# Project number

# SYR

Brief Description

| SIGNATURE PAGE |
| --- |
|  |  | Country: Syrian Arab Republic |
| UNDAF Outcome(s) | UNDAF Outcome 2: Efficiency and accountability of governance structures at central and local levels strengthened, by government, civil society and the private sector, towards sustainable development |
| Expected Outcome(s): | CPAP B.1 Policy and decision-making supported by quality information and analyses |
| Expected Output(s): | B.1.1. Access to information for decision-making strengthened including capacity building of religious leaders and public institutions to use ICT 1. The Establishment of Academy of Police Sciences including strategy and structures 2. Capacity Development for Training, Education, Research and Advanced Studies |  |
| Implementing Partner: | Ministry of Interior |

Agreed by H.E. Tayssir Al-Raddawi, Head of the State Planning Commission

On behalf of the Syrian Government and the State Planning Commission.

| Signature: |  | Date: |  |
| --- | --- | --- | --- |
|  | ………………………………………………………………… |  | …………………… |

Agreed by H.E. Said Sammour, Minister of the Interior

On behalf of the Ministry of the Interior, the Implementing Partner.

| Signature: |  | Date: |  |
| --- | --- | --- | --- |
|  | ………………………………………………………………… |  | …………………… |

Agreed by  H.E. Ismail Ould Cheikh Ahmed, UNDP Resident Representative

On behalf of the United Nations Development Programme

| Signature: |  | Date: |  |
| --- | --- | --- | --- |
|  | ………………………………………………………………… |  | …………………… |

Table of Contents

List of Acronyms	ii

PART I	SITUATION ANALYSIS	1

1.1	The Context in Syria	1

1.2	Current Status and Needs of the Police Faculty	2

1.3	Rationale for Establishing an Academy of Police Science	8

1.4	The Institutional and Legal Framework	9

1.5	Regional and International Experience	9

PART II	STRATEGY	10

2.1	Government Strategy	10

2.2	UNDP Strategy	10

2.3	Program Strategy	12

2.4	Project Outputs and Activities	13

2.5	Duration of Project	15

2.6	Intended Beneficiaries	15

Part III	MANAGEMENT ARRANGEMENTS	16

3.1	Project Board	16

3.2	Project Management Team	17

3.3	Levels of Project Management	17

3.4	Project Management Office	18

3.5	Project Assurance	18

3.6	Procurement and Sub-Contracting	19

Part IV	MONITORING AND EVALUATION	19

4.1	 Monitoring, Evaluation and Reporting	19

4.2	Opportunities and Risks	20

PART V	LEGAL CONTEXT	21

PART VI 	STRATEGIC RESULTS AND RESOURCES FRAMEWORK	22

Annexes		27

Annex 1: Police Faculty - Overview of Main Courses and Curriculum	28

Annex 2: Terms of Reference for the National Project Director (NPD)	33

Annex 3: ToR for Technical Assistance	36

# List of Acronyms

| ADG | Academy Development Group |
| --- | --- |
| APR | Annual Project Report |
| APS | Academy of Police Sciences |
| AWP | Annual Work Plan |
| CD | Capacity Development |
| ICT | Information and Communications Technology |
| IT | Information Technology |
| MoA | Memorandum of Agreement |
| MoI | Ministry of Interior |
| NCO | Non Commissioned Officer |
| PD | Project Document |
| PMO | Project Management Office |
| PB | Project Board |
| SAR | Syrian Arab Republic |
| SBAA | Standard Basic Assistance Agreement |
| SPC | State Planning Commission |
| TDC | Trainer Development Course |
| ToR | Terms of Reference |
| UNDP | United Nations Development Programme |
| USD | United States Dollars |

# PART I	SITUATION ANALYSIS

## 1.1	The Context in Syria

The National Police Force in Syria, which is under the Ministry of Interior (MoI), is responsible for routine police duties and comprises emergency police, local neighbourhood police, riot police and traffic police in addition to an arm of the Gendarmerie, which had originally been organized by the French Mandate authorities to police rural areas. Since independence, Syria’s police and internal security apparatus have undergone significant reorganization and personnel changes, reflecting national law and order needs and the security requirements of each succeeding regime.

During the 1970s and 1980s the policing and security forces assumed a more conventional civil police role coinciding with increased professionalization and the parallel development of a separate and more effective internal security apparatus. Police are structured around a two-tiered entry level: one for recruitment of general police and a higher-level direct intake for selected tertiary graduates to train at officer level. The primary officer level training is undertaken in the Police Faculty in Damascus. A number of smaller institutions throughout the country train operational level police in addition to some operational police training undertaken within the main Police Faculty.

As in the region and internationally, policing in Syria is subject to an on-going process of change as the organisation positions itself for both national and global challenges facing the maintenance of law and order, including national security. These reforms include the selection processes for police recruits and officer intakes, as well as seeking to improve the education and training of police at all levels, including specialised training.

By international standards Syria is a relatively safe society and does not face the scale of problems relating to criminal activity found in many countries, particularly in larger cities, such as high level drug abuse, armed robbery, serious assault and house-breaking. However the Government of the Syrian Arab Republic (SAR), the MoI, and the Police themselves, are well aware of the impacts of globalisation on domestic crime trends and larger-scale organised crime, and acknowledge the need to ensure police are well prepared to deal with all types of criminality ranging from community issues such as public order, theft, property damage and domestic violence, through to emerging higher-level crimes such as people trafficking, money laundering, cyber-crime and border security.

There is a desire and commitment in government and the MoI to improve the level of police training and education, consistent with similar developments in the region and internationally. A number of initiatives have been put in place to commence this process, including a request from the MoI for UNDP to provide technical support and assistance in establishing an Academy of Police Science, as well as implementing capacity development programs for the MoI. The institution is envisioned to be an academic and training resource in police sciences to study and undertake applied research in criminology and security as well as providing education and training for high and lower level law enforcement officers and MoI staff on best practices and international standards in policing science.

The Academy is also envisioned to mainstream a scientific approach as well as incorporating and supporting social sciences in order to further study and analyse best practices in law enforcement, crime prevention and reducing recidivism.  It will serve to elevate the level of professional training, as well as introducing new techniques and models to law enforcement in Syria.

An emerging function of the educational arm of the Academy will also serve as a way of disseminating relevant and updated information on crime prevention, criminal rehabilitation, security and policing to relevant stakeholders at the national level.

This Project Document (PD) is the result of an in-country Mission by an international consultant who collaborated closely with the nominated national consultant on law enforcement, as well as other key stakeholders, in identifying requirements for future development and positioning of the Academy of Police Sciences as an institution of police learning and research, including a proposed Advanced Studies Faculty delivering higher level post-graduate programs for police officers.

Prior to the in-country Mission by the international consultant, a comprehensive and thorough analysis of the current status of the Police Academy, and recommendations for enhancing the facility, was undertaken by the national consultant contracted by UNDP.

## 1.2	Current Status and Needs of the Police Faculty

Infrastructure

The current Police Faculty which was established in 1961 is a large and well maintained institution with good facilities and grounds and comprises several buildings for administration, training, and residential purposes as well as specialist areas including:

- A Language Laboratory;

- Forensics Laboratory;

- Traffic Laboratory;

- Mechanics Workshop; and,

- Two Computer Rooms.

A new building to further enhance infrastructure is currently under construction.

The Faculty is spread over an area of 121 dunums and while most of the space is designated for use by the Faculty, 10 dunums are reserved for use by the Army. There are several buildings within in the physical territory that do not belong to the Police Faculty including the Protocol Department, Training Building and a Fitness Centre.

There are currently two buildings used for training, with more training room space planned for the building currently being constructed. There are 14 dormitories for trainees (male and female) and the two main buildings comprise a total of 8 classrooms (5 in the larger building and 3 in the eastern building).

There is no gym or designated space for physical fitness activities.

The main buildings are in satisfactory condition however they are presented in a rather conventional manner as lecture rooms/classrooms equipped with basic chairs and desks. There are no areas allocated for small group discussion. Despite regular maintenance and upkeep, the buildings have kept the same basic infrastructure and layout since 1961 and would benefit from renovation and consideration of a better layout consistent with contemporary adult learning approaches.

Overall, there is a need to evaluate the utility structure of the Faculty. The current physical layout should be redesigned to fit a new organisational structure better suited to a contemporary Academy of Police Sciences, as well as defining with more clarity the specific purpose of each area consistent with building use and function.

Some of the training rooms need new furniture and equipment (desks and filing cabinets) for the students. Furthermore, the heating and air conditioning system needs to be evaluated and perhaps reconditioned or renewed and a specific space or area needs to be designated as a physical fitness room/gymnasium.

There is a view amongst some stakeholders that all buildings currently within the site should made available exclusively for use as determined by the needs of the Police Faculty, however this would require high level negotiations with appropriate decision-making bodies including the Army who currently use some of the space within the Faculty as previously stated.

Organisational Structure of the Faculty

The organisational structure of the Police Faculty currently comprises eight (8) sections and sub-sections, with each sub-section also divided into offices or branches.

The eight main sections of the Faculty are:

- Training Section (includes training, coursework and exams);

- Administrative Affairs;

- Morale Guidance (Politicization);

- Vehicles Division;

- Medical Services Division;

- Financial Affairs;

- Communications Division; and,

- Student Leadership Division.

A new organisational structure for administration, educational faculties and specialist centres is required to achieve the MoI vision for the new Academy and this should be informed by specific needs in the Syrian context as well as drawing on regional best practice in police studies and research including Egypt and Saudi Arabia, and international standards for Academies of Police Science and Security. The new structure and subsequent divisions/sections for the envisioned Academy should be consistent with its assigned future role as well as the vision and strategy to achieve this. This restructure and redesign should be undertaken in a collaborative manner with all key stakeholders, including Faculty staff, to ensure understanding and ownership of the changes required.

It is proposed that the new organisational structure for the establishment of the Academy of Police Sciences would include key areas for both administration, and for education and training. The Administration Section would comprise all finance and administrative requirements for the Academy whereas the Education and Training Section would include a range of Faculties, as well as specialist departments, laboratories and centres such as Library and Learning Centre, Research, Curriculum and Assessment, Continuing Training, Forensics and Languages. A key aspect of the new organisational structure would be some form of Advanced Studies Faculty and a mechanism to coordinate regional and international cooperation agreements with selected regional and international Universities, Security Institutes and Specialised Agencies.

The revised organisational structure would require the establishment of new departments or sections as a means to facilitate emerging needs such as international cooperation, strengthening of language training, police leadership and management development, curriculum and research facilities, and upgraded specialist areas for such skills as forensic sciences for investigations, criminal intelligence and analysis to target emerging crime, and learning about high-level crime such as transnational crime, border security, money laundering, narcotics, people trafficking, and cyber crime (e-Crime).

There is also a need to develop concise roles and unit descriptions or terms of reference (ToR) for all departments/sections/units, and their members, to delineate responsibilities as well as the mechanisms to facilitate coordination between all parties, their purpose and their specific areas of responsibility.

Staffing: Administrative and Training Faculties

There is approximately 100 administrative and training staff in the Police Faculty. Most trainers are graduates of the Faculty, have a military oriented background and few have any training in curriculum design and/or adult learning delivery methodology. There is a limited number of civilian staff (eg: the French Instructor). College professors are sometimes utilised to teach courses on an adjunct basis. Currently there are several professors who are completing doctoral degrees from other security academies: six (6) in Egypt and three (3) in Saudi Arabia.

The Faculty would benefit from developing clear policies, procedures and regulations for recruiting training staff to adequately link the practical and academic aspects of police education and learning at all levels. There is a significant need to upgrade and implement sustainable mechanisms for the selection and capacity development of trainers, and opportunities should be provided for existing staff to upgrade their training skills and knowledge in accordance with the academic and practical needs of the Faculty as it moves towards an Academy of Police Sciences model. This capacity development for trainers would be designed to ensure longer-term sustainability in learning methodologies and renewal of curriculum.

Policies, procedures and regulations would also be developed to facilitate trainer exchange fellowships on the post graduate level with similar regional and international institutions for professional development purposes.

Curriculum and Courses

The current curriculum and courses applied within the Faculty are designed and determined by the Administration Section which reports to the MoI through the Dean of the Faculty. The curricula and course material used include basic information prepared by specialized and experienced officers. However, these officers are not academically trained educators and need capacity development to improve the quality and contemporary relevance of the training and to design curriculum and deliver courses, programs, and continuing learning workshops and seminars in the field of up-to-date police sciences.

With regard to the curriculum and learning methodologies, an Academy Development Group (ADG) has been established by the MoI, to review/renew the currently offered curriculum. It is made up of 5 persons qualified in different fields ranging from those with strength in field experience as well as those with experience in academic and scientific areas, and includes the former Dean of the Faculty and the NPD for Law Enforcement.

Curriculum is always dependent of the specialised nature of the program requirements and is designed accordingly. A more detailed description of curriculum is outlined in Annex 1 however the following provides an overview of current curriculum and courses:

- Curriculum for District Directors:

- This programme is not less than one year

- Degree required: Law Degree

- Curriculum for Doctors:

- This programme lasts six (6) months

- Degree required: Medical Degree

- Curriculum for Mid-level Officers:

- This programme is four (4) to eight (8) months

- Qualification required: High School; 3 years or more professional experience

- Curriculum for Nursing Mid-Level Officers:

- This programme is four (4) to eight (8) months

- Curriculum for Basic Training Civilian Officers:

- This programme is eight (8) months

- Qualifications required: Preparatory or High School Degree

- Curriculum for Female Officers; Mid-Career:

- This programme is eight (8) months

- Basic Training Curriculum for New Recruits:

- This programme is eight (8) months

- Curriculum for Civilian Driver; New Recruits:

- This programme is eight (8) months

- Qualifications required: Preparatory Degree.

There is a need to develop new courses in alignment with MoI guidelines and state-of-the-art requirements in police sciences. This has already commenced with the establishment of the ADG however further assistance is required to ensure the new curriculum meets both best practices regionally, and international standards, as well as meet the specific needs relating to the Syrian context.

This design and development would include clear course descriptions for each program and the rationale for them, taking into account the specific material need to be covered in each course. There is a need to design flexible mechanisms to update or upgrade curriculum in line with state-of-the-art police science and to develop guidelines to prepare a new and improved curriculum, combining the academic approach with practical field experience.

Police Faculty Library

The Police Faculty has a small conventional Library with a limited number of books, most of which are old and outdated, and most of which are in the Arabic language. The Department of Political Guidance supplies the library with books and reference materials. The Library currently does have a lending policy, however, it is not often utilised and very limited use is made of the Library as a learning resource. The Faculty currently has no research capability for either staff or students.

There is currently no on-line or e-library facilities for accessing books and other resources and the Library does not have any cooperation or exchange agreements (for books and/or reference materials) with any other similar institution in the region or elsewhere.

The Faculty needs to upgrade and modernise the Library and its facilities, and would benefit from a larger Library designed around a Learning Centre model which would include more reading and study space, access to computers, more library books and reference materials for students and staff, on-line (e-library) system, audio-visual resources and small group discussion rooms. The Learning Centre could also include a dedicated and appropriately resourced Research area. Consideration could be given to setting up a new Research and Learning Centre within the building currently under construction;

Capacity development for the Library and Learning centre would also include establishing networks with similar institutions and facilitating agreements with other similar libraries for the exchange of materials and knowledge.

Information and Communications Technology (ICT)

There is currently limited application of modern information and communications technology (ICT) in the Police Faculty either for administration or as a resource to assist learning. Although there is an internal telephone network within the Faculty there is no automated or IT based system for internal email and communication, i.e. no internal server or intranet and no outlook or similar program. The Faculty only has 5 internet dial up lines and no broadband or wireless system.

Most of the paperwork in the Faculty is done manually, and most files and procedures are not automated, with limited use of ICT apart from a few stand-alone computers in some areas. There are however two computer laboratories for training, comprising approximately 120 relatively new computers (1-3 years old), which are in good condition.

Most of the training/lecture halls do not have IT and/or audio-visual equipment for presentations, although during consultations with Senior Faculty staff is was indicated that steps were being taken to obtain some equipment in this regard.

As the Faculty moves towards the status of an Academy of Police Sciences based on regional best practices and international standards, it would benefit from an internal ICT automated network for the following processes:

- Admission and Registration of new recruits and other students;

- Personal files and records for students, staff and faculty members; and

- Electronic storage and retrieval of curriculum, courses, and learning materials.

In addition to improving and expanding the current dial-up network and providing access to high-speed internet, further improvements would include upgrading, and where necessary installing, audio-visual equipment for projection halls.

Admissions and Graduation Requirements

For new intakes and admissions, the MoI announces open positions for recruits based on specific needs and specializations. The number of positions for new intakes depends of the need as determined by the MoI. Eligible candidates are considered on the basis of their qualifications or degree: eg Preparatory, Secondary or College Degree in Law or Medicine.

Duration of training is dependant on qualification/degree sought and is generally one the following:

    - Preparatory: four (4) to eight (8) month course;

    - Secondary: eight (8) months;

    - Medical Degree: six (6) months;

    - Law Degree: one (1) year minimum.

Upon completion of a course, a final exam is administered under the auspices of a Faculty Committee. The exam is conventional (theoretical and practice questions) in format and there are no graduation projects or independent research work or assignments required. The degree qualification from the Police Faculty is issued by the MoI and at this stage only recognized by the MoI.

As the Faculty positions itself to take on the future role of an Academy of Police Sciences, there is need for a comprehensive review and redraft of admissions requirements and internal policies, procedures and regulations. This would include evaluation of current specializations offered and specific divisions between the range of various courses and programs offered through a contemporary Police Science Academy.

There is a need to conduct a further and more comprehensive study of international standards for the accreditation of courses in the institute in order for the degree to be recognized outside of the MoI in Syria, and to give it practical and academic value. This will require extensive consultations with universities and accrediting bodies, and experience both regionally and internationally indicates that this process takes considerable time, high level negotiations and sustainable formal agreements with relevant tertiary institutions and other accrediting agencies..

As mentioned, part of this process includes restructuring the Police Faculty into specialized departments (training, criminal forensics, languages etc) in addition to a curriculum, research and publications centre to prepare and publish literature on Police Sciences relevant to the Syrian context.

Post-graduate program for Police Sciences need to be designed and developed according to tertiary standards for Graduate Diplomas, Masters Degrees and Doctoral Programs. These require a high level of quality and delivery, and must be underpinned by research and academic credibility. High level quality assurance of standards is essential.

In addition post-graduate courses, capacity development is required to ensure sustainability and mechanisms to provide continuing (in-service) training in specialized fields for both police and relevant staff of the MoI in areas such as organised and trans-national crime, border security, passports and immigration, property security, narcotics, people trafficking and emerging issues such as cyber crime, copyright laws and environmental crime.

Cooperation with Universities, Security Institutes and Specialised Agencies

An Academy of Police Sciences based on contemporary best-practice requires cooperative arrangements and partnerships with selected national, regional and where applicable, international universities, security institutes and specialised agencies, to enable appropriate sustainable capacity development and credibility. These agreements are usually formalised in some form of memorandum of agreement (MoA).

There are no current agreements of this kind between the existing Faculty and other organisations, and these would need to be identified, negotiated and formally established, within MoI and other relevant government guidelines.

The Academy would benefit from the establishment of these kinds of extensive cooperation agreements and partnerships with similar institutions to assist with achieving the following:

- On-going capacity development of curriculum and teaching methodologies;

- Exchange of information and experience through the exchange of lecturers and trainers;

- Exchange and sharing of curriculum and educational materials;

- Participation in relevant regional and international course and study programs; and,

- Establishment of advanced studies post-graduate programs.

## 1.3	Rationale for Establishing an Academy of Police Science

Policing in contemporary society should be informed by applied research and comprehensive analysis of criminology and sociology however its application should be practical, cost-effective and relevant to government and community needs. The challenge for a police training institute is to find the balance between practical technical skills of operational policing, and the need for more academically based training as police move into more specialized areas and into higher levels of management and leadership. A well structured, well managed and well resourced Academy of Police Sciences can achieve this, and meet the training and professional development needs of police at all levels, as well as capacity development for staff within the MoI responsible for the policy and strategic management of the delivery of policing services to government and the community.

An effective Academy of Police Sciences meeting contemporary needs learning and education needs is based on the following success criteria:

- A vision and strategic plan;

- Good facilities and organisational structure;

- High standard of education and training curriculum and teaching methods;

- Well structured and planned courses & programs;

- Cooperation arrangements with key agencies;

- Capacity for research and publication;

- Continual (in-service) training programs (short);

- Well equipped library and learning centre; and

- Academic standing and accredited courses.

## 1.4	The Institutional and Legal Framework

The institutional framework currently exists to transform the existing Police Faculty into a state-of-the-art Academy of Police Sciences under the leadership and direction of the MoI. Most importantly, there is an apparent willingness and commitment amongst key stakeholders to achieve this. The project is designed to build on the existing institutional framework, and enable the vision of the MoI to be realised.

The legal status of the Police Faculty would need to be considered and determined. For example, would an Academy of Police Sciences be autonomous or under the policy direction and financial management of a government agency such as the MoI?

The longer-term legal situation of the Academy and the degree of its independence, both administratively and financially, needs to be considered further in accordance with the MoI strategic responsibilities. However, it is recommended that given the importance of police training and education, and the need for this to align with government policy and direction, that at least in the short-term and perhaps even in the longer-term, strategic and management oversight by the MoI will result in more effective and sustainable outcomes.

## 1.5	Regional and International Experience

In recent times, internationally and regionally, there have been significant developments by governments to improve the selection, recruitment and training of police. Law and order is critical to the national security and economic development of a nation, and police play a significant role in this on behalf of government and the community.

Regional experience, in particular, is of considerable value to Syria as it plans to improve the quality and scope of police training and education. Egypt and Saudi Arabia are two excellent examples of neighbouring states which have strategically positioned and appropriately resourced respective Academies of Police Sciences to meet contemporary needs, and are recognised as good models which could be adapted to the Syrian context.

Syria is also in the position to benefit from international standards and best practice in police education and training, and to adapt this best practice, where considered relevant, to meet the context in Syria and the specific needs of government and the community.

# PART II	STRATEGY

## 2.1	Government Strategy

The Syrian Government has demonstrated strong leadership and ownership of a modernisation and reform program underpinned by a socio-economic strategy. With the beginning of the new millennium, the government recognised that further reform requires structural adjustment and administrative changes including improvements to the citizen/ civil service interface. This includes modernisation of the justice sector, and more recently endeavours to improve the quality and type of training available to police.

There is a strong level of commitment from the MoI and Senior Academy Officers for renewal of the current Police Faculty and enhancement of the learning and research capability, including a desire to provide advanced studies in policing and security at a post graduate level. An Academy Development Group (ADG) which includes the national consultant has been established to review all current curriculum and programs. The plan is to establish an Academy of Police Sciences as a centre of excellence in the region delivering a full range of training programs for police, advanced studies for higher level students and a sound research capability.

This is an ideal time to position the Academy of Police Sciences for the future and create an institution enabling high quality well trained police at all levels to serve their Government and the community. This would include the design and implementation of higher level capacity development courses, programs and specific workshops for Police Leadership and staff of the MoI.

## 2.2	UNDP Strategy

UNDP has been requested by the Government of Syria and the MoI to provide technical assistance in establishing an Academy of Police Sciences. Support for sustainable capacity development of the Police Faculty is consistent with the Syrian Government and the State Planning Commission’s recent agreement signed with UNDP for the “Country Program Action Plan (CPAP)” which aims at supporting Syria’s socio-economic reform process, as outlined in the 10th Five Year Plan of the country.

It fits within the Governance priority area and reinforces UNDP’s continuing engagement with the Syrian Government for many years, including development support in governance; such as support to Parliament, modernization of the Justice Sector as well as improving court and administrative services on local and national level. The project will also contribute to the achievement of poverty-related Millennium Development Goals (MDGs), including the promotion of an enabling environment for reform and through regulatory and administrative modernizations.

As outlined in UNDAF Outcome 2: Efficiency and accountability of governance structures at central and local levels strengthened, by Government, civil society and the private sector towards sustainable development; this project will support enhancing the efficiency and accountability of governance structures through reforming policing doctrine and studies as well as developing capacities for advanced learning in the area of police sciences in Syria.  Aligning police studies and training to international standards and implementing a capacity development strategy to expand the Academy to a regional centre of applied research and advanced studies, UNDP aims to promote the professionalization and accountability of policing through a better-trained and practised police sector capable of assuming its role in the socio-economic development of Syria, as well as meeting the emerging regional and global challenges of organized and transnational crime. The project will also focus on leveraging the use of communication technology to improve effectiveness as well as improving the analysis and dissemination of information for use by policy makers.

Furthermore, this project will focus on several cross-cutting issues through supporting a police sector more efficient towards its citizens particularly through training on human rights and gender; including traffic policing and domestic violence as well as capacity development to enhance the professionalism of the police sector in its interaction with citizens.  International treaties and conventions ratified by the Syrian Government, particularly in the area of human rights, will also be incorporated when designing the Academy mission statement, organizational structure and curricula while project strategy will focus on harmonizing with international standards of policing through modernizing the police sector as well as sensitizing to such issues.  As such, the project is an excellent entry point for integrating human rights orientation for the Syrian police force in order to improve state- citizen interface within the broader context of socio-economic reform in Syria.

UNDP is in a prime position to assist the Government and the MoI through its ability to facilitate a systematic approach to capacity assessment and needs, build partnerships, coordinate between the various parties involved, obtain knowledge from global sources and experiences, develop capacities, and assist with donor coordination and fund raising efforts.

## 2.3	Project Strategy

Based on comprehensive needs assessment including consultation with key stakeholders and lessons learnt from regional and international experience, the project will focus on targeted strategies to establish an Academy of Police Sciences through organisational and capacity development of structure, systems, procedures and personnel within the existing Police Faculty. The program strategy will be to use a three-year project with an emphasis on ownership and sustainability from inception thus enabling the transformation of the existing police faculty to a regional centre of excellence for police learning and education.

There are two key program components or outputs, in addition to a component on program management, designed to support the program goal and longer-term outcome. These outputs provide a conceptual and strategic framework for the duration of the program:

Output 1: 	The Establishment of the Police Sciences Academy including Strategy, Structure and Systems

Review and renewal of the vision, strategic framework, organisational structure and all procedures and regulations in relation to positioning the Academy for the future

Output 2:	Capacity Development for Training, Education, Research and Advanced Studies provided within the Academy

Upgraded and sustainable mechanisms in place for providing contemporary curriculum and courses, adult learning methodologies, applied research and advanced studies capability

Developmental Goal:

Promotion of democratic governance and an enabling environment for sustainable human development

Program Outcome:

The Academy of Police Sciences in Syria is established for supporting reform initiatives in the security sector.

Intended Output:

Establishment of an Academy of Police Science (APS) as an academic and training resource providing studies and research in criminology and security as well as an educational centre for higher and lower level law enforcement officers.

Outcome Indicator:

An Academy capable of designing, renewing and delivering high quality course, programs and advanced studies, and undertaking applied research based on best practice and international standards in policing science

Cross-Cutting Issues:

A significant strategic focus of curriculum and course renewal is the mainstreaming of cross-cutting issues including gender and equity, and the rights of individuals and vulnerable groups in relation to law enforcement. Discussions with senior members of the Police Faculty have already determined that DV curriculum and support material designed and developed for the Family Protection Units within the Syrian Commission of Family Affairs will be mainstreamed into curricula throughout the Faculty courses and programs.

## 2.4	Project Outputs and Activities

The project will focus on achieving the following outputs and objectives (refer to Strategic Results and Resources Framework Part VI for further details).

OUTPUT 1: THE ESTABLISHEMNT OF ACADEMY OF POLICE SCIENCES INCLUDING STRATEGY AND STRUCTURES

Objective: 	Sustainable mechanisms for APS strategy, structure, systems and procedures strengthened.

This output would provide support to implement the strategic framework and structure of the Academy and contribute to enhancement of physical infrastructure and equipment. It would also assist to redraft key regulations for the Academy of Police Sciences and design and implement automated systems for student and staff records, and the electronic storage of all curriculum and learning materials.

Activities to support this output:

1 (i) Define and agree on a vision for the Academy of Police Science (APS), and develop a strategic plan to support the vision and an organisational structure to implement the plan:

The range of activities here include a study tours/s of regional best practice in Academies of Police Science and Workshops to define and agree on a vision for the Academy, and develop a strategic plan to support the vision. Conduct of a Workshop to finalize the new organisational structure to implement the plan. This activity would also include redesigning the current physical layout to fit the new structure and redesigning Terms of Reference (roles and responsibilities) for all current and new positions within the new structure.

1 (ii) Contribute to the enhancement of the physical infrastructure of the APS:

This activity will contribute to the enhancement of the physical infrastructure of the APS including equipment and facilities. Following further consultations it may include minor refurbishments in some areas and the provision of desks, chairs, filing cabinets and audio-visual equipment in selected training rooms.

1 (iii) Review and redraft new policies and procedures related to admission and graduation requirements and internal regulations for students:

This will require the establishment of a Working Group with Technical Assistance to redraft new policies and procedures related to admission and graduation requirements and internal regulations for students.

1 (iv) Administrative Information and Communications Technology (ICT) systems including internal intranet communications strengthened

In this activity all current manual systems will be reviewed and updated in preparation for automation. It will include design and implementation an information technology based (automated) administrative system and internal intranet communication between the key sections and faculties in the Academy. This would include an automated system for student and staff records, as well as electronic storage and retrieval of all curriculum and learning materials.

OUTPUT 2: CAPACITY DEVELOPMENT FOR TRAINING, EDUCATION, RESEARCH AND ADVANCED STUDIES

Objective: 	Sustainable mechanisms for training, education, research and advanced studies strengthened.

The purpose of this output is to upgrade and implement sustainable mechanisms for the selection and capacity development of trainers, and the revision and updating of all curriculum and teaching methodologies based on adult learning principles. It would also include the establishment of a state-of-the art research and library (learning centre) facility and an advanced studies capability for the provision of post-graduate programs and qualifications in the future. This would require the establishment of extensive cooperation agreements with selected regional and international Police Academies, Security Institutes and Specialized Agencies.

Activities to support this output:

2 (i) Design and develop selection criteria and regulations for the recruitment of APS trainers:

In this activity the selection criteria and regulations for the recruitment of Academy trainers and education support staff will be reviewed and updated to fit the new vision and structure of an Academy of Police Sciences. Workshops will be conducted to familiarise all staff with the new recruitment and selection mechanisms.

2 (ii) Design, development, delivery and evaluation of capacity development and train-the-trainer programs for all APS trainers:

This activity will follow a capacity assessment and will focus on the design and implementation of a comprehensive capacity development program for trainers including training-of-trainers for sustainability. It will provide the opportunity for all staff to enhance their skills and knowledge in delivering high quality training and education for police at all levels.

2 (iii) Revise and update curriculum and learning methodologies to meet new faculty and course requirements:

Activities here will include the revision and updating of all curricula to meet new faculty requirements and emerging training needs for police and security forces in Syria including high level crime, criminology and police leadership training. It will also include study tour/s to selected relevant institutions in the region and the establishment of a curriculum and assessment capability which would provide support to all faculties on curriculum design, student assessment and course evaluation. Establishment of agreements for Faculty exchange programs with other regional policing academies will another feature of this activity.

2 (iv) Design and develop a Research and Learning Centre capability consistent with best practice in the region and to international standards:

This will include the identification of a suitable location with the Academy campus and establishment of a state-of the art Research and Learning Centre including a library with the acquisition of more books and reference materials, on-line facilities, audio-visual resources, reading and study areas, and an appropriately staffed and funded Research capability.

2 (v) Establish cooperation arrangements and formal Memoranda of Agreement (MoA) with selected regional and international Academies of Police, Universities, Security Institutes, and Specialized Agencies for sharing of information, exchange of curriculum and staff, course participation and the establishment of advanced studies:

This activity plans to assist the MoI to facilitate and secure cooperation arrangements and formal Memoranda of Agreement (MoA) with selected regional and international Academies of Police Science, Universities, Security Institutes, and specialized Agencies for sharing of information, exchange of curriculum and staff, course participation and the establishment of advanced studies. It will include regional study tours to explore options for cooperation agreements and clarify protocols and mechanisms for engagement, sharing of information and exchanges of staff.

2 (vi) Identification of strategies and preparation of a Position Paper with options, recommendations, and indicative costs for the establishment of advanced studies and accredited post graduate programs within the APS:

This final activity in output 2 will assist to facilitate negotiations with key tertiary institutions and tertiary level accrediting agencies to establish post-graduate programs in the APS. It will assist the preparation of a position paper with recommendations and an indicative budget for establishing and maintaining a Faculty of Advanced Studies in the APS, as well as the setting up of a pilot.  A series of Workshops will be conducted with key stakeholders to progressively present options and recommendations, and seek agreement on the way forward to sustainably establish an Advanced Studies Faculty.

## 2.5	Duration of Project

The timeframe for the pilot project is 3 years. The attached Strategic Results and Resources Framework (see Part VI) outlines the various intended activities that will be undertaken over the life cycle of this pilot project as well as the output indicators and the required inputs.

## 2.6	Intended Beneficiaries

While the key beneficiaries of the project will be the MoI and the Police Faculty, which are the principle administrative and delivery mechanisms within the government for police recruitment, training and education, other target beneficiaries will include:

- The education and administrative staff of the Police Faculty;

- The students who participate in formal programs and courses;

- Police who participate in continuing training and professional development seminars and workshops;

- The Police Force as a whole by the opportunities to advance the performance and professionalism of police through state-of-the-art curriculum and research relevant to contemporary policing needs in Syria;

- The Government of Syria in contributing to its goals of reform and modernisation; and ultimately,

- The people of Syria.

# Part III	MANAGEMENT ARRANGEMENTS

The project will be implemented using the National Execution Modality (NEX).  Through NEX operational arrangement, the UNDP country office along with cooperating government Ministry (MoI) assumes responsibility, and accountability, for the management and implementation of the project.  This project is planned to run for a period of three (3) years or 36 months.  The project will operate in accordance with UNDP regulations, including those for procurement and accounting.

The lead organization for this project will be the MoI and the direct Implementing Partner (IP) will be the Police Faculty. The IP will be responsible for the overall implementation of the project and the production of the outputs in accordance with the Annual Work Plans (AWP). It will also be responsible for supervising project staff and consultants in coordination with UNDP, ensuring the proper equipment and logistics are in place together with the National Project Director (NPD) for workshops, study tours, training and other events. The IP will be responsible for providing in kind contribution of office space. Staff of the IP will support the project as part of capacity development requirements.

## 3.1	Project Board

The Project Board (PB) will be established to generate consensus basis management decisions for the project when guidance is required by the NPD. Based on the approved Annual Work Plan (AWP), the PB reviews and approves project stage plans and authorizes any major deviation from these agreed stage plans. It is the authority that signs off on the completion of each stage plan as well as authorizes the start of the next stage plan. It ensures that required resources are committed and arbitrates any conflicts within the project or negotiates a solution to any problems between the project and external bodies.

In addition, it approves the appointment and responsibilities of the NPD and the Project Assurance responsibility to the UNDP Country Office.

The Project Board will be composed of:

    - Representative(s) of the SPC;

    - Representatives of the MoI;

    - Representative(s) of UNDP;

    - Representative(s) of the Committee to for the Development of the "Major Bassel El Assad Police Science Faculty"

    - The National Project Director

Other stakeholders may be invited on an ad hoc basis.

The key roles and responsibilities of the PB will be to:

- Discuss policy implications of the project and provide advice and guidance to facilitate the link between program activities and national development initiatives;

- Provide oversight of program activities and resources;

- Review the achievement of program interventions bi-annually or as required;

- Review and validate any new project proposals;

- Keep the government and relevant agencies informed of project progress;

- Provide guidance and oversight to the NPD and Program Management Team;

- Approve revision of AWPs for project supported outputs and activities.

## 3.2	Project Management Team

The project management team will consist of the NPD, who is expected to be specialized in law enforcement and security, and has experience in policing education and academic matters (Terms of Reference in Annex 2). The NPD should also have planning and capacity development experience and demonstrated ability to facilitate outcomes.

In addition to the NPD, the project management team will consist of an Output Manager for Capacity Development and IT, and an Administration/Financial Assistant (ToR to be defined by NPD). International and national consultants supervised by the NPD will undertake part of the project activities, according to the Strategic Results and Resources framework and the AWP.

All staff and other short-term staff hired if needed, will be recruited by UNDP according to its rules and regulations.

The NPD has the authority to run the project on a day-to-day basis on behalf of the PB within the constraints and policy guidance laid down by the PB. The NPD is responsible for day-to-day management and decision-making for the project, to ensure that the expected results are achieved to the required standard of quality and within the specified constraints of time and cost, according to the Annual Work Plan.

Under the leadership of the NPD, the project management team will assist with preparation of the Annual Work Plan, Quarterly Work Plans and progress reports, and will maintain up-to-date communication and monitoring plans and logs.

The team remains in constant communication with the UNDP team.

## 3.3	Levels of Project Management

There are three critical aspects of program management:

- High level policy direction and alignment with national development processes;

- Link between the high level policy and day to day implementation;

- Day to day coordination and implementation of activities, information sharing and partnership collaboration.

## 3.4	Project Management Office

The Project Management Office (PMO) will be established in an area within the existing structure of the Police Faculty to ensure effective engagement with counterparts and to accommodate the Project team including the NPD, the Capacity Development/IT Output Manager, Administration/Finance Assistant and other professional staff as required.

The PMO will be equipped with other short-term professional and national/international consulting staff as per the project Resources and Results Framework, in order to ensure intensive and extensive coordination for implementing the project including both technical and management aspects.

## 3.5	Project Assurance

The UNDP Syria Country Office will play the role of project assurance by carrying out objective and independent project oversight and monitoring functions. This role ensures appropriate project management milestones are managed and completed.

UNDP CO will support the Project by coordinating the activities of AECI and possibly other UN agencies involved in the implementation of the project and ensuring the effective participation of all the concerned parties in order to achieve the desired results. UNDP, through its technical wing UNDP SURF-Arab States, will also play an advisory role and provide technical backstopping and referrals on comparative experiences and lessons learned.

The above Project Management structure can be illustrated as follows:

## 3.6	Recruitment, Procurement and Sub-Contracting

All recruitment and procurement for the project (and sub-contracting if required) will be undertaken consistent with the procedures outlined in the UNDP Procedures Manual.

# Part IV	MONITORING AND EVALUATION

Monitoring, review, evaluation and reporting are key aspects of any capacity development program. A systematic and planned approach to this is essential as is a clear assessment and management of associated opportunities and risks associated with implementation.

Monitoring and evaluation (M&E) aims primarily to provide project stakeholders with early indications of the quality, quantity and timeliness of progress towards delivering intended results, in accordance with the Annual Work Plan. M&E also contributes to an overall assessment of project outcomes, achievements and impacts.

The PB, together with the MoI in close collaboration with the Police Faculty, will be responsible for overall project oversight in collaboration with UNDP.

## 4.1		Monitoring, Evaluation and Reporting

In carrying out such monitoring activities, a number of tools are created and updated in different timeframes for the project:

Within the annual project cycle:

- Quality Log:  Progress and quality of the deliverables being produced will be assessed based on the quality criteria established in the indicators and Deliverable Description and planned schedule and recorded in the Quality Log.  If changes are required, the Deliverable Description and/or schedule will be updated.

- Issues Log:  Any project issues will be recorded in the Issues Log to facilitate tracking and resolution.

- Risk Assessment Log:  The Risk Assessment Log will be updated by reviewing the internal and external environments that effect the project implementation, and associated risk management plans.

- Lessons Learned Log: Project lessons learned should be actively captured to ensure ongoing learning and adaptation within the organization.

- Annual Work Plan Monitoring Tool: Together with project issue/risk logs, the AWP Monitoring Tool should be used for the project review purpose.

- Project Quarterly Progress Report:  Quarterly monitoring progress reports will be submitted by the NPD to Project Assurance. Such progress reports should form a basis for decisions regarding further disbursement of UNDP resources to the Implementing Partner (Police Faculty) through the lead agency (MoI).

- Annual Project Report: The APR will be submitted along with the AWP to the PB.

Additional reports may be requested, if necessary, during the project life cycle.

Annually:

- Annual Review: An annual project review will be conducted by the PB during the fourth quarter of each year as a basis for assessing performance of the project. Such review is done in the context of the UNDAF Annual Review.

- This annual review will involve all key project stakeholders including the Lead Agency (MoI) and the Implementing Partner (Police Faculty), and focus on the extent to which progress has been made towards outputs, and that these remain aligned to appropriate outcomes. The review should update output targets and results achieved.

An independent (external) evaluation will be conducted at the end of the project.

## 4.2	Opportunities and Risks

Opportunities

The Project provides the opportunity to establish an Academy of Police Sciences in Syria with the goal of making the institution a centre of excellence in the region. Implementation of this project is timely and the outputs as agreed with the MoI/Police Faculty are designed to embed sustainable systems and capacity development for the establishment of the Academy as envisioned by the Government of Syria, the MoI and Senior Police Faculty staff.

For the Police Faculty, the project provides the opportunity to improve the quality and range of police education and training courses, programs and other professional development and continuing education initiatives for police officers.

For MoI there is the opportunity to demonstrate good governance as a key agency in the GoS responsible for the safety and security of Syrian citizens through the delivery of policing services.

For the Police Faculty and the MoI this project also provides the opportunity to gain much needed assistance to establish the Academy of Police Sciences and assist the existing Police Faculty to achieve its vision in collaboration with UNDP and other potential development partners.

Risks

A detailed Risk Assessment Log will be prepared as part of the Work Plan scheduled following inception of the program, and further negotiations with the MoI, Police Faculty, Development Partners and other key stakeholders. However a brief summary of risks associated with implementation includes:

- Delays in implementation due to recruitment of key project team personnel including NPD, and national and international consultants;

- Lack of agreement on the vision, strategy and organisational structure and legal status of the Academy of Police Sciences;

- Capacity and willingness of Faculty staff to respond to the changes required;

- Lack of feedback of lessons learned from review, monitoring and evaluation;

- Expectations are not well managed for the significant transformation required for the Police Faculty, particularly the establishment of a sustainable Advanced Studies Faculty; and,

- Insufficient resources are not made available in the longer-term to establish and maintain the Academy of Police Sciences as a state-of-the-art police training and educational institution.

# PART V	LEGAL CONTEXT

This PD shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement (SBAA) between the Government of the Syrian Arab Republic (SAR) and UNDP, signed by the parties on 12 March 1981. The host-country implementing unit shall, for the purpose of the Standard Basic Assistance Agreement, refer to the government cooperating agency described in that agreement.

The following types of revisions may be made to this PD with the signature of the UNDP Resident Representative only, provided he has assured that the other signatories of the PD have no objections to the proposed changes:

- Revisions in, or additions of, any of the annexes of the PD; and

- Revisions, which do not involve significant changes in the immediate objectives, outputs or activities of the project, but are necessitated by the rearrangement of inputs already agreed to, or by cost increases due to inflation; and mandatory annual revisions, which re-phase the delivery of agreed project inputs or expert or other costs due to inflation or take into account expenditure flexibility.

If major changes (whether to increase or limit the project) are needed then a Substantive Revision Document will be prepared detailing the changes and all their implications.  The Substantive Revision Document needs to be signed by all parties to the original PD.

# PART VI 	STRATEGIC RESULTS AND RESOURCES FRAMEWORK

| Intended Output: Establishment of an Academy of Police Science (APS) as an academic and training resource providing studies and research in criminology and security as well as an educational centre for higher and lower level law enforcement officers |
| --- |
| Outcome Indicator: An Academy capable of designing and delivering high quality course, programs and advanced studies, and undertaking applied research based on best practice and international standards in policing science |
| Applicable UNDAF Outcome: Efficiency and accountability of governance structures at central and local levels strengthened, by Government, civil society and the private sector towards sustainable development; |
| Intended Outputs | Output Indicators | Indicative Activities | Inputs |
| 1. Strategic framework, structure and regulations revised and renewed | Vision, strategic plan and organisational structure finalized and approved by the MoI | Define and agree on a vision for the Academy of Police Science (APS), and develop a strategic plan to support the vision and an organisational structure to implement the plan: 1. Study tour abroad (Arab region) for APS Development Group to consider current models of structure, function and courses provided by Academies of Police Science (eg Egypt, Saudi Arabia) 2. Workshops (2) to finalise the vision, strategic plan overview and organisation structure for the Academy 3. Prepare specific TORs for the role and function of Administrative and Education Sections, Departments and Centres in the new organisation structure 4. Technical Assistance to redesign the current physical layout to fit the new structure and advise on any longer term requirements 5. Redesign TORs for current and new positions and where necessary make appointments to these positions based on selection criteria 6. Workshops (2), work-based training and mentoring of APS senior personnel and staff to assist implementation of new structure | UNDP CO Project Board The Project Team and senior members of APS Travel expenses for Study Tour: US$ 12,000 National consultant: US$ 100*20 working days=US$ 2000 Printing and publications costs for strategic plan and other materials: US$ 2,000 Workshop costs: 4* 4,000= US$ 16,000 Sub-total: US$ 32,000 |
|  | Agreed enhancement to physical infrastructure and procurement of equipment completed | Contribute to the enhancement of the physical infrastructure of the APS: 1. With Technical Assistance undertake assessment of infrastructure and prepare a plan for the longer term refurbishment and maintenance of the Academy 2. Identify a physical fitness and training area and provide basic equipment 3. Refurbish and set up a model training room/s with desks, chairs, filing cabinets and audio visual equipment (OHP) | UNDP CO Project Board (PB) The Project Team and senior members of APS National consultant: US$ 100*20 working days=US$ 2000 Equipment: US$ 20,000 Sub-total: US$ 22,000 |
|  | New policies and procedures redrafted and submitted for approval in appropriate manner | Redraft new policies and procedures related to admission and graduation requirements and internal regulations for students: 1. Establish a working group with APS/ MoI staff and technical Assistance to review and update admission and graduation requirements 2. Establish a working group with APS/ MoI staff and Technical Assistance to review and update internal regulations for students 3. Submit the updated admission and graduation requirements and updated internal regulations to MoI for approval | UNDP CO PB The Project Team and senior members of APS National consultant: 100*20 working days = US$ 2000 Workshop costs: 2* 4,000= US$ 8,000 Printing and publications costs: US$ 3,000 Sub-total: US$ 13,000 |
|  | Automated student and staff records systems, curriculum materials and internal intranet communication system designed and implemented | Administrative Information and Communications Technology (ICT) systems including internal intranet communications strengthened 1. Review and update student and staff manual records system to ensure suitability for automation 2. Implement an automated system for student and staff records 3. Design and implement an intranet system for communication between Dean and senior staff | UNDP CO PB The Project Team and senior members of APS National consultant: 100*30 working days = US$ 3000 Equipment US$ 40,000 Sub-total: US$ 43,000 |
| Strategic Framework, Structure and Regulations | Total: US$ 110,000 |

| Intended Outputs | Output Indicators | Indicative Activities | Inputs |
| --- | --- | --- | --- |
| 2. Upgraded and sustainable mechanisms in place for providing curriculum and research, and advanced studies capability | Selection criteria and regulations to select training and educational staff developed and submitted for approval | Design and develop selection criteria and regulations for the recruitment of APS trainers: 1. Design of selection criteria and regulations for recruitment of trainers to be implemented over time 2. Conduct workshop to familiarize existing trainers and other staff of APS and MoI on new selection mechanisms 3. Submit the new recruitment policy and procedures for approval | UNDP CO PB Project Team and senior APS staff National consultant: 100*30 working days = US$ 3000 Workshop costs: 1* 4,000= US$ 4,000 Sub-total: US$ 7,000 |
|  | Capacity development program for trainers designed, delivered, evaluated and revised as necessary | Design, development, delivery and evaluation of capacity development and train-the-trainer programs for all APS trainers: 1. Develop a training course to upgrade the capacity of current staff to design and deliver courses, programs, workshops and field based training in accordance with academic, training and practical needs of the academy and the new faculty structure 2. Deliver and evaluate the training capacity development program through the train-the-trainer concept so that selected trainers can train and up-skill future trainers when recruited | UNDP CO Team/APS staff International consultant: 500*40 working days = US$ 20,000 Travel expenses Intl Conslt: US$ 12,000 Translation and Publication costs: US$ 4,000 Workshop costs: 3* 4,000= US$ 12,000 Sub-total: US$ 48,000 |
|  | Curriculum revised and updated to meet new faculty requirements | Revise and update curriculum and learning methodologies to meet new faculty and course requirements: 1. Study tours abroad (Arab region) for selected APS senior staff responsible for education 2. Technical assistance to design and develop new curriculum and courses in collaboration with Faculty staff to transfer skills 3. Translation and printing of curriculum and support materials 4. Establish agreement for Faculty staff exchange with other regional Policing Academies and Security Institutes and conduct pilot exchange programs 5. Design and conduct Workshops to introduce staff to the new curriculum and teaching approaches and assessment and evaluation methodologies | UNDP CO The Project Team and senior members of APS Travel expenses for Study Tour: US$ 12,000 International consultant: 500*40 working days = US$ 20,000 Travel costs (DSA only) US$ 8000 Translation and Publication costs: US$ 10,000 Workshop costs: 3* 4,000= US$ 12,000 Sub-total: US$ 62,000 |
|  | Research and Learning Centre established and procurement completed | Design and develop a Research and Learning Centre capability consistent with best practice in the region and to international standards: 1. Identification of the new location for the Research and Learning Centre 2. Design and implement the staffing structure of the Research Unit and procure materials and IT needs 2. Strengthening of library facilities including furniture, book cases and equipment and audio-visual materials 3. Procurement of books, audio-visual and other learning materials 4. Design and implement On-line library automated system 5. Procurement and setting up printing equipment for publications | UNDP CO PB The Project Team and senior members of APS National consultant : 100*60 working days = US$ 6000 IT equipment: US$ 25,000 Furniture, books and equipment: US$ 25,000 Printing and Publication Equipment: US$ 10,000 Sub-total: US$ 66,000 |
|  | MoAs for selected cooperation arrangements negotiated and formalized | Establish cooperation arrangements and formal Memoranda of Agreement (MoA) with selected regional and international Academies of Police, Universities, Security Institutes, and specialized Agencies for sharing of information, exchange of curriculum and staff, course participation and the establishment of advanced studies: 1. Study tour/s (Arab Region) to explore options for cooperation agreements with relevant key institutions and agencies (regional and international) 2. Clarify protocols for engagement and cooperation with selected key institutions and negotiate to establish MOAs 3. Establish protocols and mechanisms for exchange of curriculum materials and development of teaching methodologies 4. Establish agreement and logistics for staff exchange with other relevant and appropriate institutions and conduct pilot 5. Identify suitable programs, workshops and study programs in regional police and security institutes for participation by APS staff and other Police 6. Develop procedures and regulations to facilitate exchange fellowships on post graduate studies for selected students with similar regional and international institutions | UNDP CO Project Board The Project Team and senior members of APS Travel expenses for study tours: US$ 12,000 National consultant : 100*40 working days=US$ 4000 International consultant: 500*20 working days = US$ 10,000 Travel costs (DSA only) US$ 4000 Sub-total: US$ 30,000 |
|  | Proposal for Advanced Studies and Accreditation completed and submitted to MOI for approval | Identification of strategies and preparation of a Position Paper with options, recommendations, and indicative costs for the establishment of advanced studies and accredited post graduate programs within the APS: 1. Negotiations with key national tertiary institutions and tertiary level Accrediting agencies to establish post graduate programs within the APS 2. Preparation of a Position Paper/ Concept Proposal with recommendations and indicative budget for establishing a Faculty of Advanced Studies in the APS 3. Conduct Workshops (3) with key stakeholders to progressively present options and recommendations for the establishment of the Faculty of Advanced Studies 4. Seek avenues for funding to support the establishment of a Faculty of Advanced Studies within the APS 5. Establish pilot program within APS | UNDP CO PB The Project Team and senior members of APS National consultant : 100*50 working days=US$ 5,000 Workshop costs: 3* 4,000= US$ 12,000 Sub-total: US$ 17,000 |
| Curriculum, Research and Advanced Studies | Total: US$ 236,000 |

| Activities | US$ 340,000 |
| --- | --- |
| Project Management 1 NPD, 1CD/IT output manager, 1 Admin/Finance Asst | US$ 210,000 |
| TOTAL | US$ 550,000 |

# Annexes

# Annex 1: Police Faculty - Overview of Main Courses and Curriculum

- The currently applied curriculum in the Police Faculty is designed and determined by Administration Institute with reports to the Ministry of Interior

- The material used includes basic information written by specialized and experienced officers.  However, they are not academically trained and this is not sufficient to improve the capacity of the training to training in the field of police science.

- As for the lecturers; there is currently a committee to review/reform offered curriculum. It is made up of 4 persons qualified in different fields ranging from those strong in field experience as well as the academic and scientific

- Curriculum is always dependent of the specialty and is designed accordingly.  It is divided into the following:

- Curriculum for District Directors:

  - This programme is not less than one year

  - Degree required: Law Degree

  - Courses are:

    - Personal Status

    - Organization of Police Service

    - Laws and Regulations pertaining to Police Sector

    - Criminal and Technical Investigations

    - Public Relations

    - Political Guidance

    - Laws & Police Regulations

    - Internal Police Organization (Hierarchy)

    - Reporting Regulations

    - Prison Regulations

    - Security

    - Property Security

    - Administrative Laws

    - Emerging Crimes (money laundering)

    - Foreign Languages (English & French)

    - IT Skills

    - Immigration & Passports

    - Communication Rules

    - Vehicle Mechanics

    - Inspection

    - Registrars

    - Quality Assurance

    - Discipline & Protocol

    - Weapons and Target Practice

    - Combat

    - Topography

    - Strength Training

    - Civil Defense

    - First Aid & Forensics

    - Drugs

- Curriculum for Doctors:

  - This programme lasts six (6) months

  - Degree required: Medical Degree

  - Courses are:

    - Administrative Laws

    - Political Guidance

    - Inspection

    - Internal Regulations and Regulations of Policing

    - Reporting Regulations

    - Laws pertaining to Policing

    - Organization of Police Service (Heirarchy)

    - First Aid & Forensics

    - Foreign Language (English & French(

    - IT Skills

    - Driving & Mechanics

    - Weapons

    - Target Practice

    - Discipline & Protocol

    - Strength Training

- Curriculum for Mid-Career Officers:

  - This programme is four (4) to eight (8) months

  - Degree required: High School; 3 years or more professional experience

  - Courses are:

    - Laws and Regulations pertaining to Police Sector

    - Registrars

    - Laws & Police Regulations

    - Internal Police Organization (Hierarchy)

    - Reporting Regulations

    - Political Guidance

    - Immigration & Passports

    - Criminal Investigations

    - Sentencing Laws

    - Prison Regulations

    - Traffic Regulations

    - IT Skills

    - Foreign Languages (English & French)

    - Discipline & Protocol

    - Target Practice & Weapons

    - Leadership Training & Combat

    - Communications

    - Drugs

    - First Aid and Forensics

    - Strength Training

- Curriculum for Nursing Mid-Career Officers:

  - This programme is four (4) to eight (8) months

  - Courses are:

    - Registrars

    - Organization of Police Service

    - Reporting Regulations

    - Political Guidance

    - Immigration & Passports

    - Penal Code

    - Typing

    - Prison Regulations

    - IT Skills

    - English

    - French

    - Discipline & Protocol

    - Weapons and Target Practice

    - Combat

    - Laws and Police Regulations

    - Drugs

    - First Aid and Forensics

    - Strength Training

- Curriculum for Basic Training Civilian Officers:

  - This programme is eight (8) months

  - Degree required: Preparatory or High School Degree

  - Courses are:

    - Reporting Regulations

    - Laws and Regulations pertaining to Police Sector

    - Regulations of Policing

    - Internal Regulation of Policing

    - Political Guidance

    - Public Relations

    - Immigration & Passport

    - Prison Regulations

    - Technical and Criminal Investigations

    - Civil Defense

    - Security

    - Foreign Languages (English & French)

    - IT Skills

    - Registrar

    - Traffic Regulations

    - Penal Code

    - Property Security

    - First Aid & Forensics

    - Weapons and Target Practice

    - Combat

    - Strength Training

    - Drugs

- Curriculum for Female Officers; Mid-Career:

  - This programme is eight (8) months

  - Courses are:

    - Laws and Regulations pertaining to Police Sector

    - Internal Police Organization (Hierarchy)

    - Reporting Regulations

    - Internal Police Regulations

    - Political Guidance

    - Laws & Police Regulations

    - Immigration & Passports

    - Prison Regulations

    - Criminal Investigations

    - Civil Defence

    - Security

    - Public Relations

    - Foreign Languages (English & French)

    - IT Skills

    - Registrars

    - Traffic Regulations

    - Penal Code

    - Property Security

    - First Aid & Forensics

    - Discipline & Protocol

    - Weapons and Target Practice

    - Combat

    - Strength Training

    - Drugs

- Basic Training Curriculum for New Recruits:

  - This programme is eight (8) months

  - Courses are:

    - Organization of Police Service

    - Criminal Investigation

    - Registrars

    - Laws and Regulations pertaining to Police Sector

    - Reporting Regulations

    - Prison Regulations

    - Political Guidance & Public Relations

    - Drugs

    - Internal Police Structures

    - Traffic Regulation

    - Security and Civil Defence

    - Foreign Languages (English & French)

    - IT Skills

    - First Aid & Forensics

    - Discipline & Protocol

    - Weapons and Target Practice

    - Combat

    - Strength Training

- Curriculum for Civilian Driver; New Recruits:

  - This programme is eight (8) months

  - Degree required: Preparatory Degree

  - Courses are:

    - Laws and Regulations pertaining to Police Sector

    - Registrars

    - Organization of Police Service

    - Reporting Regulations

    - Political Guidance

    - Security

    - Criminal Investigation

    - Prison Regulations

    - Public Relations

    - Internal Police Regulations

    - Traffic Regulations

    - Civil Defence

    - Foreign Languages (English & French)

    - Discipline & Protocol

    - Weapons and Target Practice

    - Combat

    - Strength Training

    - Laws and Regulations of Policing

    - Drugs

    - First Aid & Forensics

    - Arabic Language

    - Driving

    - Mechanics

# Annex 2: Terms of Reference for the National Project Director (NPD)

    - Background:

The project on providing technical support assistance in establishing the Academy of Police Sciences in Syria, as well as implementing capacity development programs for the ministry of Interior (MoI) is scheduled over a three year timeframe. The institution is envisioned to be an academic and training resource in police sciences including research studies in criminology and security as well as an educational centre for high and lower level law enforcement officers on best practices and international standards in policing science. The Academy is also envisioned to mainstream a scientific approach as well incorporating and supporting social sciences in order to further study and analyse best practices in law enforcement, crime prevention and reducing recidivism. It will serve to elevate the level of professional training, as well as introducing new techniques and models to law enforcement in Syria. The centre will also serve as a way of disseminating relevant and updated information on crime prevention, criminal rehabilitation, security and policing to relevant stakeholders on the national level.

II. Objective:

The National Project Director (NPD), working in close cooperation with the MoI as Lead Agency and the Police Faculty as the Implementing Partner (IP), other participating agencies and UNDP, is responsible for the delivery of the project outputs as per the Project Document and in accordance with UNDP rules and regulations.

III. Responsibilities:

- Overall responsibilities:

  - Assume overall responsibility for the successful execution and implementation of the project towards achieving the outputs as per the Project Document.

  - Represent the Project Board Meetings and other Reviews.

  - Ensure the adherence of project activities to the approved project work plan.

  - Ensure the proper use of project resources.

  - Ensure that UNDP rules and regulations for nationally executed projects are implemented in all project activities, including procurement and recruitment.

  - Represent the national executing agency at project and annual reviews.

  - Support resource mobilization efforts to increase resources in cases where additional outputs are required;

The National Project Director will be assisted by a Capacity Development/IT Output Manager and an Administration/Finance Assistant as well as national and international consultants as outlined in the Project Document (PD).

- Management:

  - Supervise the work of the project team, consultants, and sub-contractors.

  - Manage the project’s financial resources to achieve the completion of project outputs.

  - Manage the project’s material resources, ensuring that any vehicles )if utilised), office equipment, furniture, etc are properly maintained and used correctly for implementation of project activities.

  - Ensure that the required work plan is prepared and updated in consultation and agreement with UNDP and distributed to the Government (Counterpart Ministry).

  - Initiate and administer the mobilization of project inputs under the responsibility of the Implementing Partner.

  - Support to media/communications work of the project;

  - Ensure that UNDP is invited to all stakeholder meetings.

- Technical:

  - Identify and locate, in consultation with UNDP, the services needed to move the project along, and prepare terms of reference and contracts according to UNDP authorized procedures.

  - Arrange, in consultation with UNDP, the recruitment of project professional and support staff in line with approved recruitment processes.

  - Prepare annual and detailed quarterly work plans;

  - Obtain approval from UNDP on annual and quarterly work plans during their preparation and present the final work plans to the Project Board for approval.

  - Prepare papers for the Project Board.

  - Prepare funding proposals if required.

  - Draft technical and other documents as required.

  - Share with UNDP draft document and outputs for comments, as well as final products.

  - Develop mechanisms for updating stakeholders on progress of project.

  - Participate in all project meetings and annual reviews.

- Facilitation:

  - Ensure that UNDP’s name is mentioned in all publications, workshops, and project’s activities;

  - Serve as the focal point of the project for coordination of the project activities with UNDP, the Government (including SCFA) and other partners on behalf of the project.

  - Ensure that the Government inputs for the project are available;

  - Liaise with the UNDP Programme Officer on weekly basis to ensure proper monitoring and realization of results.

  - Liaise with UNDP staff to organize the annual review, evaluation missions and project visits.

  - Liaise with various stakeholders (academic, media, government, donors, etc).

  - Lead efforts to build partnerships for the support of outcomes indicated in the project document.

  - Support resource mobilization efforts to increase resources in cases where additional outputs and outcomes are required.

- Financial

  - Act on behalf of the executing agency in preparing and adjusting commitments and expenditures.

  - Act as the sole authorizing officer for all project financial transactions (i.e. approve all financial expenditures and sign all direct payments.)

  - Authorize commitments of resources and expenditures for inputs including staff, consultants, goods and services and training

  - Hold Responsibility for delivery of project’s services and achieving annual financial delivery targets;

  - Manage the project resources e.g. vehicles (if utilised), office equipment, furniture and stationery procured under the project and maintain asset register;

  - Ensure that appropriate accounting records are kept and organized;

  - Facilitate and cooperate with audit requirements at all times, as required.

- Reporting

  - Progress towards achieving outputs :

        - Quarterly reports of progress on project activities for each of the activities listed for that quarter in the annual and quarterly workplans.’

        - Annual project report (APR).

        - A Terminal Report at the end of the project, in the approved UNDP format.

        - Technical, policy and briefing papers as requested by UNDP and the executing agency.

        - Any reports requested by UNDP for the TPR meeting (Tripartite Review).

  - Financial reporting:

        - Quarterly financial reports, in the approved UNDP format.

        - Annual financial reports, in the approved UNDP format.

        - Final financial report at the end of the project, in the approved UNDP format.

IV. Reporting Line:

Contractually to the UNDP Resident Representative and technically to both UNDP and the Syrian Commission for Family Affairs.

V. Evaluation:

The renewal of contract will be based on satisfactory mid-term and final performance evaluation by UNDP and the executing agency.

VI. Duration of Contract:  Annual contract, subject to confirmation after three months.

VII:  Qualifications:

The NPD should be a Syrian National with

- at least 10 years management and organisational development experience, including 5 years experience managing strategic policy oriented projects, preferably in the justice sector and/or social/family affairs;

- management experiences should preferably be in development work or at least in working with governments of developing countries;

- experience in managing projects with a strong IT and/or capacity building component highly desirable;

- a higher university degree in humanities, development studies or international relations, preferably from a reputable overseas university;

- have good facilitation skills and be outcome oriented;

- and have excellent spoken and written English, in addition to Arabic.

VIII:  Salary:

The salary will be based on UNDP salary scales.

# Annex 3: ToR for Technical Assistance

To be determined by NPD in consultation with PB

# Footnotes

Non-Commissioned Officer (NCO) level General Duties Police.

The name of the current Police Faculty is the Major Martyr Basel Al-Asad College for Police Sciences.

A dunum is a measure of land area equivalent to one-quarter of an acre.

Academies of Police Science in both Egypt and Saudi Arabia are examples of very good regional institutions which could offer beneficial partnership and collaborative relationships with Syria.

UNDP has been assisting with development for some years but the most recent agreement between the Government of Syria, represented by the State Planning Commission, for the CPAP was signed on June 19th 2008.

# Text boxes

Two (2) Output Manager

Capacity Development/IT

National & International

Consultant/s

National Project Director

Project Assurance

UNDP P.O.

Project Board

- MoI

- SPC

- UNDP

- NPD/Police Faculty

Administration/ Finance Assist

Programme Period: 2007 – 2011

Programme Component:

Democratic Governance

Project Title:

Support to the Establishment of the Academy of Police Sciences in Syria

Project ID:  SYR

Project Duration: 	36 months

(July 2009 – July 2012)

Management Arrangement: NEX

Total Project Budget: US$ 550,000

General Management Support Fee:  US$  10,000

Allocated resources:

- Ministry of the Interior: 2010 	US$ 200,000

- Programme C/S : 2009	US$ 100,000

- TRAC: 2009  		US$ 100,000

- Other :    		US$ 150,000

(To be mobilized during 2010/2012)

- In kind contributions:

  - Office premises & facilities.

The Government of the Syrian Arab Republic (SAR) and the Ministry of Interior (MoI) recognize the importance of an efficient and effective academic and training resource in police sciences for learning and research studies in criminology and security as well as an educational centre for high and lower level law enforcement officers. The Academy will serve to enhance the level of professional training, as well as introducing new techniques and models of law enforcement in Syria.

This project will focus on establishing an Academy of Police Sciences in Syria based on regional best practice and international standards for police education and training. It will contribute to improved performance and professionalism in policing thus enabling Syria to strategically meet law enforcement challenges into the future including domestic crime as well as emerging higher-level organised criminal activity resulting from globalisation such as people trafficking, money laundering and border security.