Good Practices Implementation Plan for DRR

by Dr Gordon Holder

national lead consultant TCP BZE 3202

Summary

This second technical report provided by the national lead consultant is related to the selection and demonstration of the implementation plan of good DRM practices, selected from a menu for Belize and presented in this first report, to support and nurture the development of farming systems in pursuit of enhanced climate resilience and sustainable livelihoods.  Using Amish farming systems as a successful local model exhibiting very low vulnerability to hydromet hazards, four core characteristics were identified as crucial to the success of small farming systems in situations of high risk. These are common vision, teamwork, integrated mixed farming, and prudent natural resource management. The first two defines the character if the community, and the latter two relates to the technical nature of sustainable agriculture.

The groups selected for this intervention were Santa Martha, Concepcion, Calla Creek, and El Progresso, all villages in rural Belize.  A qualitative evaluation shows them all to be weak in the core characteristics essential for successful farming in pursuit of enhanced climate resilience and sustainable livelihoods.

Based on a situational analysis, DRM practices were selected to support the development of coping and resilience capacities, through a variety of pathways, including enhanced income generation and food security, developing the culture of planning and working together, shifting production away from high risk periods, and paying particular attention to soil and soil water management, all in an effort to reduce vulnerability.

Budgets were presented for the various interventions and a proposed disbursement schedule presented in Table.21.  Investments in livestock and crop development by FAO were US$ 22,035.97, and US$ 49,742.85 respectively with a sum total investment of $71,778.81US. Counterpart contributions were US$ 56,809.36US or 79.1% of FAO’s investments. These would be supported by an intensive program of capacity building, and, in partnership with other organizations, some degree of institutional support development at UB to ensure continuity.

The Approach

The introduction of and testing of good DRM practices to reduce losses due to disasters at the farming level is the common approach taken in introductory DRM studies in the Caribbean (FAO, 2007, 2009(a); SPENCE, 2008; ROBERTS & SHEARS, 2008) and forms the basis of this study.  However, the current approach goes a step further and uses DRM practices to support and nurture the development of farming systems in pursuit of sustainable livelihoods.

Characteristics of successful, sustainable, small farming systems in Belize

The characteristics of successful, sustainable small farming systems in Belize were discussed previously (section), and four were selected in defining a standard. The selected characteristics were:

Common vision.

Team work/collective approach.

Integrated mixed farming.

Natural resource management, with emphasis on soil management.

Common vision

Successful small farming communities must share a common vision which among other things must include farming as a business generating income and capable of supporting healthy, honest, and sustainable livelihoods. The stigma of associating agriculture as an inferior income generating activity, and excessive manual labour must be dispelled.

Team work/collective approach

Promoting a culture of planning and working together is as essential to risk management and recovery efforts as it is to successful farming systems. Meeting to plan the crop cycle, planting schedules, procurement of inputs, marketing, etc., are all essential prerequisites in developing the collective approach in small farming communities. The practice once implemented and even institutionalized, becomes an important tool in planning and mobilization for disasters, and coordinating recovery efforts in the aftermath of disasters.

Integrated mixed farming

While essential to natural resource management, mixed farming is the prime ingredient in risk mitigation and sustainability, especially in rainfed, small farming systems where weather adversely affects some species more than others.

Natural resource management

The productive capacity and sustainable use of the natural resource base, namely soil, water, and forests, depends on prudent balance of output and input, checking degradation and pollution and the promotion of practices to restore and enhance desirable properties.

Situational analysis

This section deals with the physical environment in relation to rainfall, water deficits, flood frequency, and soil and water properties at the selected demonstration sites.  For a variety of reasons, the desired data are not all available for this report as the laboratory in Florida seems to have misplaced two soil samples. The sites will be resampled and the analysis included in an update to this report. Eventually, the information will be merged with socioeconomic data to present a comprehensive analysis of the situation at each of the selected sites.

Santa Martha Village

Rainfall and mean daily temperatures for Tower Hill station in Orange Walk, the closest hydromet gauging station to Santa Martha village, and considered representative of conditions in that village have been used to compute water deficits using an empirical relationship developed by Holdridge (ARSCOTT et al., 1965). The method though having limitations is considered adequate for a general characterization of the water regime especially in situations where hydromet network density is low and only a few meteorological parameters are available.

The data are presented in Table 1. The high rainfall months are June to October when risks a rising from floods, and coincidentally hurricanes, are high. The water deficit months are November through to May when supplemental watering is required for crop production, and the farmer, using irrigation, is better able to control the soil-water regime. The same period covers conditions of both short days and low temperatures (November-January), and long days and high temperatures (March-May), which permit the cultivation of a wide range of crop varieties.

Selected information on soils sampled from the three sites in Santa Martha is presented in Table 2. The data for Santa Martha show high soil pH values at and beyond which availability of most plant nutrients, both macro and micro, decline (Follet et al, 1981).  The C.E.C. values are low indicating that the soil has a low buffering capacity and therefore fertilizer must be applied regularly and in small quantities. The predominance of calcium in the soil environment and naturally on the exchange complex (>82% saturation) suggest likely problems with potassium and magnesium uptake and availability.

The organic matter content is low, a given for most tropical soils, and management should prevent further decline through organic matter additions. This would also increase the soil buffering capacity, enhancing both storage and availability of plant nutrients. Management must supply the crops’ requirements for most nutrients through a programme which supplies small quantities regularly, as the soil, without organic matter additions, is a poor source of crop nutrients. Weekly fertigation is one such programme.

Table 1: Average monthly rainfall, potential evapotranspiration, and water deficits for Tower Hill (Lat. 18(12” N; Long. 88(24”W, elev. 13M AMSL) considered representative of conditions at Santa Martha Village.

| Parameters | Jan. | Feb. | Mar. | Apr. | May | Jun. | Jul. | Aug. | Sept. | Oct. | Nov. | Dec. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Average Monthly Rainfall (mm) | 76.8 | 33.7 | 28.8 | 45.9 | 99.1 | 202.5 | 191.7 | 205.6 | 171.0 | 188.7 | 101.6 | 77.4 |
| Average*pot. Evapotranspiration (mm) | 117.5 | 112.0 | 129.0 | 134.9 | 139.2 | 141.1 | 143.4 | 143.9 | 139.2 | 138.4 | 126.7 | 123.5 |
| Deficits (mm) | 40.7 | 78.3 | 100.2 | 89.0 | 40.1 | (61.4) | (48.3) | (61.7) | (31.8) | (50.3) | 25.1 | 46.1 |

*Estimated from Holdridge empirical formula

ETp = 0.0035T – 0.112

ETp = pot.  Evapotranspiration in ins/day

T = mean daily temperature (F

Table 2: Analysis of soil samples taken from Santa Martha and Concepcion in the North of Belize

| Location | Organic Matter % | pH | C.E.C meq/100g | Potassium | Magnesium | Calcium |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | ppm. (%BS) | ppm. (%BS) | ppm. (%BS) |
| SM I | 3.4 | 6.5 | 2.5 | 23 (2.4) | 23 (7.6) | 411 (82.0) |
| SM II | 5.8 | 6.6 | 6.2 | 71 (2.9) | 46 (6.1) | 1056 (84.5) |
| SM III | 4.6 | 6.9 | 3.7 | 70 (4.9) | 29 (6.6) | 652 (88.6) |

Table 3: Analysis of irrigation water for three sites in Santa Martha, and one in Concepcion villages, Northern Belize.

| Parameters | Location | comments |
| --- | --- | --- |
|  | SM I | SM II | SM III | CI |  |
| pH | 7.4 | 7.2 | 7.5 | 7.3 |  |
| Cond. Mmhos/cm | 0.76 (H) | 2.91 (VH) | 1.39 (H) | 0.85 (H) |  |
| TDS (ppm) | 486.4 (H) | 1862.4 (VH) | 889.6 (H) | 544.0 (H) | Impacts osmotic potential, and as a consequence uptake of both water and nutrients. |
| Hardness | 275.5 (A) | 652.5 (EH) | 314.1 (MH) | 362.0 (MH) |  |
| Na+ (ppm) | 34 (M) | 753 (VH) | 156 (H) | 10 (M) | Has a dispersing effect on soil, degrading structure, and reducing infiltration, water holding capacities and redistribution. |
| K+ (ppm) | 4 (M) | 8 (M) | 2 (M) | 4 (M) |  |
| Ca2+ (ppm) | 85 (H) | 177 (VH) | 87 (H) | 128 (VH) |  |
| Mg2+ (ppm) | 15 (M) | 50 (H) | 23 (M) | 10 (M) |  |
| HCO3- (ppm) | 207 (VH) | 120 (M) | 181 (VH) | 129 (H) |  |
| Cl- | 101 (H) | 640 (VH) | 187 (H) | 112 (H) |  |

The analysis of irrigation water samples taken from the three sites in Santa Martha village are presented in Table 3. In general the water quality is poor with site II in particular exhibiting the poorest quality.

The TDS values are high giving rise to high osmotic potentials which reduces the uptake of both water and nutrients.  High osmotic potentials in the soil water reduce water gradients at the soil/plant root interface and a consequential reduction the mass flow of water and nutrients is reduced.  Additionally, the high sodium contents tend to degrade soil structure through colloidal dispersion, reducing infiltration, water holding capacity, and water redistribution within the soil.  It is therefore important to manage the buildup of these harmful salts.

Management practices on these lands should include:

- Organic matter additions to protect the integrity of soil structure, maintain good internal drainage to facilitate leaching during the rain months of June to October.

- The use of high beds to facilitate leaching.

- Deep surface drains to control the water table depth, reduce ponding, and waterlogging.

- The use of salt tolerant varieties when available.

- The application of water directly to the soil with minimum wetting of the foliage, and in quantities sufficient to leach the root room.

Concepcion village

Mean monthly rainfall and mean daily temperatures collected from Libertad and considered representative of conditions at Concepcion were used to compute water deficit data presented in Table 4.

Table 4: Average monthly rainfall, potential evapotranspiration and water deficits for Libertad (Lat. 18(17” N; Long. 88(28” W, elev. 12M AMSL) considered representative of conditions at Concepcion village.

| Parameters | Jan. | Feb. | Mar. | Apr. | May | Jun. | Jul. | Aug. | Sept. | Oct. | Nov. | Dec. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Average monthly rainfall (mm) | 68.8 | 29.9 | 33.1 | 63.2 | 97.1 | 222.2 | 137.9 | 188.5 | 226.3 | 208.1 | 89.1 | 64.2 |
| Average monthly *pot.Evapotrans (mm) | 114.1 | 109.8 | 124.0 | 128.2 | 133.5 | 135.4 | 139.4 | 138.9 | 142.6 | 131.5 | 117.1 | 117.6 |
| Deficits (mm) | 45.3 | 79.9 | 90.9 | 65.0 | 36.4 | (86.8) | 1.0 | (49.6) | (83.7) | (76.6) | 28.0 | 53.4 |

*Estimated from Holdridge empirical formula

ETp = 0.0035T – 0.112

ETp = pot. Evapotranspiration in ins/day

T = mean daily temperature (F

The data show trends similar to those for Santa Martha permitting the cultivation, with irrigation, of a wide range of crops. The vulnerable months, when both floods and hurricanes pose potential threats, are June to October.

Soil data for the Concepcion site are presented in Table 2 and again the trends are similar to those identified for Santa Martha, and a similar management approach is recommended. Data for irrigation water taken from the site are presented in Table 3.  Though the total dissolved solids are high, sodium is not as predominant as the Santa Martha sources and therefore for irrigation purposes the water is of better quality.

El Progresso Village (Cayo)

Mean monthly rainfall and mean daily temperatures collected from Barton Creek considered representative of conditions in El Progresso village were used to compute water deficits and the data are presented in Table 5.

Table 5: Average monthly rainfall, potential evapotranspiration and water deficits for Barton Creek (Lat. 17(06” N; Long. 88(57” W) considered representative of conditions at El Progresso village.

| Parameters | Jan. | Feb. | Mar. | Apr. | May | Jun. | Jul. | Aug. | Sept. | Oct. | Nov. | Dec. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Average monthly rainfall (mm) | 93.1 | 54.2 | 37.5 | 28.4 | 88.8 | 123.4 | 225.9 | 156.1 | 180.2 | 205.7 | 171.2 | 133.1 |
| Average*pot. Evaportranspiration (mm) | 112.6 | 110.2 | 128.0 | 132.5 | 139.7 | 140.2 | 139.4 | 140.4 | 136.8 | 135.9 | 122.9 | 119.1 |
| Deficits (mm) | 19.5 | 56.0 | 90.5 | 104.1 | 50.9 | 16.7 | (86.5) | (15.7) | (43.4) | (69.8) | (48.3) | (14.0) |

*Estimated from Holdridge empirical formula

ETp = 0.0035T – 0.112

ETp = pot. Evapotranspiration in ins/day

T = mean daily temperature (F

The data show a shift in the high rainfall months, July to November, when crop production is vulnerable to waterlogged and hurricanes. The area is classified as rolling lands and floods are not considered serious hazards. A serious danger however, is soil erosion and soil loss on sloping lands with shallow soils overlying limestone. Winter (Nov.-Jan.) crops have been successfully cultivated with careful planning and execution of land preparation practices. Organic matter additions on the lands have the additional benefit of structural improvement and stabilization, enhancing infiltration, reducing surface runoff and as consequence, erosion.

The deficit months are January to June with the latter being a transition month. While irrigation is desirable, a source of water for such is not easily accessible and any recommended systems must use water efficiently.

Soil data are not currently available for this site.

Calla Creek, (Cayo)

Mean monthly rainfall and daily temperatures for Chaa Creek, considered representative of conditions in Calla Creek were used to compute water deficits presented in Table 6.

Table 6: Average monthly rainfall, potential evapotranspiration and water deficits for Chaa Creek (Lat.17(06” N; Long. 88(04” W, 241M AMSL) considered representative of conditions at Calla Creek, Cayo.

| Parameters | Jan. | Feb. | Mar. | Apr. | May | Jun. | Jul. | Aug. | Sept. | Oct. | Nov. | Dec. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Average monthly rainfall (mm) | 48.7 | 57.7 | 26.9 | 16.3 | 140.4 | 120.8 | 112.1 | 117.4 | 140.7 | 236.4 | 156.8 | 113.9 |
| Average*pot. Evapotranspiration (mm) | 111.6 | 110.2 | 131.5 | 133.5 | 139.2 | 137.8 | 139.9 | 140.4 | 137.8 | 135.9 | 123.9 | 119.1 |
| Deficits (mm) | 62.9 | 52.5 | 104.6 | 117.2 | (1.18) | 17.0 | 27.8 | 23.0 | (2.9) | (100.5) | (32.9) | 5.2 |

*Estimated from Holdridge empirical formula

ETp = 0.0035T – 0.112

ETp = pot. Evapotranspiration in ins/day

T = mean daily temperature (F

The situation in Calla Creek with respect to rainfall and deficits differ significantly from the other selected areas.  October is the most vulnerable month when the likelihood of floods is high.  Calla Creek shares a watershed with Peten, Guatemala, and runoff is influenced not only by the characteristics of rainfall and the drainage basin within Belize but more important, rainfall and land management within the Guatemalan portion of the watershed.

Deficits are experienced from December to August with May showing small surplus water.  The majority of villagers inhabit the vulnerable alluvial flats along the Mopan River, and while conditions are ideal for irrigated crop production for most of the year, and a surface source of good quality water in the river is readily available throughout the dry season, the expected, commensurate agricultural output is lacking.

Soil data are not currently available for this site.

Farming systems

Four characteristics, namely common vision, teamwork, mixed farming, and natural resource management, were used to define the standard practices for successful small farming systems in Belize. The first two define the social character of the residents and the community, while the latter two addresses the technical capabilities.

Farmers from the four selected groups were qualitatively rated based on these criteria and the results summarized in Table 6. Vision was lacking in all the groups. Santa Martha exhibited the best teamwork approach, though there is room for development in relation to structure and responsibilities. All had some form of mixed farming as a coping strategy, but integration was lacking. Natural resource management was weak to non-existent and there was tendency towards the unsustainable and heavy use of fertilizers and chemicals in crop production; primarily as a response to advice from agrochemical businesses, but also because information of the dangers to the environment and its users, along with credible alternatives were lacking.

With respect to Hydro meteorological hazards, the groups at Concepcion, Calla Creek, and El Progresso are considered highly vulnerable, while Santa Martha is considered moderately vulnerable.

Table 6: Qualitative rating of the four demonstration groups in relation to the standard practices for successful small farming.

| Village | Common Vision | Team Work/Collective Approach | Mixed Farming | Natural Resources Management |
| --- | --- | --- | --- | --- |
| Santa Martha | Weak | Moderate | Moderate | Moderate |
| Concepcion | Weak | Weak | Weak | Weak |
| Calla Creek | Weak | Weak | Moderate | Weak |
| El Progresso | Weak | Weak | Moderate | Weak |

Selection and review of DRM practices for demonstrations

A first round of good DRM practices, taken from the options menu previously presented, were selected jointly with  each village group based on the principles of supporting the development of farming systems in pursuit of enhanced climate resilience and sustainable livelihoods. The selected DRM activities were consolidated into this work plan which was presented to and cleared by a national technical validation group, established under the project to evaluate the practices in their suitability for the pilot villages in Belize; thereafter it was also reviewed and cleared by the national project steering committee, and then shared with FAO for final review and technical clearance.

The format for presentation was taken from FAO (2009 (b)) with modifications which included sections on capacity building requirements and a description of the practice. A comprehensive program of capacity building is considered crucial to the success of this phase of the project.

A second round of good practice selection is planned for later in 2009, after the first round of demonstrations will have started and further demands maybe identified.

The selected good practice options are village/site specific and presented in detail in the following chapters for each village separately.

The approach presented involves synergies with other organizations, namely UB, OIRSA, and RUTA, to develop the institutional capacity at UB for the sustainable supply of dual purpose poultry breeds to rural small farmers, at subsidized costs, in an effort to enhance local fowl production. This would be supported by the development of a compulsory course in Disaster Risk Management at this institution with the assistance of IADB. Together, the package is considered a solid foundation for an effective, inexpensive, and sustainable way to show case in selected villages good DRM practice and use them for wider dissemination after successful demonstrations, while disseminating the message of better preparedness and mitigation in disaster management throughout rural Belize if not the whole country.

Implementation of Demonstrations

Approach

Weaknesses/Deficiencies in the farming systems were identified for each pilot group, and appropriate DRM practices, taken from the menu presented in section (  ), were introduced. The primary goal is to support the development of the selected farmers to effectively live with, and manage risks associated with likely hazards.

Since this report focuses on the technical interventions also the proposed capacity building intervention are technical in nature and directly linked to the proposed activities. It is important to stress here, that the technical training packages will be supplemented by process oriented aspects of capacity building including group formation and management, DRM planning, risk contingency planning etc. (not included in this report)

Santa Martha Group

The DRM practices jointly selected and to be introduced by the project are:

- Dairy cattle production.

- Irrigation development at each site.

- Local fowl production enhancement.

Dairy cattle management is compatible with small mixed farming systems, and provides: additional income during the dry season, source of organic matter for soil management, enhanced returns from sugarcane crop, and last but not least, additional source of protein as fresh milk, cream, and cheese, for the community.

Supplemental watering or irrigation is essential to extending the cropping pattern into the months of November to May when crop water deficits are experienced in this area (Table 1). This period of water deficits is characterized by low to moderate rainfall and reduced risks of crop losses arising from floods and hurricanes. The traditional rainy season of June to December still requires supplemental watering on account of the distribution pattern of rainfall with significant periods of deficit within months showing on average water surpluses. Combined with enhanced drainage systems, the small farmer is provided with soil water management tools effective in reducing risks associated with soil water extremes.

Local fowl production enhancement is not only a good DRM practice, but also an inexpensive way to propagate the DRM message throughout the community.

The package of DRM practices selected supports the development of a sustainable farming system which enhances the coping and resilience capacities of the group and hence reduces their vulnerability to climate risks.

Dairy cattle production

Context and Justification

Dairy products account for some 20% of Belize’s total agricultural food imports, equivalent to an average of 23.5M$ annually over the past 11 years (MAF, 2009).  Promoting dairy production is consistent with the policy of GOB for small farmer development while attempting to reduce the food import bill.

The members of the group at Santa Martha are all small Milpa cane farmers, receiving low returns on their cane on account of low yields and the system of licensing of sugarcane producers which prevents them from selling directly to the factory. Yet sugarcane, one of the more efficient grasses, is an ideal forage for ruminant production systems. A small dairy production unit would not only give better returns on the cane crop, but would enhance incomes throughout the year, provide organic matter for soil management, and make additional sources of protein available in the community, while contributing to a reduction in the national food import bill. Since cattle are mobile and can be easily moved to safer places (higher grounds) when hurricane and/or flood warnings are issued (A hurricane warning is in place and reaches each village; a flood warning system is just being establishment where needed by NEMO).

Objectives

Objectives of the demonstration are to promote small farmer dairy production in the Santa Martha area, which would better utilize the sugarcane crop, enhance incomes throughout the year, create additional income generation during periods when crop production is severely constrained, provide an important source of soil additive/ ameliorant, namely, organic matter and as a result of the above, reduce the overall farming system’s vulnerability to natural hazard impacts.

Description

The group would be supplied with 6 Dairy heifers, approximately 12 to 20 months of age, after constructing a feeding shed and holding area. The animals would be confined to this area for feeding, herein called the “Plot”. The diet would be sugarcane based diet following the recommendation from studies conducted at the sugarcane feed centre, Trinidad. (SFC, 1983) This would be supplemented with controlled grazing on the roadside, and on small pastures plots to be developed by each member.

A dairy bull would be borrowed/rented from GOB when the heifers are of breeding weight/age for a sufficient period to have all animals served. At parturition, the calves would be allowed an intake of colostrum for two days before placing on an artificial milk replacer diet to be followed by a dry diet, or half the cow’s production of milk followed by a dry diet, or a combination of the two. The other half would be used for processing.  In addition:

- The demonstration plot must be accessible to visitors by vehicle, and must be in close proximity to a water source.

- The farmers must each have at least one acre of Milpa sugarcane, within close proximity to the plot, or with means of transporting cane to the plot.

- Additional land to develop three small pastures, each of one acre is desirable.

- Experience with cattle handling is desirable.

- Farmers must agree to bear any costs outside the budget line.

Implementation Schedule

The implementation schedule is presented in Fig.1. It is envisaged that implementation would start in September and the entire process would be completed by December. A supply of organic matter would be available from November.

Technical details/Production technology

Animals: Dairy breeds used in Belize are the Brown Swiss, Jersey and Holstein Freisen.  Obtainng heifers may be a difficult task, but arrangements could be made with one of the Amish communities for a supply of six animals of 12to 20 months in age.

Nutrition:  The aim is to used cultivated forages and mineral supplements, as opposed to processed feeds. The bulk of the nutrition would be based on chopped Sugarcane (S. officinarum), mixed with high protein forages such as Mulberry(M. alba), Nacadero(T. gigantea), and Mombassa (P. maximum cv.Mombassa), and supplemented with a general purpose range mineral, trace mineral blocks, urea and molasses.

Animal health: It is important to ascertain that the animals were given blackleg vaccinations at weaning, but never the less they should receive a booster shot annually. Deworming should be done every 90days using Ivermectin, in rotation with an Albendazol, until maturity, thereafter every six months.  Exotic breed are very susceptible to ticks infestations and as such the animals should be carefully monitored. Any infestation must be treated by spraying with Bayticol in rotation with Bovitraz on a 3week cycle until the parasites disappear. Other ectoparasites,such as beef worms, should be treated by physical removal of the larvae, and cleaning the wound with an antiseptic and fly repellant. Cuts and bruises should be similarly treated.

General instructions

Asign board has to be posted at the demonstration site. A sample of which is presented in section. All demonstration records must be kept in an assigned ledger at intervals as recommended in the monitoring plan. Exteme care should be taken that animals are not allowed to roam, as damage to other farmers crops could result with serious liabilities for the pilot group.

Capacity building requirements

Short courses dealing with:

- Cattle management with emphasis on dairy cattle.

- Cheese and cream production and non-refrigerated storage.

- Virtues of team work and systematic planning.

- Group leadership, group management and business planning for 2 years

- Risk and emergency contingency planning

Figure 1:  Implementation Schedule.

| Activities to be undertaken | Who is responsible? | Expected Output or Outcome | Monthly Chronogram |
| --- | --- | --- | --- |
|  |  |  | J | F | M | A | M | J | J | A | S | O | N | D | Etc. |
| Cutting posts and collection of waste lumber from sawmill. | Farmers | Lumber procured. |  |  |  |  |  |  |  | X |  |  |  |  |  |
| Procurement of roofing material, barbed wire, staples, nails. | FAO/MAF | Constr. Materials procured |  |  |  |  |  |  |  | X |  |  |  |  |  |
| Transporting materials to Plot. | FAO/MAF | Construction materials delivered to plot. |  |  |  |  |  |  |  | X |  |  |  |  |  |
| Construction of feeding shed and holding area. | Farmers/ FAO/MAF | Shed and feeding area completed. |  |  |  |  |  |  |  |  | X |  |  |  |  |
| Purchase of heifers and cane chopper,M&S. | FAO/MAF | Animals, chopper and M&S procured. |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Transporting animals, cane chopper, M&S to plot. | Contractor FAO/MAF | Animals, chopper, and M&S delivered to plot. |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Train animals and start feeding program. | Farmers | Adjustment to new environment. |  |  |  |  |  |  |  |  |  |  | X | X |  |
| Collection and storage of manure and unutilized cane for composting. | Farmers | Stockpile of manure and cane trash. |  |  |  |  |  |  |  |  |  |  | X | X | X |

Budget

Table7: Dairy cattle production, Santa Martha group.

| Category | Item of Expenditure | Amount of Input | Unit Cost ($Bze) | Contributions ($Bze) |
| --- | --- | --- | --- | --- |
|  |  |  |  | FAO | Farmer Group |
| Construction of Shed & Feeding area. 20’ x 16’ | Bush Lumber (posts, beams, rafters) | Various | - | - | $1,500.00 |
|  | Sawn Lumber | Various size 400Bft. | $1.82/Bft | $728.00 | - |
|  | Zinc for Shed (galvanized) | 7 Sheets (16’ x 40’) 26 gauge | $110.35/sheet | $772.45 | - |
|  | Barbed wire | 6 | $125.00/roll | $750.00 | - |
|  | 1” staples | 10 lbs | $2.95/lb | $29.50 | - |
|  | Nails (3 ½ ” & 4”) | 10 lbs | $3.65/lb | $36.50 | - |
|  | Transporting lumber | 3 trips | $300/trip | $900.00 | - |
|  | Construction Supervision | 2 days | $75/day | $150.00 | - |
|  | Construction Labor | 16 man days | $30/man-day | - | $480.00 |
| Pasture planting. | Labour | 10man days/ ½ acre. X 6persons | $30.00/man-day |  | $1,800.00 |
| Animal care | Labour | (3hrs/day)X180days | $30.00/man-day |  | $1,800.00 |
| Animals | Heifers | 6 x 700 lb/each | $2.00/lb | $8,400.00 | - |
| Equipment | Cane Chopper | 1 | $650/each | $650.00 | - |
|  | Small Motor | 1 | $1200/each | - | $1,200.00 |
| M&S | Salt Blocks | 3 | $23.00/each | $69.00 | - |
|  | Range Minerals | 2 sks | $69.00/sk. | $138.00 | - |
|  | Molasses | 2 x 55gal. drums | $28.50/drum | $57.00 | - |
|  | Urea | 30 lbs | $6.50/10lb | $ 19.50 | - |
|  | Dewormers | 250 mls | $80.00 | $80.00 | - |
|  | Syringes & Needles | 10 x 10 ml | $20.00 | $20.00 | - |
|  | Fly Spray (matacresa) | 1 can | $18.50/can | $18.50 | - |
|  | Rope | 6 lbs | $6.00/lb | $36.00 | - |
|  | (55 gal) plastic drums | 3 | $25.00/each | $75.00 | - |
| Visibility FAO/GOB | Metal sign | 1(4’x2.5’) | $282.00 | $282.00 |  |
|  | Contingencies | 5%TC |  | $660.57 |  |
| Total |  |  |  | $13,872.02 | $6,780.00 |

Irrigation development Santa Martha village

Context and Justification

Belize imports some 8-13M$ of fruits and vegetables annually which accounts for a 11yr-average of about 10% of the total food import bill (MAF, 2009). This is unacceptable for a country which has a deficit budget and GOB’s policy aims to stimulate local production of fruits and vegetables with the hope of reducing the import bill.

Shifting production to periods of water deficit, through the introduction of irrigation, not only reduces the risks associated with crop production, common in rainfed systems, but enhances the income generating capacity of small farmers and their families. The short growing period of most vegetable crops make them ideal for small farming systems and allows the complete production shift to the less vulnerable months of the year, enhanced livelihoods, and greater resilience to disasters.

Objectives

To promote the production of vegetables during the period of low risk from hydro meteorological hazards, November to May for Santa Martha, through the introduction of irrigation technology.

Description

Three sites have been identified for vegetable production by the Santa Martha group.  Moving from one to the other is necessitated by changes in the quality of irrigation water as the dry season intensifies. The project proposes to supply the group with training, a complete irrigation system for use at one site with T-tape requirements for all sites, seed, pesticides, and fertilizers for 1.5 acres of vegetables and other crops at two sites. The farmer group is expected to participate in training exercises, and would be responsible for the second irrigation system, the crop inputs at the third site and labour requirements of the entire project.

The group, in consultation with the implementation committee, may adjust the planting calendar to suit weather and market conditions provided the respective budget lines are not exceeded.

The program of vegetable production proposes 1.5 acres at each of the sites as follows:

- Nov/Dec.  Site I.  Onions, carrots, potatoes, and tomatoes each at ¼ acre, sweet peppers at ½ acre.

- Jan/Feb.  SiteII.  Tomatoes and cabbage at ¼ acre each, sweet peppers and irrigated corn at ½ acre each.

- Mar. /Apr. SiteIII.  Sweet peppers, tomatoes and irrigated corn each at ½ acre.

In addition:

- The demonstration plot must be accessible to visitors by vehicle, and must be in close proximity to a water source.

- The farmers must each have a valid pesticide applicator’s licence.

- Farmers must be willing to attend and participate in training sessions, and be willing to conduct tours of their demonstration plots for other farmers.

- Experience with vegetable production and marketing is desirable.

- Farmers must agree to bear any costs outside the budget line.

Implementation time

Training is expected to start in the first week of July, with field plot implementation scheduled for mid-August. Seedbed preparation is one month before the scheduled planting dates.

Figure 2:  Implementation Schedule

| Activities to be undertaken | Who is responsible? | Expected Output or Outcome | Monthly Chronogram(2009) |
| --- | --- | --- | --- |
|  |  |  | J | F | M | A | M | J | J | A | S | O | N | D | Etc. |
| Budgets approved and training Starts. | FAO/MAF | Implementation commenced. |  |  |  |  |  |  | X | X |  |  |  |  |  |
| Seedbed for site 1 prepared and planted. | Farmers | Nursery stage, site 1 completed. |  |  |  |  |  |  |  | X |  |  |  |  |  |
| Site 1Prepared and irrigation installed and planted. | Farmers | Site1 planted with irrigation installed. |  |  |  |  |  |  |  |  | X | X |  |  |  |
| Seedbed for site II prepared and planted. | Farmers | Nursery stage siteII completed |  |  |  |  |  |  |  |  |  |  |  | X |  |
|  |  |  | Monthly Chronogram(2010) |
|  |  |  | J | F | M | A | M | J | J | A | S | O | N | D |  |
| SiteII prepared, irrigation installed, and planted. | Farmers | Site II planted with irrigation installed | X | X |  |  |  |  |  |  |  |  |  |  |  |
| Seedbed for site III prepared and planted. | Farmers | Nursery stage, site III completed. |  |  | X |  |  |  |  |  |  |  |  |  |  |
| SiteIII prepared, irrigation installed, and planted. | Farmers | Site III planted with irrigation installed |  |  |  | X | X |  |  |  |  |  |  |  |  |

Implementation site

Three sites in Santa Martha village identified simply as sites I, II, and III.

Capacity building requirements

Short courses dealing with:

- Soil management for sustainable vegetable production.

- Pesticides use and its impact on the environment, the user, and the consumers of produce.

- Virtues of team work and systematic planning.

General instructions

Asign board has to be posted at the demonstration site. A sample of which is presented in section. All demonstration records must be kept in an assigned ledger at intervals as recommended in the monitoring plan. Exteme care should be taken that the protocols of pesticide use are adhered to.

Technical details and production technology

Presented in programs of production activities in the appenix

On account of the poor quality of irrigation water, planting beds should be raised to facilitate internal drainage and leaching, to delay if not prevent a buildup of harmful salts in the rooting zone.  Deep drains are recommended to facilitate orderly runoff, and control the watertable depth.

Budget

Table 8: Irrigation development and vegetable production, Santa Martha Group, Site1.

| Category | Item of Expenditure | Amount of inputs | Unit Costs ($Bze) | Contributions($Bze) |
| --- | --- | --- | --- | --- |
|  |  |  |  | FAO | Farmer Group |
| Site I. | Irrigation Equipment (Pump, mains, sub-mains, valves, connectors) | Various (table.A1) | Various (table.A1) | $1,260.00 | $4,495.00 |
|  | T-tape | 1 ½ rolls | $780/roll | $1,170.00 | - |
|  | Tools and equipment. | Various (Table. A14) | Various (Table. A14) | $2,461.25 |  |
|  | ¼ acre Tomatoes (seed, pesticides, fertilizer) | Various (Table.A4) | Various (Table. A4) | $553.84 | -$250.00 |
|  | ½ acre Sweet Peppers (seed, pesticides, fertilizer) | Various (Table.A3) | Various (Table.A3) | $1616.63 | -$500.00 |
|  | ¼ acre each of carrots, onions, and potatoes(seed,fertilizers,pesticides) | Various (Tables. A5, A6, A7.) | Various (Tables. A5, A6, A7.) | $1,600.43 | -$937.14 |
|  | Metal sign | 1 | $282.00 | $282.00 |  |
|  | Contingency | 5%TC |  | $384.21 |  |
|  | Sub-totals(Site1) |  |  | $9,328.46 | $6,182.14 |

Table 9:  Irrigation development and vegetable production. Santa Martha Group, Site II

| Category | Item of Expenditure | Amount of inputs | Unit Costs ($Bze) | Contributions($Bze) |
| --- | --- | --- | --- | --- |
|  |  |  |  | FAO | Farmer Group |
| Site II. | Irrigation Equipment (mains, sub-mains, valves, connectors) | Various (Table.A1) | Various (Table.A1) | $3,235.00 | - |
|  | T-tape | 1 ½ rolls | $780/roll | $1,170.00 | - |
|  | ½ acre Tomatoes (seed, pesticides, fertilizer) | Various (Table.A4) | Various (Table.A4) | $553.84 | $250.00 |
|  | ½ acre Sweet peppers (seed, pesticides, fertilizer) | Various (Table.A3) | Various (Table.A3) | $1,616.63 | $500.00 |
|  | ¼ acre Cabbage (seed, pesticides, fertilizer) | Various (Table.A2) | Various (Table.A2) | $291.62 | $250.00 |
|  | ½ acre Irrigated corn | Various (Table.A11) | Various (Table.A11) | $296.64 | $388.50 |
|  | Contingency | 5%TC |  | $421.19 |  |
|  | Sub-totals(Site II) |  |  | $7,584.92 | $1,388.50 |

Table 10: Irrigation development and vegetable production, Santa Martha Group, Site III.

| Category | Item of Expenditure | Amount of inputs | Unit Costs ($Bze) | Contributions($Bze) |
| --- | --- | --- | --- | --- |
|  |  |  |  | FAO | Farmer Group |
| Site III. | Irrigation Equipment (Pump, valves, mains, sub-main, connectors) | Various (Table) | Various (Table) | - | - |
|  | T-tape | 3 rolls | $780/roll | $2,340.00 | - |
|  | ½ acre Tomatoes (seed, pesticides, fertilizer) | Various (Table.A4) | Various (Table.A4) | - | $1,607.68 |
|  | ½ acre Sweet Pepper (seed, pesticides, fertilizer) | Various (Table.A3) | Various (Table.A3) | - | $2,116.63 |
|  | ½ acre irrigated corn (seeds, pesticides, fertilizers) | Various (Table.A11) | Various (Table.A11) | - | $685.14 |
|  | Contingency | 5%TC |  | $117.00 |  |
|  | Sub-total(Site111) |  |  | $2,457.00 | $4,409.45 |
|  | Grand Total (Crops). ($US) |  |  | $19,370.38 ($9,685.19) | $11,980 09 ($5,990.04) |
|  | Grand Total(All practices) ($US) |  |  | $33,242.40 ($16,621.20) | $18,760.09 ($9,380.04) |

Calla Creek residents

The DRM practices to be introduced are:

- Pasture improvement.

- Homestead gardening.

- Fruit tree and horticultural nursery.

- Local fowl production enhancement.

The practices were selected to enhance climate resilience and food security in the community, improving the income generation capacity of residents, and promote integrated farming within the community. The practices themselves encourage interaction and foster a culture of communicating, working, and planning together.  The overall impact is expected to be enhanced coping and resilience capacities, and as a consequence reduced vulnerability to the principal hazards, flood, and drought.

Pasture improvement

Context and Justification

The last ten years has seen significant improvements in the local cattle industry resulting from a demand driven, unofficial market in neighboring Guatemala and Mexico.  Improved forages, genetic stock, and management have all contributed to growth and development in this sub-sector. The formalization of the Mexican market in May of this year will see significant movement of live animals to that country, leaving shortages at home. The small farmer who individually is not poised to supply the export market has a vital role in supplying the expected shortfall locally. Developing this small producer is important to the sustainability of cattle exports.

A supply of good quality forages is the foundation of cattle development. Most farmers at Calla Creek depend on local forages, which were demonstrated to be highly susceptible to waterlogging during the flood in October of 2008 when the area was inundated for 17days killing most forages. Forage improvement is essential to ruminant development in the area. The forages which have shown tremendous resilience during the said flood, Mombassa, and African star will be promoted.

Objectives

Objectives of the demonstration are to establish improved grass nurseries, 2 acres of Mombassa and ¼ acre of African star, on high ground on each of 4 ruminant producers.  The former will be allowed to grow to full maturity, cut and fed to the animals daily, while the latter would be used as a source of planting material for improved pasture expansion over a period of two years.  A task of sugarcane would be planted to augment the zero grazing system during the period of pasture improvement. In return the recipients would collect manure for sale to the homestead gardeners and tree crop developers.

Description

Each member of the group would be supplied with material for fencing, 2¼ acres for the nursery, herbicides, seeds, and fertilizer for establishing 2 acres of Mombassa and 2 tasks of African Star grass. The recipient would be responsible for manual labour, which includes land clearing, constructing the fence, herbiciding, applying fertilizer, cutting star grass and establishing one task of cane, and two protein banks, to assist with forages for zero grazing during the establishment of pastures.

- The demonstration plot must be accessible to visitors by vehicle, and must be in close proximity to a water source.

- The farmers must each have a system of ruminant production which would benefit from pasture improvement, and be willing to undertake a comprehensive pasture improvement program.

- An elevated area of 3 acres must be available to develop the nursery and feeding plots.

- Farmers would have to supply vitamins, vaccines, and dewormers as required.

- Experience with cattle handling, and access to a small engine is desirable.

- Farmers would be encouraged to invest in small irrigation systems

- Farmers must agree to bear any costs outside the budget line.

Implementation Schedule

The implementation schedule is presented in Fig.3. It is envisaged that implementation would start in July and be completed with the second fertilizer application in October, leaving three monthe of growth before the traditional dry season starts. Cut and feed would start in January,2010, and this would be supplemented with citrus pulp feeding.  This process would be conducted with two farmers, and a repeat, with improvements where identified, would begin with the two other farmers in April of 2010.

Technical details/Production technology

Animals: Should be selected and culled to adjust the stocking rates to match the available pasture and feed, especially during the replanting period. Failure to do this could result in forced access to and destruction of the nurseries.

Nutrition:  The aim is to improve pastures, but also to adjust stocking rates based on available forage. During replanting, nutrition would use chopped Mombassa, augmented with sugarcane (S. officinarum), and high protein forages such as Mulberry (M. alba), Nacadero (T. gigantea).  Citrus pulp, molasses and urea would also be used in the dry season, and supplemented with a general purpose range mineral, trace mineral blocks year round.

Animal health:  All animals would be vaccinated, dewormed castrated and culled at the beginning of the program. A program of health care would be developed for the duration of the demonstrations.

General instructions

- Asign board has to be posted at the demonstration site. A sample of which is presented in section.

- All demonstration records, including photographs, must be kept in an assigned ledger at intervals as recommended in the monitoring plan.

- Exteme care should be taken to adjust the stocking rates during pasture replanting.  Failure to do so could be detrimental to the nurseries.

Capacity building requirements

Short courses dealing with:

- Cattle and pasture management with emphasis on beef cattle.

- Team building and working and planning collectively.

- Animal nutrition and dry season feeding systems.

Figure 3: Implementation Schedule.

| Activities to be undertaken | Who is responsible? | Expected Output or Outcome | Monthly Chronogram(2009) |
| --- | --- | --- | --- |
|  |  |  | J | F | M | A | M | J | J | A | S | O | N | D | Etc. |
| Budgets approved and finalized. Training begins. | FAO/MAF | Implementation begins. |  |  |  |  |  |  | X | X | X |  |  |  |  |
| Animals vaccinated, dewormed castrated and culled to adjust the stocking rate. | Farmer FAO/MAF | Stocking rate matches available pasture. |  |  |  |  |  |  | X |  |  |  |  |  |  |
| Procurement of Posts, barbed wire, staples, nails. | FAO/MAF | Fence. Materials procured |  |  |  |  |  |  | X |  |  |  |  |  |  |
| Transporting materials to Plot. | FAO/MAF | Fence materials delivered to plot. |  |  |  |  |  |  | X |  |  |  |  |  |  |
| Fence erected and herbicides applied. | Farmers/ FAO/MAF | Site preparation completed. |  |  |  |  |  |  | X |  |  |  |  |  |  |
| Nursery plots/cane planted and fertilized. | FAO/MAF Farmers | Planting completed. |  |  |  |  |  |  |  | X |  |  |  |  |  |
| Urea applied and pulp ordered. | Farmer FAO/MAF | Fertilization completed. Pulp ordered. |  |  |  |  |  |  |  |  |  | X |  |  |  |
|  | Monthly Chronogram(2010) |
|  | J | F | M | A | M | J | J | A | S | O | N | D |  |
| Cut and feed starts, augmented by pulp, molasses and urea | Farmers | Adjustment to new environment. | X | X | X | X | X |  |  |  |  |  |  |  |  |
| Collection and storage of manure and unutilized cane for composting. | Farmers | Stockpile of manure and cane trash. | X | X | X | X | X | X | X | X | X | X | X | X | X |

Budget

The budget is presented in Table 11. The data show that FAO would invest $3,236.05 per farmer in establishing a nursery and a source of supplemental feed for use in the dry season and during pasture planting. Citrus pulp as an additional supplement is also budgeted. The farmer would contribute $2,895.00 or 89.5% of FAO’s investments.  There are 4 farmers in the group, and two would start this year, and the others in June of next year.

Table 11: Materials for pasture improvement demonstration, Calla Creek, Cayo district, Belize.

| Item of Expenditure | Amount of Input | Unit Cost | Contributions |
| --- | --- | --- | --- |
|  |  |  | FAO | Farmer Group |
| Roundup/Wipeout | 1 ½ liters | $17.95/liter | $35.90 | - |
| Weedmaster (2-4-D) | 1 ½ liters | $22.60/liter | $45.20 | - |
| Knapsack spray can. | 1 | $102.00 | $102.00 |  |
| Sugarcane chopper | 1 | $650.00 | $650.00 |  |
| Small engine | 1 | $1,200.00 |  | $1,200.00 |
| Posts | 146 | $4.00/post | $584.00 | - |
| Barb Wire | 6 | $125.00/roll (300m) | $750.00 | - |
| Staples | 5 lbs | $2.95/lb | $14.75 | - |
| 46:0:0 | 2 sks | $56.25/sk | $112.50 | - |
| 14:36:12 | 2 sks | $60.55/sk | $121.10 | - |
| Seed (Mombassa) | 10 lbs | $16.00/lb | $160.00 | - |
| Molasses | 1drum | $55.00 | $55.00 |  |
| Plastic drum | 1 | $25.00 | $25.00 |  |
| Urea | 10lbs. | $6.50 | $6.50 |  |
| Citrus Pulp | ½ load | $220.00 | $220.00 |  |
| Labor (fence, posts, fertilizing,herbiciding) | 16 man days | $30.00/man day | - | $480.00 |
| Labor (African star) | 3 man days | $30.00/man day | - | $90.00 |
| Labour (feeding) | 2.25hrs/dayX150days (37.5man-days) | $30.00/man-day |  | $1,125.00 |
| Sign board | 1(3’x2.5’) | $200.00 | $200.00 |  |
| Contingency | 5%TC |  | $154.10 |  |
| Total (per farmer) |  |  | $3,236.05 | $2,895.00 |
| Total (4 farmers) |  |  | $12,944.20 | $11,580.00 |

Homestead gardening

Context and Justification

There have been significant decreases in agriculture and agricultural activity as viable and sustainable livelihoods, in rural Belize despite national programs of sorts to promote rural farming. The trend has been a movement towards subsistence farming, supported by incomes generated through work in other sectors, quite often outsides of the community. The net result has been the intensification of the state of food insecurity and increasing dependence on the network of food suppliers, which promotes the consumption of imported commodities.  Incomes generally fall short of needs and as a consequence we witness the intensification of poverty, malnutrition, and a certain degree of social degradation. In the event of disasters, communities lacking a sound food production and storage system are more vulnerable to risks, than  those sharing a vision and developing effective food security strategies, in support of “producing what you eat,” as practiced among the Amish colonies.

Calla creek is a community which could benefit from interventions to promote more food production and enhanced food security, training in healthy diets and good food nutritional practices, processing and non refrigerated storage of foods during periods of excess production. One such intervention is Homestead gardening which not only addresses food security, but involves women in production.

Objectives

Objectives of the demonstration are to promote the production of indigenous food varieties in small plots close to the home which would not only provide more food for family consumption but would also add diversity and enhanced nutrition to the family’s diet. This would be augmented by training in food preservation and storage of both food and seeds/planting materials.

Description

The group, of approximately 12 women, would be supplied with materials and supplies to develop and fully fence a small plot (20’X20’) of land in close proximity to their homes for the production of indigenous food varieties. A likely layout is 5 beds, each 3’X16’ separated by drains 10” wide and 4”-6” deep, and program of planting over a year as planting dates vary widely.

Bed 1. Condiments: peppers (Capsicum spp.), cilantro (Coriandrum sativum), eshallot, thyme (Thymus vulgaris), oregano (Origanum vulgare).

Bed 2. Okra (Hibiscus esculentus) followed by winter vegetables: carrots (Daucus carota), radish (Raphanus sativus), and onions (Allium cepa).

Bed3. Leafy green vegetables: Spinach, amaranths (Amaranthus spp.)

Bed 4. Potatoes (Solanum tuberosum).

Bed 5. Other starchy foods. Cocoyam (Xanthasoma sagittifolium), soup yams (Diascorea spp.).

Along the fence: sorrel, pigeon peas (Cajanus cajan), chaya (Cnidoscolus chayamansa), and vine beans, and in the drains, dasheen (Colocasia esculenta var.esculenta).

- The demonstration plot must be accessible to visitors by vehicle, and must be in close proximity to a water source.

- The housewives must each have a small area of deep well drained soil for planting 10 plantain suckers; dwarf Curare, a cultivar highly tolerant of sigatoka disease.

- Participants must attend all training sessions

- House wives must agree to bear any costs outside the budget line.

Implementation Schedule

The implementation sched ule is presented in Fig.4. It is envisaged that implementation would start in mid-July and continue into the following year, completing the entire process by August.  Six house wives would start in July and the remainding six in October. All would be trained at the same time. A supply of organic matter would be available from the commencement of the project.

Technical details/Production technology

Planting materials and seed storage. Indigenous varieties would be planted where possible.  Seed and planting materials would be collected during the crop and stored for use after disasters, and/or the next crop cycle.

Fertilizers. Acombination of organic and inorganic fertilizers would be used.

Pest control. Based on monitoring and the utilization of principles of integrated pest management where applicable.

General instructions

A sign board has to be posted at the demonstration site. A sample of which is presented in section. All demonstration records, including photographs, must be kept in an assigned ledger/electronic files at intervals as recommended in the monitoring plan. Exteme care should be taken with the storage of fertilizers and chemicals, especially in homes with small children.

Capacity building requirements

Short courses dealing with:

- Local foods, balanced and healthy diets.

- Non refrigerated preservation of foods.

- Composts from kitchen wastes and soil management.

- Virtues of team work and systematic planning.

Fig. 4 Implementation Schedule for homestead garden project, Calla Creek Cayo.

| Activities to be undertaken | Who is responsible? | Expected Output or Outcome | Monthly Chronogram(2009) |
| --- | --- | --- | --- |
|  |  |  | J | F | M | A | M | J | J | A | S | O | N | D | Etc. |
| Budgets approved and Training starts. | FAO/MAF | Implementation phase begins. |  |  |  |  |  |  | X |  |  |  |  |  |  |
| Materials and supplies procured and tools and fence materials delivered | FAO/MAF | Plot constr. Begins. |  |  |  |  |  |  |  | X |  |  |  |  |  |
| Plots fenced and beds prepared. | Housewives | Plots ready for planting |  |  |  |  |  |  |  |  | X |  |  |  |  |
| Seedbed prepared and planting begins. | Housewives | Planting starts. |  |  |  |  |  |  |  |  | X | X | X | X |  |
| Weed control and fertilizer applications. | Housewives | Maintenance and crop nutrition programs in place. |  |  |  |  |  |  |  |  |  | X | X | X | X |
|  |  |  | Monthly Chronogram(2010) |
|  |  |  | J | F | M | A | M | J | J | A | S | O | N | D |  |
| Bed prep. For May planting. | Housewives | Beds ready for May planting |  |  | X | X |  |  |  |  |  |  |  |  |  |
| Crops planted April/May with irrigation. | Housewives | Planting of annuals completed. |  |  |  | X | X |  |  |  |  |  |  |  |  |
| Site visits, record keeping, and evaluation. | FAO/MAF | M&E in place. | X | X | X | X | X | X | X |  |  |  |  |  |  |
| Evaluation report presented. | FAO/MAF | Responsibility and ownership transferred to housewives. |  |  |  |  |  |  | X | X |  |  |  |  |  |

Budget

The budget is presented in Table.12. The data show that FAO would invest $1,031.55 per housewife, while the housewife would contribute $1,020.00 or 98.9% of the former.  Budgeting was restricted to 12 housewives.

Table 12: Materials for Homestead Garden project, Calla Creek, Cayo district, Belize.

| Item of Expenditure | Amount of Input | Unit Cost | Contributions |
| --- | --- | --- | --- |
|  |  |  | FAO | Farmer Group |
| Water can (2 gals) | 1 | $14.00/each | $14.00 | - |
| Plastic drum (55 gals) | 1 | $25.00/each | $25.00 | - |
| Spray can (13.5L) | 1 | $75.00/each | $75.00 | - |
| Machete | 1 | $10.50/each | $10.50 | - |
| Garden Hose | 75ft. | $125.00 | $125.00 |  |
| Weeding tool (Cuma) | 1 | $20.00/each | $20.00 | - |
| Urea | 10 lbs | $8.25/10 lbs | $8.25 | - |
| 14:36:12 | 10 lbs | $10.75/10 lbs | $10.75 | - |
| 19:19:19 | 25lbs. | $20.00 | $20.00 |  |
| Cow manure | 10bags | $5.00/bag | $50.00 |  |
| Seed (vegetables) | Various | $50.00 | $50.00 | - |
| Seed (Plantain) | 10suckers. | $10.00/each | $100.00 |  |
| Malathion | 1 liter | $13.25/liter | $13.25 | - |
| Condifor | 52 g | $56.25/52 g | $56.25 | - |
| Multimaya wire | 1.5 roll | $120.00/roll | $180.00 | - |
| Posts | 12 | $4.00/each | $48.00 | - |
| Labor (fence & beds) | 4 man days | $30.00/man day | - | $120.00 |
| Labour (maintenance and care) | 1hr/dayX9mths. (30 man-days) | $30.00/day |  | $900.00 |
| Signs | 1 | $185.00 | $185.00 |  |
| Contingency | 5%TC |  | $40.55 |  |
| Total (per garden) |  |  | $1,031.55 | $1,020.00 |
| Total (12 Homestead gardens |  |  | $12,379.60 | $12,240.00 |

Tree crop and horticulture nursery

Context and Justification

Calla creek, with almost 10 months of water deficits, is considered more conducive in the absence of irrigation to the cultivation of deep rooting tree crops, than shallow rooting species, on the alluvial terrace along the Mopan River. Local experiences in this low rainfall area have all supported this assertion. The survival of a large proportion of fruit trees in the area in the aftermath of seventeen days of prolonged floods of October, 2008 lends further credence to the theory.

There is a genuine interest in rehabilitating the existing population of fruit trees in the area and planting more, especially short varieties, which are less susceptible to wind damage, to transform Calla Creek into a major producing area for a wide variety of indigenous fruits. This not only establishes an income base for the residents, but provides an important temporary sanctuary for people and fowls during periods of unexpected, night time, flash floods until rescue operations are launched.

Objectives

Objectives of the demonstration are to promote indigenous fruit production in the Calla Creek area through the rehabilitation of existing trees, and the development of improved planting materials in nurseries for expanding the current fruit tree base and creating an additional income generating opportunity.

Description

The group would be supplied with technical assistance from the University of Belize (UB) and MAF to assess the state of fruit trees in the Calla Creek area and in consultation with the interested residents, make specific recommendations for rehabilitation and further development. A small nursery consisting of 500 bagged plants is to be established by each of 8 persons and this would be used to develop propagation skills while producing plants for the fruit tree expansion and sale.

In addition:

- The small nursery plots must be accessible to visitors, and must be in close proximity to a water source.

- The farmers must each have established fruit trees on their property to qualify for participation.

- Areas/holdings where land stabilization and erosion control is needed would be given priority.

- Experience with fruit processing and preservation would be desirable.

- Participating residents must agree to bear any costs outside the budget line.

Implementation Schedule

The implementation schedule is presented in Fig.5. It is envisaged that implementation would start in October with 4 participants and continue during the remainder of the project. The second 4 would start in January. Scheduling of the value added phase would depend on the availability of fruit for processing.

Technical details/Production technology

To be provided by trainers.

General instructions

A sign board has to be posted at the demonstration site. A sample of which is presented in section. All demonstration records must be kept in an assigned ledger at intervals/electronic files as recommended in the monitoring plan. Exteme care should be taken that the nurseries are not accessible to animals, especially cattle as they eat the plastic. Fertilizers and chemicals should at all times be stored in a safe place, out of reach of children and animals.

Capacity building requirements

Short courses dealing with:

- Varietal selection, plant propagation of both fruit and horticultural plants, and nursery management.

- Post harvest handling of fruit, processing, preservation and marketing.

- Virtues of team work and systematic planning.

Figure.  5  Implementation Schedule.

| Activities to be undertaken | Who is responsible? | Expected Output or Outcome | Monthly Chronogram(2009) |
| --- | --- | --- | --- |
|  |  |  | J | F | M | A | M | J | J | A | S | O | N | D | Etc. |
| Assessment of needs and developing plans for nurseries. | UB/MAF | Development plans completed. |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Training in plant propagation techniques. | UB/MAF | Implementation commenced. |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Materials purchased and delivered to 4 participants. | FAO/MAF | Construction phase commenced. |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Construction of nurseries, rooting media prepared, and seed/cuttings planted. | Participants/ FAO/MAF | Nurseries completed |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Plant care, propagation, and marketing. | Participants | Nursery is active and producing. |  |  |  |  |  |  |  |  |  | X | X | X | X |
|  | Monthly Chronogram(2010) |
|  | J | F | M | A | M | J | J | A | S | O | N | D |  |
| Plant care, propagation, and marketing. | Participants | Nursery is active and producing. | X | X | X | X | X, |  |  |  |  |  |  |  |  |
| Site preparation and transplanting in the field. | Participants | Expansion phase commenced |  |  |  |  | X | X |  |  |  |  |  |  |  |
| Care in the field. | Participant. | Crop development phase commenced. |  |  |  |  |  |  | X | X | X |  |  |  |  |
| Post harvest handling of fruits from rehab trees, processing, and preservation. | UB/MAF | Value chain development commenced. |  |  | X | X | X |  |  |  |  |  |  |  |  |

Budget

The budget is presented in Table 13. The data show an investment of $1,052.63 per person by FAO, with the participant contributing $600.00 or 57% of the former.

Table 13: Materials for fruit tree grafting project, Calla Creek, Cayo district, Belize.

| Item of Expenditure | Amount of Input | Unit Cost | Contributions |
| --- | --- | --- | --- |
|  |  |  | FAO | Farmer Group |
| Polyethylene bags (10” x 14”) | 500 bags | $25.00/100 bags | $125.00 | - |
| Budding Tape | 20 rolls | $5.00/roll | $100.00 | - |
| Ideal plastic bags | 500 bags | $3.00/100 bags | $15.00 | - |
| Sharpening Stone | 1 | $10.00/each | $10.00 | - |
| Shade cloth. | 30ft | $4.84/ft | $145.20 |  |
| Rootstock Seeds | $1,000 | $0.10/each | $100.00 | - |
| Rooting hormone | 4ozs. | $6.95/oz | $27.80 |  |
| Polyfeed (19-19-19) | 50 kg | $114.00/25 kg | $288.00 | - |
| Cow manure | 10 bags | $5.00/bag | $50.00 |  |
| Contingency | 5% |  | $35.90 | - |
| Labor (constr. Bagging, grafting etc.) | 10 man days | $30.00/man day | - | $300.00 |
| Labour(maintenance and care) | 90hrs over 9mths. | $30.00/9hrs |  | $300.00 |
| Signs | 1 | $105.60 | $105.60 |  |
| Contingency | 5%TC |  | $50.13 |  |
| Total (per 500 plants) |  |  | $1,052.63 | $600.00 |
| Total (for 8persons) |  |  | $8,421.04 | $4,800.00 |

Concepcion Village

The DRM practices to be introduced are:

- Irrigation development for vegetable production.

- Local fowl production enhancement.

Supplemental watering or irrigation is essential to extending the cropping pattern into the months of November to May when crop water deficits are experienced in this area (Table 4). This period of water deficits is characterized by low to moderate rainfall and reduced risks of crop losses arising from floods and hurricanes. The traditional rainy season of June to December still requires supplemental watering on account of the distribution pattern of rainfall with significant periods of deficit within months which show an average water surplus, a pattern which is expected to worsen as climatic changes are experienced.

Local fowl production enhancement is not only a good DRM practice, but also an inexpensive way to propagate the DRM message.

The practices introduced were selected to assist the members of this group to develop both their coping and resilience capacities and as a consequence, reduce their vulnerability to hazards. The principal hazard is drought for 5 months, followed by floods and hurricanes during September and October. Irrigation allows the members to shift production away from the high risks months of September and October, to enhance their livelihoods while working together and developing a team spirit.  Local fowl production enhances food security.

Irrigation development for vegetable production

Context and Justification

Belize imports some 8-13M$ of fruits and vegetables annually which accounts for a 11yr-average of about 10% of the total food import bill (Anon., 2009). This is unacceptable for a country which has a deficit budget and GOB’s policy aims to stimulate local production of fruits and vegetables with the hope of reducing the import bill, and at the same time pursuing a path of diversification in the sugar cane belt.

Shifting production to periods of water deficit, through the introduction of irrigation, not only reduces the risks associated with crop production, common in rainfed systems, but enhances the income generating activity of small farmers, farm workers, and their families. The short growing period of most vegetable crops make them ideal for small farming systems and allows the complete production shift to the less vulnerable months of the year, diversifies the production base, enhances livelihoods, and creates greater resilience to disasters.

Objectives

To promote agricultural product diversification in the village of Concepcion, located in a sugar cane belt, an industry in decline, through the introduction of irrigation technology.

Description

An area of some 12 acres in an abandoned Papaya field in Cocepcion village has been identified for vegetable production by the Concepcion group of farmers. The site has three abandoned wells and an analysis of the water available for irrigation is presented in Table.3.  The project proposes to supply the group with training, a complete irrigation system, inclusive of T-tape for three plantings, each for 3 acres. A supply of seed, pesticide and fertilizers for the first two plantings, each of 3 acres, would be provided, and the group would be required to supply their own inputs for the third. The farmer group is expected to participate fully in all training exercises.

The program of planting is presented below. However, the group may decide to vary this schedule based on market and production conditions, but such changes must maintain a crop size of three acres at each planting, and cannot exceed the value of investments presented in the budget (Table.13).

- Sept. /Dec. Onions, carrots, potatoes, tomatoes, sweet peppers, and cabbage at ½ acre each.

- Jan/Feb.  Irrigated corn at 2 acres, ½ acre of melons, and ½ acre of onions.

- Mar. /Apr. An acre each of Sweet peppers, and tomatoes, ½ acre each of cabbage and irrigated corn.

In addition:

- The demonstration plot must be accessible to visitors by vehicle, and must be in close proximity to a water source.

- The farmers must each have a valid pesticide applicator’s licence.

- Farmers must be willing to attend and participate in training sessions, and be willing to conduct tours of their demonstration plots for other farmers. Family members are also invited to attend the training sessions.

- Experience with vegetable production and marketing is desirable.

- Farmers must agree to bear any costs outside the budget line.

Implementation time

Training is expected to start in the first week of July, with field plot implementation scheduled for mid-August. Seedbed preparation is one month before the scheduled planting dates.

Figure 6.  Implementation Schedule.

| Activities to be undertaken | Who is responsible? | Expected Output or Outcome | Monthly Chronogram(2009) |
| --- | --- | --- | --- |
|  |  |  | J | F | M | A | M | J | J | A | S | O | N | D | Etc. |
| Budgets approved and training Starts. | FAO/MAF | Implementation commenced. |  |  |  |  |  |  | X | X |  |  |  |  |  |
| Seedbed for Sept/Nov. planting: prepared and planted. | Farmers | Nursery stage, first planting completed. |  |  |  |  |  |  |  | X |  |  |  |  |  |
| Land for Sept/Nov. planting Prepared and irrigation installed and planted. | Farmers | First planting site planted with irrigation installed. |  |  |  |  |  |  |  |  | X | X | X |  |  |
| Seedbed for Jan. /Feb. planting: prepared and planted. | Farmers | Nursery stage, 2nd planting completed. |  |  |  |  |  |  |  |  |  |  |  | X |  |
|  | Monthly Chronogram(2010) |
|  | J | F | M | A | M | J | J | A | S | O | N | D |  |
| Land for Jan. /Feb. planting: Prepared and irrigation installed and planted. | Farmers | 2nd planting site planted with irrigation installed. | X | X |  |  |  |  |  |  |  |  |  |  |  |
| Seedbed for Apr. /May. Planting: prepared and planted. | Farmers | Nursery stage, 3rd planting completed. |  |  | X |  |  |  |  |  |  |  |  |  |  |
| Land forApr. /May. Planting: Prepared and irrigation installed and planted. | Farmers | 3rd planting site planted with irrigation installed. |  |  |  | X | X |  |  |  |  |  |  |  |  |

Implementation site

Abandoned papaya field in Concepcion village

Capacity building requirements

Short courses dealing with:

- Soil management for sustainable vegetable production.

- Pesticides and the impact on the environment, the user, and the consumers of produce.

- Virtues of team work and systematic planning.

General instructions

Asign board has to be posted at the demonstration site. A sample of which is presented in section. All demonstration records must be kept in an assigned ledger at intervals as recommended in the monitoring plan. Exteme care should be taken that the protocols of pesticide use are adhered to.

Technical details and production technology

Seedbeds for peppers and tomatoes must be protected from white fly (T. vaporariorum) damage. Other details are presented in the programs of activities presented in the appendix.

Budgets

Budgets are presented in Tables.14,15,and 16 and the data presented show a total FAO investment with this group of $29,963.79 with the group contributing $18,238.63 or 60.9% of the former.

Table 14: Irrigation development and vegetable production, Concepcion Village, Sept. /Dec.

| Category | Item of Expenditure | Amount of inputs | Unit Costs ($Bze) | Contributions($Bze) |
| --- | --- | --- | --- | --- |
|  |  |  |  | FAO | Farmer Group |
| Nov./Dec | Irrigation Equipment (Pump, mains, sub-mains, valves, connectors) | Various (Table.A8) | Various (Table.A8) | $7,605.00 |  |
|  | T-tape | 3 rolls | $780/roll | $2,340.00 | - |
|  | Land prep and development. (Organic matter appl.) | Various | Various | $2,400.00 | $750.00 |
|  | Mist blowers | 2 | $1,485.00 | $1,485.00 |  |
|  | Knapsack sprayers | 5 | $101.75 |  | $508.75 |
|  | ½ acre Tomatoes (seed, pesticides, fertilizer) | Various (Table.A4) | Various (Table.A4) | $1,107.68 | $500.00 |
|  | ½ acre Sweet Peppers (seed, pesticides, fertilizer) | Various (Table.A3) | Various (Table.A3) | $1616.63 | $500.00 |
|  | ½ acre each of carrots, onions, and potatoes(seed,fertilizers,pesticides) | Various (Table.A5, A6, A7.) | Various (Table.A5, A6, A7.) | $3,200.86 | $1,874.28 |
|  | ½ acre cabbage (seed,fertilizer,pesticides) | Various (Table.A2) | Various (Table.A2) | $583.24 | $500.00 |
|  | Metal sign | 1 | $282.00 | $282.00 |  |
|  | Contingency | 5%TC |  | $1,031.02 |  |
|  | Sub-totals(Nov/Dec) |  |  | $21,651.43 | $4,633.08 |

Table 15: Irrigation development and vegetable production, Concepcion Village, Jan/Feb.

| Category | Item of Expenditure | Amount of inputs | Unit Costs ($Bze) | Contributions($Bze) |
| --- | --- | --- | --- | --- |
|  |  |  |  | FAO | Farmer Group |
| Jan./Feb. | Irrigation Equipment (Pump, mains, sub-mains, valves, connectors) | Various (table) | Various (table) |  |  |
|  | Mist Blower | 1 | $1,485.00 | $1,485.00 |  |
|  | Land prep and org. matter additions. | Various | Various | $600.00 | $750.00 |
|  | 2 acre Irrigated corn (seed, pesticides, fertilizer) | Various (Table.A11) | Various (Table.A11) | $1,186.54 | $1,554.00 |
|  | ½ acre Onions (seed, pesticides, fertilizer) | Various (Table.A5) | Various (Table.A5) | $1,290.37 | $695.00 |
|  | ½ acre melons (seed,fertilizers,pesticides) | Various (Table.A12) | Various (Table.A12) | $414.62 | $241.50 |
|  | Contingency | 5%TC |  | $248.83 |  |
|  | Sub-totals (Jan. /Feb.) |  |  | $5,225.36 | $3,240.50 |

Table 16: Irrigation development and vegetable production, Concepcion Village, Mar. /Apr.

| Category | Item of Expenditure | Amount of inputs | Unit Costs ($Bze) | Contributions($Bze) |
| --- | --- | --- | --- | --- |
|  |  |  |  | FAO | Farmer Group |
| Mar./Apr. | Irrigation Equipment (Pump, mains, sub-mains, valves, connectors) | Various (table) | Various (table) |  |  |
|  | T-tape | 3 rolls | $780/roll | $2,340.00 | - |
|  | Land prep. And org. mat. additions | Various | Various | $600.00 | $750.00 |
|  | 1 acre sweet peppers (seed, pesticides, fertilizer) | Various (Table.A3) | Various (Table.A3) |  | $4,233.26 |
|  | 1 acre cabbage (seed, pesticides, fertilizer) | Various (Table.A2) | Various (Table.A2) |  | $2,166.48 |
|  | 1 acre tomatoes (seed,fertilizers,pesticides) | Various (Table.A4) | Various (Table.A4) |  | $3,215.36 |
|  | Contingency | 5%TC |  | $147.00 |  |
|  | Sub-totals (Mar. /Apr.) |  |  | $3,087.00 | $9,615.10 |
|  | Grand Total($Bze) ($US) |  |  | $29,963.79 ($14,982.90) | $18,238.63 ($9,119.32) |

El Progresso (Cayo)

The DRM practices to be introduced are:

- Agryl tunnel structures for vegetable production.

- Local fowl production enhancement.

Supplemental watering or irrigation is essential to extending the cropping pattern into the months of January to June when crop water deficits are experienced in this area (Table 5). This period of water deficits is characterized by low to moderate rainfall and reduced risks of crop losses arising from floods and hurricanes. The agryl tunnel structure allows vegetable production both in the periods of excess water and water deficits, and has the distinct advantage of reduced pesticide use, and erosion risk. This allows the production of high priced crops at both times of potential waterlogging and deficits.

Local fowl production enhancement is not only a good DRM practice, but also an inexpensive way to propagate the DRM message.

The demonstrations are designed to enhance the coping capacities, and as a consequence lower the vulnerability of the group to drought and erosion hazards. The intervention facilitates the production of high priced crops with reduced levels of pesticide use during the dry season when water for irrigation is scarce and during the rains when the risk of erosion on the rolling lands is high.

Agryl tunnel structures for vegetable production

Each farmer would be provided with materials to construct Agryl tunnels for use both in the rainy season, using clear plastic covers over the Agryl net, and in the traditional dry season with the net alone, in both cases using irrigation and pest control measures requiring less pesticide usage.

Context and Justification

Belize imports some 8-13M$ of fruits and vegetables annually which accounts for a 11yr-average of about 10% of the total food import bill (Anon., 2009). This is unacceptable for a country which has a deficit budget and GOB’s policy aims to stimulate local production of fruits and vegetables with the hope of reducing the import bill.

Agryl structures are used to produce vegetables both in periods of excess rain when waterlogging and erosion are serious risks on the shallow soils of El Progresso, and periods of low rainfall when production is seriously constrained by soil water deficits.  This would guarantee a more stable output of vegetables, and contribute significantly to the livelihood enhancement of the residents. It would also be consistent with the national goals of increased local production, reducing the need for imports.

Objectives

To promote the production of vegetables in protected Agryl tunnels during period of both low and high rainfall as a practice to mitigate risks associated respectively with water shortages and excesses. It also reduces risks associated with erosion and insect infestations.

Description

Six farmers have volunteered for the demonstrations and each would be supplied with materials to construct Agryl Tunnel structures for production of Bell Peppers during both the rainy and dry seasons. Each farmer will produce about 1/20 acre (525 plants at 2’X2’ spacing) at three times using both soil organic additives and fertilizer. Planting would coincide with periods when normal production of the crop is not possible, and the particulars production system would demonstrate:

- A system of pest control, relatively independent of chemicals.

- The benefits of soil management and reduced fertilizer use.

- Efficient irrigation water use.

- A system of crop production on shallow soils during rainy periods.

- Controlling market supply through planning and timing of production.

- The virtues of working together.

In addition:

- The demonstration plot must be accessible to visitors by vehicle, and must be in close proximity to a water source.

- The farmers must each have a valid pesticide applicator’s licence.

- Farmers must be willing to attend and participate in training sessions, and be willing to conduct tours of their demonstration plots for other farmers.

- Experience with vegetable production and marketing is desirable.

- Farmers must agree to bear any costs outside the budget line.

Implementation time

Training is expected to start in September, with field plot implementation scheduled for October for two farmers. Seedbed preparation is one month before the scheduled planting dates which covers both the wet and dry seasons, but essentially outside of the high risks months of September and October. Growth, development, and yield would be monitored and the information used to guide the future development of Tunnel structures. Completion of this group is scheduled for August 2010. A second group of four farmers would start field implementation and continue with a similar schedule until the end of the project.

Figure 7.  Implementation Schedule.

| Activities to be undertaken | Who is responsible? | Expected Output or Outcome | Monthly Chronogram(2009) |
| --- | --- | --- | --- |
|  |  |  | J | F | M | A | M | J | J | A | S | O | N | D | Etc. |
| Budgets approved and training Starts. | FAO/MAF | Implementation commenced. |  |  |  |  |  |  |  |  | X |  |  |  |  |
| Model Tunnel structure established for training.2farmers | FAO/MAF/Farmer. | Construction training completed. |  |  |  |  |  |  |  |  |  | X |  |  |  |
| Protected seedbed planted for first crop of Bell peppers. | Farmers | Seedlings ready for first planting in September. |  |  |  |  |  |  |  |  |  | X |  |  |  |
| First planting in November, rainy season planting. | Farmers | Planting first crop, at two sites completed. |  |  |  |  |  |  |  |  |  |  | X |  |  |
|  | Monthly Chronogram(2010) |
|  | J | F | M | A | M | J | J | A | S | O | N | D |  |
| Protected seedbed January, and Second planting in Feb/Mar. Dry season planting. | Farmers | 2nd planting completed, dry season crop. | X | X | X |  |  |  |  |  |  |  |  |  |  |
| Protected seedbed in March, and third planting in Apr. /May Dry season planting. | Farmers | 3rd planting completed, dry season crop. |  |  | X | X | X |  |  |  |  |  |  |  |  |
| Crop monitored and data on costs, growth, and yield collected. | FAO/MAF | Quantitative information available for Tunnel structure. | X | X | X | X | X | X | X | X |  |  |  |  |  |

Implementation site

The village of El Progresso in the Cayo district.

Capacity building requirement

Short courses dealing with:

- Agryl Tunnel structure construction and management of this structure and the family drip system.

- Soil management for sustainable vegetable production.

- Pesticides and the impact on the environment, the user, and the consumers of produce.

- Virtues of team work and systematic planning.

General instructions

Asign board has to be posted at the demonstration site. A sample of which is presented in section. All demonstration records must be kept in an assigned ledger at intervals as recommended in the monitoring plan. Exteme care should be taken that the protocols of pesticide use are adhered to.

Technical details and production technology

Seedlings must be produced under a protected structure to eradicate or reduce viral infections transmitted by white flies (T vaporariorum).

Presented in programs of production activities in the appenix.

Budgets

The budget for Agryl tunnel demonstrations planned for El Progresso village are presented in Table 16. The contribution from FAO is $29,351.88, and from the farmers mainly for labour in construction, land preparation, irrigation and crop care is $24,300.00 for the three crops, or 82.8% of the former.

Table 17:  Materials for construction of Agryl Tunnel structure

| Item of Expenditure | Amount of Input | Unit Cost ($Bze) | Contributions($Bze) |
| --- | --- | --- | --- |
|  |  |  | FAO | Farmer Group |
| Agryl | 1 roll | $1,350.00 | $1,350.00 | - |
| Lumite net. | 1/3 roll (13’X54’) | $950.00/roll | $316.67 |  |
| Clear plastic | 1 roll | $975.00/roll | $975.00 |  |
| String | 1 roll | $25.00 | $25.00 | - |
| Staples | 1 Pk | $10.00 | $10.00 | - |
| 3” Nails | 3 lbs | $3.54 | $10.62 | - |
| 1” PVC sch 40 | 20 lengths | $24.83 | $496.60 | - |
| Labour, cutting posts and constructing tunnel/protected seedbed. | 10 man-days | $30/man day |  | $300.00 |
| Crop maintenance. | 2hrs/dayX120daysX3crops (26.6man-days)X3 | $30.00/manday |  | $2,400 |
| Contingency | 5%TC |  | $159.19 |  |
| Total |  |  | $3,343.08 | $2,700.00 |
| Total(six structures) |  |  | $20,058.48 | $16,200.00 |

Table 18: Materials for family drip system of irrigation, seed, and fertilizer appropriate for agryl tunnel vegetable production unit.

| Item of Expenditure | Amount of Input | Unit Cost | Contributions |
| --- | --- | --- | --- |
|  |  |  | FAO | Farmer Group |
| Micro-Drip tape 250 m/4 mm | 3 | $250.00/each | $750.00 | - |
| ½” lay flat PE hose | 200 ft | $0.40/ft | $80.00 | - |
| 200 L PE drum | 1 | $50.00/each | $50.00 | - |
| 4/7 x 4/7 connectors | 50 | $0.50/each | $25.00 | - |
| Filter | 1 | $100.00/each | $100.00 | - |
| Crop inputs (Seed and fertilizer) 1 acre sweet peppers. | 1/6 acre | $2,820.85/acre | $470.14 |  |
| Labour inputs | 15 man daysX3crops | $30/man day |  | $1,350.00 |
| 5% Contingency |  |  | $73.76 | - |
| Total |  |  | $1,548.90 | $1,350.00 |
| Total(six systems) |  |  | $9,293.40 | $8,100.10 |

Local fowl production enhancement

Local fowl production enhancement forms part of an effort of several organizations, namely MAF, RUTA, OIRSA, and IADB to develop the institutional capacity at University of Belize (UB) to deliver training, and provide information, services, and materials for the replication of a simple, yet very effective DRM practice, as for example local fowl production, to rural Belize in an organized and sustainable manner.

Context and Justification

The success of this project in replicating good DRM practices while promoting the importance of preparedness, community planning, and mitigation in Disaster Risk Management depends in large measure on the level of institutional support received.  Though requested by GOB, the current level of support from MAF is far from encouraging. If used as an indication of support after FAO’s funding expires, then the project would join the pile of failed interventions.

It is expedient at this time therefore, to join with other organizations in developing the capacity at UB which would be used to promote DRM in a tangible way after FAO’s commitment ends. IADB has expressed an interest in developing the teaching capacity of the Department of Agriculture, UB, to deliver courses in Climate Change and Disaster Risk Management. When combined with efforts to produce materials, information and services to replicate good DRM practices, such as local fowl production, it provides a sustainable approach to enhancing coping capacities of rural communities. Developing a seed bank, and a nursery to supply dwarf cultivars of wind tolerant fruit trees, and pedigree dairy animals for sale are some of the additional ways the University plans to get more involved in Disaster risk management.

This section details FAO’s contribution to a collective effort to assist in the development of the institutional capacity at UB in the area of enhanced local fowl production.

Objective

Objectives are to develop and maintain two nucleus flocks of Rhode Island Red (RIR), and local hens, for the purpose of collecting information on the performance of crosses, supplying cockerels and incubation services to farmers for flock upgrades, all as an initial part of institutional support in replicating good DRM practices throughout rural Belize.  This along with training, materials, information, and services in support of replicating other DRM practices provides a sustainable approach to developing a Disaster Risk Management capability.

Description

Farmers’ groups would be supplied with dual purpose imported cockerels of the Rhode Island breed, at a subsidized price, to replace small and often old roosters in their flocks.  The enhancement strategy is designed to promote DRM in these communities.

FAO would join with other organizations, namely UB, OIRSA, and RUTA and establish and maintain two nucleus flocks of 100 Rhode Island hens and 100 local hens essentially to:

- Produce hatching eggs for incubation to supply replacement pullets and breeder cockerels from the Rhode Island flock.

- Crossbreed selected local hens with purebred Rhode Island cockerels to produce F1 pullets with improved laying capacity, observe, and document their performance.

- Supply surplus purebred Rhode Island cockerels to rural farmers to upgrade local flocks, while promoting a strong awareness of DRM and potential benefits.

- Create a teaching tool for poultry management, the importance of local fowl in meat production and as a powerful DRM practice for rural households in resource deficient communities.

- Initiate and establish a poultry extension program to supply information, incubation and veterinary services, and purebred Rhode Island Red pullets and cockerels to upgrade local flocks for improved egg and meat production.

The approach of developing synergies with other organizations is consistent with the objectives of FAO managed projects, and would increase capacity while ensuring continuity after this phase of the project is completed.

Implementation Schedule

The implementation schedule is presented in Fig.8. It is envisaged that implementation would start in September and the entire process would be completed by October,2010.

Technical details/Production technology

Birds:  All birds must be vaccinated against Newcastle disease. This is a free service provided by GOB in the aftermath of a recent outbreak of the said disease.

Nutrition:  The aim is to kitchen wastes, earthworms, grass and high protein forages for the local birds and the F1 crosses. The RIR chickens would be raised to four month on a diet of soybeans and corn mixtures, and slowly introduced and finished on the diet for the local and local crosses flocks.

General instructions

Asign board has to be posted at the demonstration site. A sample of which is presented in section. All demonstration records must be kept in an assigned ledger/electronic files at intervals as recommended in the monitoring plan. Exteme care should be taken to protect the flocks from outside sources of infection, through the introduction of sanitation protocols for persons moving in and out of the production sites.

Capacity building requirements

Short courses dealing with:

- Training the trainers. Short intensive course to staff in Disaster Risk management, and good Disaster Risk Mitigation practices in the Caribbean.

- Poultry management and poultry production as a DRM practice.

- Market opportunities for local fowls, local fowl eggs, and by-product utilization.

- Virtues of team work and systematic planning.

Figure 8:  Implementation Schedule.

| Activities to be undertaken | Who is responsible? | Expected Output or Outcome | Monthly Chronogram(2009) |
| --- | --- | --- | --- |
|  |  |  | J | F | M | A | M | J | J | A | S | O | N | D | Etc. |
| Repair and upgrade the current poultry production facilities. | FAO/MAF | Facilities ready for stocking. |  |  |  |  |  |  |  |  |  |  | X | X |  |
|  |  |  | Monthly Chronogram(2010) |
|  |  |  | J | F | M | A | M | J | J | A | S | O | N | D |  |
| Stock pens with Rhode Island Red chicks, and local pullets. | FAO/MAF | Project established. | X | X |  |  |  |  |  |  |  |  |  |  |  |
| Feeding, monitoring and implementation of health program. | UB/FAO | Growth and development of flocks. | X | X | X | X | X |  |  |  |  |  |  |  |  |
| Construction and introduction of nesting boxes and incubators. | UB/OIRSA/RUTA | Reproductive facilities ready. |  |  |  |  | X | X | X |  |  |  |  |  |  |
| Initiate cross breeding program, hatching and info services selection and rearing of birds for farmers. | UB/FAO | Project fully operational. |  |  |  |  |  |  | X | X | X |  |  |  |  |
| Sale of eggs, chicks, and RIR cockerels to farmers and general public. | UB | Marketing commenced. |  |  |  |  |  |  |  | X | X | X | X |  |  |
| Introduction of cockerels to farmer groups with strong awareness campaign of DRM and integrated farming systems. | FAO/UB | Promotion of DRM countrywide |  |  |  |  |  | X | X | X |  |  |  |  |  |
| Evaluation of the process, for further development. | All | Evaluated and adjusted for continuity. |  |  |  |  |  |  |  | X | X | X | X |  |  |

Budget

The budget for establishing two nucleus flocks at UB Central Farm which would act as a teaching tool, a demonstration to farmers, a source of information on the performance of crosses, a consistent and reliable source of RIR birds for upgrading local fowl flocks at the household level, and a powerful tool in DRM awareness campaign is presented in Table 18. The information shows a contribution of $17,436.83 from FAO, and $23,700.00 from the partners.

Table 19: Development of nucleus flocks of Rhode Island Red and local fowl crosses at UB Central Farm in support of a plan to enhance local fowl production.

| Category | Item of Expenditure | Amount of Input | Unit Cost ($Bze) | Contributions($Bze) |
| --- | --- | --- | --- | --- |
|  |  |  |  | FAO | Other Partners. |
| Repair and upgrade of local facilities. | Chicken Coops and range facilities. | Various | Various | $5,679.50 |  |
|  | Nesting boxes. | 10 boxes(range of six boxes) | $120.00/box range. |  | $1,200.00 (UB) |
|  | Electrification and plumbing. | Various | Various | $1,500.00 | - |
|  | Feeders and waterers. | Various | Various |  | $1,450.00 (RUTA) |
|  | Incubator units inclusive of shed, heating lamps, sexing equipment, debeakers, carton boxes. | Various | Various |  | $15,500.00 (RUTA/OIRSA) |
| RIR chickens/local fowls. | RIR hatching eggs. | 360 | $900.00 | $900.00 | - |
|  | Local chicken Pullets | 100 | $10.00/each | $1,000.00 | - |
| M&S | Feed (Soybean) | 5100lbs. | $0.75/lb | $3,825.00 | - |
|  | Feed corn. | 9500lbs | $0.36/lb. | $3,420.00 | - |
| Labour. | Care and monitoring. | 185 man-days. | $30.00/man day. |  | $5,550.00 (UB) |
| Visibility FAO/GOB | Metal sign | 1(4’x2.5’) | $282.00 | $282.00 |  |
|  | Contingencies | 5%TC |  | $830.33 |  |
| Total |  |  |  | $17.436.83 | $23,700.00 |

Budget summary and proposed disbursement schedule

The data show that for the four demonstrations along with the institutional strengthening of UB, FAO’s investments in livestock, inclusive of pasture development, is $22,035.97USD, and in irrigated crop production, $49,742.85USD making a total of $71,778.81USD.  Local counterpart investments account for $56,809.36USD or 71.2% of the former. Additional supporting data are presented in Tables A17 to A21 in the appendix. This is by no means the sum total of all activities planned as others may be added as the project progresses.

References

ANONYMOUS, (1983). Annual report of the Sugarcane Feed Centre. Pokhor Road, Longdenville, Trinidad, West Indies.

ANONYMOUS, (2009). Statistics on imports of food and agricultural inputs. Ministry of Agriculture and Fisheries, Belmopan, Belize.

ARSCOTT, T. G., BHANGOO, M. S., and KARON, M. L. (1965).  Irrigation investigation of the Giant Cavendish banana.  1. Consumption of water applied to banana plantings in the upper Aguan Valley Honduras, as influenced by temperature and humidity.  Trop.Agric. (Trinidad), vol. 42, 139-144.

FAO, (2007). Good Practices for Hazard Risk Management in Agriculture. FAO and Ministry of Agriculture, Natural Resources, and Rural Development (MARNDR) Haiti.  FAO project TCP/RLA/3101.  pps 77.

FAO, (2009a).  Good practice examples for disaster risk reduction in Cuban Agriculture.  FAO project TCP/RLA/3101.

FAO, (2009b).  Livelihood Adaptation to Climate Change in Drought Prone Areas of Bangladesh.  Technical guideline, Establishment of Field Demonstrations for Rabi season/October-March 2007-2008.  http://www.fao.org/climatechange/laceproject/en/

FOLLET, R. H., MURPHY, L. S., and DONAHUE, R. L., (1981). Fertilizers and Soil Amendments, Ch8 pgs.  395-396. Prentice Hall Inc.  N.J.

ROBERTS, D.A. & SHEARS, R. (2008) Good Agriculture Practices for Climate change Management in Grenada. FAO project TCP/RLA/3101. pps. 72.

RODNEY, W. (1981) A History of the Guyanese Working People, 1881-1905. John Hopkins University Press.  Ch.3.pps.60-89.

SELVARAJU, R. (2007) Sharing Lessons. Hazard Risk Preparedness in Agriculture: Good Practice Examples from South and South East Asia. Asian Disaster Preparedness Centre (ADPC), Bangkok, Thailand.

SPENCE, B. (2008) Good Practices for Hazard Risk Management in Agriculture.  Summary Report, Jamaica.  FAO project TCP/RLA/3101 pps.  60

Appendix

(List of tables in support of budget data)

Table A1: Irrigation equipment and costs for a drip system for 3 acres of vegetables.

| Item of Expenditure | Quantity | Unit Cost | Total Cost |
| --- | --- | --- | --- |
| 3” polyethylene hose | 2 rolls | $780/roll | $1,560.00 |
| 2” polyethylene hose | 1 roll | $570/roll | $570.00 |
| T-tape | 3 rolls | $780/roll | $2,340.00 |
| 3” polybarb T | 1 | $45.00 | $45.00 |
| 3” Honda water pump | 1 | $1,200 | $1,200.00 |
| 3” Suction line | 15ft | $9.00/ft | $135.00 |
| 3” disc filter | 1 | $350.00 | $350.00 |
| 3” polybarb male | 4 | $45.00 | $180.00 |
| 3” female adaptor | 6 | $5.00 | $30.00 |
| 3” elbow | 3 | $6.00 | $18.00 |
| 3” pvc tee | 3 | $6.00 | $18.00 |
| Reducer 3” to 1” | 1 | $8.00 | $8.00 |
| 1” female adaptor | 1 | $2.00 | $2.00 |
| 1” air relief valve | 1 | $40.00 | $40.00 |
| 3” pvc pipe | 1 length | $76.00 | $76.00 |
| 3” pvc elbow | 2 | $6.00 | $12.00 |
| 3” clamp | 10 | $2.00 | $20.00 |
| Reducer 3” to 2” | 4 | $9.00 | $36.00 |
| 2” pvc ball valve | 4 | $25.00 | $100.00 |
| 2” female adaptor | 4 | $5.00 | $20.00 |
| 2” polybarb male | 4 | $5.00 | $20.00 |
| 2” clamps | 8 | $1.50 | $12.00 |
| Pvc glue | ½ quart | $18.00 | $18.00 |
| Pvc cleaner | ½ quart | $15.00 | $15.00 |
| Teflon | 5 rolls | $2.00 | $10.00 |
| Total | - | - | $6,835.00 |
| Equipment less T-tape (2,340.00) |  | $4,495.00 |

Table.A2. Seed, fertilizer, and pesticide inputs for one acre of Cabbages based on calendar of activities, MAF.

|  | Item of Expenditure | Quantity | Unit Cost | Total Cost |
| --- | --- | --- | --- | --- |
|  | Seed (Green boy) | 11,000 | $44.75/2,500 | $179.00 |
|  | Gaucho | 1 Pk | $40.00/48 g | $40.00 |
| Herbicide | Roundup | 2 liters | $17.95/liter | $35.90 |
|  | Dual Gold (Lasso)* | ½ liter | $76.00/liter | $76.00 |
|  | Select (Fusilade)** | ½ liter | $27.00/liter | $27.00 |
| Fungicide | Amistar (Ridomil)*** | 10g | $5.75/pk | $5.75 |
| Insecticide | Dipel | 1 can | $27.95/500g | $27.95 |
| Fertilizers | 14:36:12 | 2 sks | $60.55/110 lb sk | $121.10 |
|  | KNO3 | 140 lbs | $118.25/55 lbs | $354.75 |
|  | Urea (46:0:0) | 395 lbs | $56.25/100 lbs | $225.00 |
|  | Polyfeed (19:19:19) | 44 ½ lbs | $114.00/55 lbs | $114.00 |
| Total (one acre) |  |  |  | $1,206.45 |

Input costs for ½ acre $603.23

50% fertilizer reduction on ½ acre $399.51

*Dual Gold is used as a substitute for Lasso.

** Select is used as a substitute for Fusilade.

*** Amistar is used as a substitute for Ridomil.

Table. A3.  Seed, fertilizer and pesticide inputs for one more of Sweet Peppers (Bell peppers) based on calendar of activities, MAF.

|  | Item of Expenditure | Quality | Unit Cost | Total Cost |
| --- | --- | --- | --- | --- |
|  | Seed (Lido co.) | 11 Pks | $137.50/Pk of 1,000 | $1,512.50 |
|  | Gaucho | 1 Pk | $40.00/48g | $40.00 |
| Insecticide | Condifor | 273 g | $56.25/52g | $337.50 |
|  | Lursban (Regent)* | 150 mls | $39.00/liter | $39.00 |
| Fertilizers | 14:36:12 | 2 bags | $60.55/110 lb bag | $121.10 |
|  | Ammon. Nitrate (NH4NO3) | 336 lb | $60.00/110 lb bag | $180.00 |
|  | MAP (12:61:0) | 52 lb | $156.75/55 lb bag | $156.75 |
|  | Polyfeed (19:19:19) | 70 lb | $114.00/55 lb bag | $228.00 |
|  | Pot. Nitrate (KNO3) | 270 lb | $118.25/55 lb bag | $591.25 |
| Total |  |  |  | $3,206.25 |

Input costs for ½ acre $1,603.05

50% fertilizer reduction on ½ acre $1,283.78

* Lursban is used as a substitute for Regent

Table. A4.  Seed, fertilizer, and pesticides inputs for one acre of Tomatoes based on calendar of activities, MAF.

|  | Item of Expenditure | Quantity | Unit Cost | Total Cost |
| --- | --- | --- | --- | --- |
|  | Seed (Green Pride) | 11,000 | $80.00/1,000 Pk | $880.00 |
|  | Gaucho | 1 Pk | $40.00/48 g | $40.00 |
| Fungicide | Amistar (Ridomil)* | 1 Pk | $5.75/10 g Pk | $5.75 |
| Herbicides | Gromaxone | 1 ½ liters | $16.25/liter | $32.50 |
|  | Select (Fusilade)** | 1 liter | $27.00/liter | $27.00 |
| Insecticide | Confidor | 26 g | $56.25/52 g | $56.25 |
| Fertilizers | 14:36:12 | 2 bags | $60.55/110 lb bag | $121.10 |
|  | Ammon. Nitrate | 216 lbs | $60.00/110 lb bag | $120.00 |
|  | Polyfeed (19:19:19) | 40 lbs | $114.00/55 lbs | $114.00 |
|  | MAP (12:61:0) | 65 lbs | $156.75/55 lbs | $313.50 |
|  | NuFol. Ca. | 180 mls | $31.75/liter | $31.75 |
|  | KNO3 | 132 lbs | $118.25/55 lbs | $354.75 |
| Total (one acre) |  |  |  | $2,096.60 |

Input costs for ½ acre $1,048.30

50% fertilizer reduction on ½ acre $768.90

* Amister is used as a substitute for Ridomil.

** Select is used a substitute for Fusilade.

Table. A5.  Condensed Schedule of costs for production of onions.

| Item | Contributions |
| --- | --- |
|  | FAO ($) | Farmer Group ($) |
| Land Preparation | - | 320.00 |
| Seed | 1,095.00 | - |
| Herbicide | 243.00 | - |
| Insecticide | 87.00 | - |
| Fungicide | 243.00 | - |
| Fertilizer | 533.90 | - |
| Labor | - | 968.00 |
| Irrigation System Fuel (30 x $8.50) | 255.00 | - |
| Subtotal | 2,457.85 | 1,288.00 |
| Contingency 5% | 122.89 | 103.04 |
| Grand Total | 2,580.74 | 1,391.04 |
| ¼ acre | 645.19 | 347.76 |

Table A6.  Condensed Schedule of costs for production of carrots extracted.

| Item | Contributions |
| --- | --- |
|  | FAO ($) | Farmer Group ($) |
| Land Preparation | - | 120.00 |
| Seed | 104.00 | 16.00 |
| Fertilizer (3 Urea $56.25, 14:36:12 $67.55, Potassium $96.25) | 579.00 | - |
| Thinning | - | 256.00 |
| Manual Weed Control | - | 768.00 |
| Irrigation | 128.00 | - |
| Pest Control | 308.00 | - |
| Disease Control | 179.00 | - |
| Harvesting | - | 256.00 |
| Subtotal | 1,298.00 | 1,416.00 |
| Contingency 5% | 64.90 | 70.80 |
| Grand Total | 1,362.90 | 1,486.80 |
| ¼ acre | 340.73 | 371.50 |

Table. A7.  Condensed Schedule of costs for production of potatoes.

| Items | Contributions |
| --- | --- |
|  | FAO ($) | Farmer Group ($) |
| Land Preparation | - | 130.00 |
| Seeds (1000 lbs x 0.85/lb) | 850.00 | - |
| Bags | 70.00 | - |
| Fertilizer | 991.75 | - |
| Fungicide | 180.00 | - |
| Insecticide | 163.50 | - |
| Herbicide | 71.00 | - |
| Other | 14.75 | - |
| Labor (25/man day) | - | $700.00 |
| Subtotal | 2,341.00 | 830.00 |
| Contingency 5% | 117.05 | 41.50 |
| Grand Total | 2,458.05 | 871.50 |
| ¼ acre | 614.51 | 217.88 |

Table A8: List of materials for the Concepcion irrigation system designed by the irrigation and drainage unit of MAF.

| Item of Expenditure | Amount of Input | Unit Cost | Total Cost |
| --- | --- | --- | --- |
| 1 ft dripper spacing T-tape | 9 rolls | $780.00/roll | $7,020.00 |
| 2” Blue Stripe | 3 roll | $780.00/roll | $2,340.00 |
| 3” Blue Stripe | 3 roll | $570.00/roll | $1,710.00 |
| 3” PVC Tee | 3 | $6.00/each | $18.00 |
| 3” to 2” PVC reducer | 12 | $6.00/each | $72.00 |
| 2” Ball valve | 12 | $25.00/each | $300.00 |
| 2” Male Poly Barb | 13 | $5.00/each | $65.00 |
| 2” Female PVC adaptor | 12 | $5.00/each | $60.00 |
| 3” Female PVC adaptor | 15 | $5.00/each | $75.00 |
| 3” Male Poly Barb | 12 | $45.00/each | $540.00 |
| 3” Tee Poly Barb | 1 | $45.00/each | $45.00 |
| 2” PVC Pipe | 1 length | $32.00/each | $32.00 |
| 3” PVC Cross | 4 | $40.00/each | $160.00 |
| 2” Clamps | 26 | $1.50/each | $39.00 |
| 3” Clamps | 20 | - | $40.00 |
| 3” Elbow | 3 | $12.00/each | $36.00 |
| 3” to 1” Reducer | 1 | - | $8.00 |
| 1” Female adaptor | 1 | - | $2.00 |
| 1” Air Releaf valve | 1 | - | $35.00 |
| 3” Disc Filter | 1 | - | $350.00 |
| 3” PVC pipe | 10 ft | - | $40.00 |
| 3” Check valve | 1 | - | $150.00 |
| 3” Suction Hose | 30 ft | - | $240.00 |
| 60 M3/Hr. 85 ft pressure Honda Water Pump | 1 | - | $1,200.00 |
| PVC Glue | 1 qt | $18.00/qt | $18.00 |
| PVC Cleaner | 1 qt | $15.00/qt | $15.00 |
| Teflon Tape | 10 rolls | $1.50/roll | $15.00 |
| Total |  |  | $14,625 |

Table A9: cost of production for 1 acre of potatoes in Cayo

| Activities | Quantity | Unit Cost | Total Cost |
| --- | --- | --- | --- |
| Land Preparation |  |  |  |
| Plow | 2 hrs. | $50.00 | $50.00 |
| Harrow | 1 hr. | $40.00 | $40.00 |
| Bedding | 1 hr. | $40.00 | $40.00 |
| Materials |  |  |  |
| Seed | 1,000 lbs. | $0.85 | $850.00 |
| Bags | 100 bags | $0.70 | $70.00 |
| Fertilizer |  |  |  |
| 46-0-0 | 4 bags | $32.00 | $128.00 |
| 0-46-0 | 4 bags | $31.40 | $125.60 |
| 0-0-60 | 5 bags | $26.90 | $134.50 |
| Nutrileaf | 2 pks | $10.50 | $21.00 |
| Bayfolan | 2 liters | $10.75 | $21.50 |
| Fungicides |  |  |  |
| Ridomil | 3 pks. | $60.00 | $180.00 |
| Manzate | 10 kilos | $12.50 |  |
| Insecticides |  |  |  |
| Pegasus | 1 liter | $39.50 | $39.50 |
| Confidor | 1 pk. | $60.00 | $60.00 |
| Decis | 1 liter | $64.00 | $64.00 |
| Herbicides |  |  |  |
| Sencor | 3 pks. | $7.00 | $21.00 |
| Fusilade | 1 liter | $50.00 | $50.00 |
| Other |  |  |  |
| Hormone | 1 pk. | $6.75 | $6.75 |
| Sticker | 1 liter | $8.00 | $8.00 |
| TOTAL COST OF INPUTS |  |  | $1,909.85 |

Table A10: cost of production for one acre of onions

| Activity |  | Description | Cost per Unit | Cost | Total |
| --- | --- | --- | --- | --- | --- |
| Land Preparation | Ploughing |  | 40 | 60.00 |  |
|  | Harrowing |  | 40 | 40.00 |  |
|  | Cross Plough |  | 40 | 40.00 |  |
|  | Bedding |  | 40 | 40.00 | 180.00 |
|  | Seed |  | $180.00 | 540.00 |  |
|  | Planting |  | 4 | 200.00 | 740 |
|  | Fertilizer/Granular | 0-46-0 | 38.5 | 115.50 |  |
|  |  | 0-0-60 | 32 | 64.00 |  |
|  |  | 46-0-0 | 35 | 70.00 |  |
|  |  | 13-0-44 | 75 | 300.00 |  |
|  | Fertilizer/Foliar | 20-20-20 | 12 | 24.00 |  |
|  |  | Bayfolan | 10 | 20.00 |  |
|  | Herbicide | Fusilate | 60 | 120.00 |  |
|  |  | Basagran | 36 | 72.00 |  |
|  |  | Ronstar | 54 | 54.00 |  |
|  | Insecticide | Ambush | 35 | 35.00 |  |
|  |  | Malathion | 15 | 11.25 |  |
|  |  | Vertimec | 50 | 25.00 |  |
|  | Fungicide | Amistar | 50 | 200.00 |  |
|  |  | Silvacur | 44 | 176.00 |  |
|  |  | Bravo C.M | 55 | 165.00 | 1451.75 |
|  | Onion Bags |  | 0.6 | 240.00 | 240.00 |
|  | Spreading Fertilizer |  | 2.5 | 97.50 |  |
|  | Spraying Herbicide |  | 2.5 | 37.50 |  |
|  | Spraying Insecticide |  | 2.5 | 37.50 |  |
|  | Harvesting |  | 2.5 | 200.00 | 372.5 |
| TOTAL |  |  |  | 2984.25 | 2984.25 |

Table A11: Production costs for 10 acres of mechanized corn

| Particulars | Unit Cost | Total Cost |
| --- | --- | --- |
| Bush hogging (land preparation | $35.00 | $280.00 |
| Rome plowing | $65.00 | $650.00 |
| Harrowing 2 passes | $35.00 | $525.00 |
| Seeds | $2.45 | $392.00 |
| Planting | $35.00 | $175.00 |
| Fertilizer |  |  |
| Fertilizer at planting 14-36-12 | $47.65 | $476.60 |
| Urea for( side area)before30 days of planting | $46.00 | $460.00 |
| Herbicide |  |  |
| Atrazine(2 litre/acres) | $5.86 | $117.20 |
| Prowl(1 liter/acre | $33.00 | $330.00 |
| Insecticide -Procrone (1 liter/acre) | $22.00 | $225.00 |
| Cultivate | $35.00 | $350.00 |
| Harvesting with combine(($1.30 bags/acre | $1.30 | $325.00 |
| Total |  | $4,305.80 |
| 10 % contingency |  | $430.00 |
| Grand Total |  | $4,736.27 |
| Income from Corn Production |  |  |
| Dried Corn | $0.23 | $6,750.00 |

Table A12: cost of production for 1 acre of watermelon

| Activities | Quantity | Unit Cost ($) | Total Cost |
| --- | --- | --- | --- |
| Land Preparation |  |  |  |
| Plough | 1 hr. | 40 | 40 |
| Harrow | 1 hr. | 40 | 40 |
| Seed |  |  |  |
| Top Yield | 4 oz. | 110 | 110 |
| King Charles ($85.00) |  |  |  |
| Fertilizer |  |  |  |
| Urea | 1 bag | 31 | 31 |
| 14:36:12 | 3 bags | 32.5 | 97.5 |
| Crop Finisher | 2 pks | 14 | 28 |
| Fungicides |  |  |  |
| Antracol | 10 pks | 17.5 | 175 |
| Bravo | 4 liters | 33.5 | 134 |
| Insecticides |  |  |  |
| Baytroid | 3 liters | 33.25 | 99.75 |
| Confidor | 1 pk. | 54 | 54 |
| Weed Control |  |  |  |
| Paraquat | 4 liters | 11.5 | 46 |
| Grand Total |  |  | 855.25 |

Table A13: cost of production for one acre of carrots

| HEAD | ACTIVITY | UNIT | COST/UNIT | TOTAL |
| --- | --- | --- | --- | --- |
| Land Preparation | Plough | 1 hr. | $40.00 | $40.00 |
|  | Harrow | 1 hr. | $40.00 | $40.00 |
|  | Bed Preparation | 1 hr. | $40.00 | $40.00 |
|  |  |  |  | $120.00 |
| Sowing | Seeds | 8 oz. | $13.00 | $104.00 |
|  | Sowing | 4 hrs. | $4.00 | $16.00 |
|  |  |  |  | $120.00 |
| Fertilizer | Urea | 3 bags | $37.00 | $111.00 |
|  | Phosphorus | 2 bags | $37.00 | $74.00 |
|  | Potassium | 3 bags | $37.00 | $111.00 |
|  |  |  |  | $296.00 |
| Thinning | Manual Thinning | 64 hrs. | $4.00 | $256.00 |
| Weed Control | Manual Weed Control | 192 hrs. | $4.00 | $768.00 |
| Irrigation | Irrigating 3 days after | 32 hrs. | $4.00 | $128.00 |
|  | sowing/3 days after |  |  |  |
|  | germination |  |  |  |
| Pest Control | Sevin | 16 lbs. | $11.50 | $84.00 |
|  | Rat Bait | 8 kgs. | $16.00 | $128.00 |
|  | Labour | 24 hrs. | $4.00 | $96.00 |
|  |  |  |  | $308.00 |
| Disease Control | Manzate | 2 kgs. | $12.50 | $25.00 |
|  | Benlate | 1 kg. | $34.00 | $34.00 |
|  | Labour | 30 hrs. | $4.00 | $120.00 |
|  |  |  |  | $179.00 |
| Harvesting | Manually | 64 hrs. | $4.00 | $256.00 |
| Grand Total |  |  |  | $2,431.00 |
| Average yield per acre = 8,000 lbs. (none irrigated) |  |  |

Table A14: Condensed Schedule of costs for production of 1 acre of watermelons.

| Item | Contributions |
| --- | --- |
|  | FAO | Farmer Group |
| Land Preparation | - | $80.00 |
| Seed (4 ozs) | $110.00 | - |
| Fertilizer | $145.00 | - |
| Fungicide | $309.00 | - |
| Insecticides | $153.75 | - |
| Herbicides | $72.00 | - |
| Labor (Manual Spraying/Fertilizer application/Harvesting) | - | $150.00 |
| Subtotal | $789.75 | $230.00 |
| Contingency 5% | $39.49 | $11.50 |
| Total | $829.26 | $241.50 |

Table A15: Condensed Schedule of costs of production of irrigated corn per acre.

| Item | Contributions |
| --- | --- |
|  | FAO | Farmer Group |
| Land Preparation | - | $90.00 |
| Seed (25,000 kernels) | $70.00 | - |
| Planting (8 man days) | - | $200.00 |
| Fertilizer | $157.25 | - |
| Herbicides | $82.17 | - |
| Manual Spraying | - | $50.00 |
| Harvesting (16 man days) | - | $400.00 |
| Irrigation Costs (30 days x 1 gal gas/day) | $255.00 | - |
| Subtotals | $565.02 | $740.00 |
| Contingency 5% | $28.25 | $37.00 |
| Total | $593.27 | $777.00 |
| ½ acre | $296.64 | $388.50 |

# Footnotes

C.E.C=Cation Exchange Capacity.

%BS=Percent Base Saturation.

SM1=Santa Martha,site1

SMI=Santa Martha site1

(H)=High

(VH)=Very High.

(A)=Average.

(EH)=Extremely High

(M)=Medium