Triathlon Event Management & Race Operations Manual

Lake Tinaroo, Tablelands

1.0	Pre Event Planning	2

1.1	Risk Management & Sanctioning	2

1.1.1	Risk Management Plan	2

1.1.2	Sanctioning Procedure	2

1.2	Event Approvals/Permits	3

1.3	Promotion/Sponsorship of Event	4

1.4	Organise Volunteers, Staff and Services	5

1.5	Operations (for race weekend)	7

2.0	Race Day Management	9

2.1	Event Logistics/Operations	9

2.2	Event Equipment	14

2.3	Other Important Race Operational Items	18

3.0	Post Event	19

- Introduction

This event operations and management manual has been modified from the Triathlon Queensland version to provide new and current triathlon race directors a resource to help aid in the running of an effective and efficient triathlon event.

The manual enables event operators to set time frames, identify essential tasks and identify persons responsible for each task. The manual is divided into three sections;

- Pre-Event

- Race Day Management and Operations

- Post-Event

A specific manual is to be developed for each race venue/course to help in the running and coordination of the event. The initiative also aims to increase the holistic quality of events by making them safer and better delivered.

# Pre Event Planning

## Risk Management & Sanctioning

| Risk Management | Comments | Deadline | Person | Done | Cost |
| --- | --- | --- | --- | --- | --- |
| Prepare Budget/Breakeven Analysis | Template in Appendix A Will run event as a loss. | 03/02/12 | Jonothan Hardy |  |  |
| Complete Risk Management Plan | Template in Appendix B | 03/02/12 | Jonothan Hardy |  |  |
| Sanction Event |  |  |  |  |  |
| Evaluate previous year’s event | Update Events Manual Tri De Femme Learnings | 03/02/12 | Jonothan Hardy |  |  |

### Risk Management Plan

This must be done for all events. An analysis of potential risks must be undertaken in conjunction with the Risk Matrix; the most commonly used table to assess risk.

For more information on how to implement a Risk Management plan into the running of your event please go to http://www.triathlonqld.com.au/ClubsCoaches/ClubSupportDocuments.aspx

### Sanctioning Procedure

The aims of sanctioning a race are to:

- Assist Race Organisations and Race Directors to stage safe and fair triathlon events.

- Maintain a positive image of the sport of triathlon by setting minimum standards for the staging of safe races which are accessible to all members of the community.

- Ensure that triathlon events are conducted in accordance with minimum standards of safety and fairness on a uniform basis throughout Australia, and in accordance with international standards and obligations as required by Triathlon Australia’s membership of the International Triathlon Union.

| Private race promoter/affiliated clubs: Cover $20 million | Premium | Done |
| --- | --- | --- |
| A.Sanctioned event that allows non-TA members to compete in full triathlon events (Swim, Bike, Run) and a field greater than 100 entrants | $465.00 |  |
| B.All other events (inc. Aquathlon, Duathlon and open Club Triathlon events with more than 100 entrants). | $270.00 |  |
| C. Club Sanctioned Events that allows own club members only AND maximum field 100 entrants (No sanctioning required from TQ, as Club insurance covers this event). | Nil |  |

For more information on Sanctioning and the extra benefits that it brings your event please go to; http://www.triathlonqld.com.au/Events/Howtorunanevent/SanctioningProcess.aspx

## Event Approvals/Permits

| Event Approval | Comments | Deadline | Person | Done | Cost |
| --- | --- | --- | --- | --- | --- |
| Finalise Venue/Event Dates |  | Completed | Jonothan Hardy |  |  |
| Traffic Management | Appendix C - Traffic Management Plan | Completed | Jonothan Hardy |  |  |
| Council & Venue Approvals | Council Permit Application Received. | Minimum 14 days prior to event Completed/Approved | Jonothan Hardy |  |  |
| Department of Transport Application | Applicable if using state controlled roads Road Corridor Permit Info Sheet Road Corridor Permit Application NA | Minimum 28 days prior to event | Jonothan Hardy |  |  |
| Police Permits | Police Permit Application NA | Completed/Approved | Jonothan Hardy |  | $222.00 |
| Aquatic Permit | Maritime Safety Permit NA | Minimum 90 Days prior to event |  |  | Yes |

Traffic Management – A Traffic Guidance Scheme needs to be done up for any roads that need to be used for your event. After finalising dates and the venue this should be your first port of call.

Council/Venue Approvals – They will require a Traffic Management Plan of the event (if Triathlon/Duathlon) and site plan with this application. Later add on’s to this will be Police Permits and Certificate of Currency.

Department of Transport – This is only required if your event will be on State Controlled Roads SCR) or you need to put Variable Message Boards (VMS) on the side of SCR. Council should be able to inform you if this is the case.

Police Permits – To use a road you will need a Police Permit and if you need police services you will need to apply for that as well. They again will require Traffic Management Plans upon consultation

Aquatic Permit – This will only be needed if the event swim leg is taking place where boat craft usually reside e.g. out from a boat ramp, in a boat passage etc.

## Promotion/Sponsorship of Event

| Promotion of Event | Comments | Deadline | Person | Done | Cost |
| --- | --- | --- | --- | --- | --- |
| Organise Sponsorship | Pump/Pedals |  |  |  |  |
| Advertise on Website |  | 24/02/12 | Luke Johnston |  |  |
| E-Mail to previous athletes | Newsletter to be sent | 24/02/12 02/02/12 | Matt Carman |  |  |
| Brochure, Posters, Flyer, Newsletter | Brochure developed and distributed |  | Pippa Keith |  |  |
| Advertising Signage | Put up signs around town | 02/02/12 | Jo Carman |  |  |
| Create Media Release & Distribute | Template in App. D Brochure | 24/03/12 | Pippa/Morgan Thomas |  |  |
| Road Closure Announcement in Papers | Template in App. E NA-no road closures | NA |  |  |  |
| Notify local Residents/Businesses | Template in App. F NA | NA | Morgan Thomas |  |  |
| Notify Bus lines that may be affected | Template in App. G NA | NA |  |  |  |
| Register Forms / Online Entries | registeronline | 26/02/12 | Luke Johnson |  |  |

Sponsorship – It is imperative that this is sourced at the very start of the process. It is not fun chasing around sponsors close to the event date.

Local Business/Residents – Local support of an event is integral to the eventual success and longevity of any event. Inform them early to gauge interest and try to smooth over any negativities. Ultimately local backlash can stop an event from taking place in future years.

Road Closure Announcement – When closing roads, council require you to put an advert in the general notices section of at least the local newspaper to inform the public of the event. If State Controlled roads are used regional papers may need to be utilised

Bus Lines – Clarify with council if your event affects any bus services and if so who will be informing them of the closures and ways in which they can continue picking up passengers along their affected route.

Registration – Online companies such as Register Now can be used to handle event registrations in addition to manual entries (if capability allows)

## Organise Volunteers, Staff and Services

| Organise Volunteers & Services | Comments | Deadline | Person | Done | Cost |
| --- | --- | --- | --- | --- | --- |
| Motor Cycle | NA |  |  |  |  |
| MC/ Race Commentator |  |  | Matt Carman |  |  |
| Timing | Clock set up and record overall times. |  | Chris Gould |  |  |
| Sports Trainer/First Aid/Physio | St John's or First Response St John’s (David Beckham) cairnsdivision@stjohnqld.com.au Mobile: 0413 448 004 Ph: (07) 4031 0651 | 26/02/12 | Jonothan Hardy |  |  |
| Police | Police Services Application Application submitted | 26/02/12 | Jonothan Hardy |  |  |
| Photographer | Bring Camera for use - ask Terri and Russell | 26/02/12 | Jo Carman |  |  |
| PA system | Ensure sufficient charge in batteries or power source available. | 03/03/12 | Matt Carman |  |  |
| Life Savers | Present at Pool | 26/02/12 | Gavin Butler |  |  |
| Swim Caps | NA | NA |  |  |  |
| Barrier Hire | NA | NA |  |  |  |
| Marquees | In Gear Trailer - Get repaired if possible | 03/03/12 | Matt Carman |  |  |
| Medals/ Prizes | vouchers |  | Jo Carmen |  |  |
| Portable Toilets | Toilets at venue - NA |  |  |  |  |
| Security | NA |  |  |  |  |
| Volunteers | Complete volunteer lists and email out |  | Jonothan Hardy |  |  |
| Race Referee/TO’s | Check Andrew availability | 26/02/12 | Andrew Butler/Luke Johnson |  |  |
| Portable Radio’s | Ensure charged & functional | 08/03/12 | Matt Carman |  |  |
| Ambulance | First Response | 26/02/12 | Jonothan hardy |  |  |
| Fruit & Drink for recovery | Purchase fruit and plastic cups | 08/03/12 | Pippa Keith |  |  |
| Finish Arch | Pump n Pedals and Crocs banners Collect PnP banners. Collect new Crocs banners | 06/03/12 | Luke Johnston |  |  |
| Bike Racking/Signs | In trailer. Collect trailer on Sa. | 09/03/12 | Anthony Lucas |  |  |
| Lighting | NA |  |  |  |  |
| Generator | NA |  |  |  |  |
| Food/Coffee Vendors |  | 03/03/12 | Andrew Butler |  |  |

Motorcycle – The hiring of motorcycles is required for  Triathlon’s and Duathlon’s so that Technical Officials can monitor drafting during the race.  These bikes will need to be able to seat driver and passenger

Medical – At least two first aid officers are required for the safe running of the event. One must be stationed at the finish and one can effectively utilise the ability to roam.

Police – Police will be required where there are implications to normal traffic due to the running of your event. They are typically required for the running of Triathlon’s and Duathlon’s.

Photographer – Determine what kind of things you want from your photographer, competitor photo’s versus event photo’s. This will determine who you will use.

Life Savers – Are required for the safe running of any water activity. Use of at least 1 IRB and personnel on boards around course will suffice. Donation to SLSC will be required.

Swim Caps – For any event that has a swim leg, swim caps are usually provided as a part of the race competitor pack.

Barrier Hire – This is for areas such as transition, the finish and recovery area, and if budget allows for the run course to keep spectators off. Type of Barrier hire depends on budget, e.g. Crowd Control Barriers can be hired and sponsor banners can easily be attached to these at a higher cost to orange mesh fencing and star pickets. Also affected by what kind of surface is being used, concrete vs. grass.

Security – If setting up the night before the event, security will be required overnight to ensure the safety of expensive equipment.

Recovery – Fruit, water (and if budget allows nutritional drink) supplied in recovery area for all participating athletes.

Food Vendors – Food Vendors such as coffee vans, hot food, cold food, ice creams etc. for participants and spectators.

Generator – A Generator will need to be present to supply electricity to sound, timing, blow up finish arch, lighting (for early registrations) etc.

Lighting – For those cooler months, lighting may be required if registration and bike check-in is taking place early in the morning. Also look at the need for security to have sufficient lighting overnight.

Bike Racking – The accepted amount of bikes to a length of bike racking could be 8 bikes to 2m. This ratio can differ according to the race directors wants.

## Operations (for race weekend)

| Operations | Comments | Deadline | Person | Done | Cost |
| --- | --- | --- | --- | --- | --- |
| Course Visit (2-3 times) | Complete |  | Jonothan Hardy |  |  |
| Finalise Course Layout |  | 20/02/12 | Jonothan Hardy |  |  |
| Finalise Race Times | 10 am race start | 20/02/12 | Jonothan Hardy |  |  |
| Site Plan | See below | 20/02/12 | Jonothan Hardy |  |  |
| Create Information Boards | Set up around sign on area | 10/03/12 | Registration volunteers |  |  |
| Complete operational manual |  | 03/03/12 | Luke Johnston |  |  |
| Road Closure Signage | NA |  |  |  |  |
| Competitor Information kits | Club info kits | 03/03/12 | Pippa Keith and Andrew Butler |  |  |
| Finalise Event day run sheet |  | 26/02/12 | Jonothan Hardy |  |  |
| Race Briefing Document | Appendix H | 03/02/12 | Pippa Keith |  |  |
| Equipment Checklist complete |  |  |  |  |  |
| Accommodation | NA |  |  |  |  |
| Water Quality Tests | NA |  |  |  |  |
| Volunteer Manual | Not yet developed |  |  |  |  |
| Technical Official Manual | Not yet developed |  |  |  |  |
| Race Bibs | NA |  |  |  |  |
| Athlete Competitor Information Correspondence pre event | NA |  |  |  |  |
| Photographer Manual | NA |  |  |  |  |

Course Visit – This should be done a number of times so as to familiarise yourself with the course. Go over it with an athlete as well to get their view of it as competitors sometimes see a course in a different way to an organiser.

Race Times – Make sure there is as little overlap as possible if holding a number of events on the one day.

Site Plan – This should be one of the first operational aspects completed. It may well get refined after each course visit but the main logistics of the course should be sorted when applying for council, police and transport permits.

Information Boards – Information should be fixed to a notice board using large print that enables competitors to inspect the material prior to the event. The noticeboard should include the following information; decisions on wetsuit swim, wave starts and swim cap colours, a large map of transition and course, penalties notice board, disqualification & appeals and name of race director technical delegate race referee and senior delegates. This should be located near Registration Area.

Operational Manual – This will be a working document for the race director and staff. It will outline everything that needs to be done at the venue in the lead up to the event, on race-day and pack down. This document has all information in it so that any event leader can step up into another role if required.

Road Closure Signage – For events where roads are closed or partially closed then signage along this course to inform the public will be required. Road closure times, roads to be affected and times that the roads reopen to full traffic will need to be noted.

Competitor Information Kit – The quality of the information provided to competitors before a race is essential to the success of most aspects of an entire event. The mass participation nature of triathlon, combined with the numerous safety issues demands a low tolerance for error in regard to the accuracy of the information that must be conveyed to competitors. The information included in this mail out will include; info on parking, how to get there, presentation times, when and where results will be found, likelihood of wetsuit swim, wave start order and time between, hazards on the course. Athletes now expect to receive a document like this prior to every event.

Event Day Run Sheet – This document will have all race times, race finishes, registration opening/closing times, transition opening/closing times. Presentation expected times, and who will be required to do what task.

Race Briefing Document – This document will form the overall scope of what is spoken about in the pre-race briefing. Race rules, course features etc. will be featured in this document.

Accommodation – Ensure that if accommodation is required for staff that this is booked before announcing dates of the event. Many athletes like to stay the night before so as not to rush the morning of an event.

Water Quality – If using a water facility where water quality may be a concern, it would be advisable to get the water tested at the beginning of the event process to ensure that the location that you envisage using for the event is actually suitable.

Volunteer Manual – All events are reliant on volunteers, and volunteers that are aware of what is required of them are potentially beneficial to your event. This manual will outline where they have to meet and at what time, the roles that are required to be filled, detailed descriptions of what is required of each volunteer role, the amount of time that they are required in that role and what time they are expected to be finished.

Technical Official Manual – This document should have an outline of the timings of the day. Therefore what time your first swimmer finishes and what time your last runner starts. This will also include; wave start times, transition/registration open and closing times and first and last finish of all legs.

Race Bibs – These will need to be done before the event once number of athletes of the event are finalised. Also numbering for their bags (to be stored at a secure location during the event), and for their handle bars will be required. This should all be found in the race competitor packs on the day.

Photographer Manual – Ensure that the photographer you have hired knows exactly what kind of photo’s required.

# Race Day Management

## Event Logistics/Operations

| Registration | Comments | Deadline | Person | Done |
| --- | --- | --- | --- | --- |
| Set up registration area |  | 05/02/12 | Committee and Volunteers |  |
| Race packs & checklist |  | 05/02/12 | Pippa Keith |  |
| Course maps on display | Print and have on display |  | Pippa Keith |  |
| Start/Closing time | Advertised on brochure and web |  | Matt Carman |  |
| Products/Prize monies as per entry conditions presented | NA |  |  |  |

Registration

Competitor Registrations

An efficient and orderly competitor registration process is essential if a race is to start on time, with competitors in a relatively relaxed state. Registrations should commence at least 90 minutes before the scheduled race start time, and earlier for larger races. It is normal for many competitors to arrive 30 to 60 minutes before the race starts. Registrations should close no later than 15 minutes before the race starts so that an official pre-race briefing can be given to all competitors, and to enable competitors to make their own final race preparations.

The registration process must be properly planned and resourced to ensure registrations occur without overcrowding, long queues and time delays. Registrations should take place in an indoor or sheltered outdoor area to ensure wet weather, high winds or darkness do not disrupt the process. Access to power and lighting should be considered.

Information and directional signs should be placed above head height, rather than at table level, to enable competitors to find their own way in a crowded area. The registration area should contain table areas for the following purposes:

- Late entry form completion area

- Late entry cashier

- Adequate number of category registration tables, each sharing approximately the same number of competitors

- Texta body marking areas.

Pre-Race Day Registrations

Additional optional registration times can be offered on race eve to help ease the registration time pressures that exist on race morning. This service could be provided for up to 2 hours anytime between 2.00pm and 6.00pm. This period may coincide with the arrival of out of town competitors and other competitors who wish to inspect the race venue, transition area or course before race day.

Competitor Identification Numbers

Competitor identification numbers must be prominently displayed on and by competitors at all times during a race. The numbers are essential for timekeeping, responding to medical and other emergencies, race commentary, enforcing rules and for post-race identification by the media in photographs and video footage. Competitor identification numbers should include a letter and a number. Numbers should be displayed on competitor chest plates and texta body markings, eg ‘D546’.

| Transition Area | Comments | Deadline | Person | Done |
| --- | --- | --- | --- | --- |
| Set up Transition Area |  | 11/03/12 | com and vol |  |
| Compound size |  | 11/03/12 | Jonothan Hardy |  |
| Race Briefing, audible/content |  | 11/03/12 | Matt Carman |  |
| Race marshals, quantity |  | 02/03/12 | Pippa Keith |  |
| TQ Officials, quantity |  | 02/03/12 | Andrew Butler/Luke Johnson |  |
| Open/closing times |  | 26/02/12 | Andrew Butler/Luke johnson |  |
| Competitor flow |  | 11/03/12 | Pippa Keith |  |
| Security | NA |  |  |  |
| Baggage Area | NA |  |  |  |
| Race marshals Checkout/quantity |  | 02/03/12 | Andrew Butler |  |
| Public address system |  | 11/03/12 | Matt Carman |  |

The Transition Area

General

The transition area is the area partitioned for the racking of competitors’ bikes and the storage of clothing, shoes and equipment required for each leg of the race. This acts as the point from which spectators, media and competitors watch and judge the overall appeal of the race. The general principles to be observed when designing a transition are:

- Competitors aim to spend as little time as possible ‘in transition’

- Competitor movements should be capable of being swift yet orderly

- Entry and exit points should be created so that the positioning of bikes anywhere in the transition area does not create transition time (dis)advantages

- The transition area is a place for competitors only.

Bike Rack Design

Bike racks should consist of horizontal members onto which bikes are hooked. Bikes can be hooked to a rack by the handlebars or seat. Horizontal members should be attached by ‘A’ framed supports placed at 3 metre intervals to reduce sagging or collapse under the weight of bikes. The racks should be about 1.2 metres high to ensure only 1 wheel is off the ground when a bike is hooked on the rack. Dangling bikes are an annoyance to adjacent competitors if their storage area is encroached by other bikes twisting in mid air.

Bike Rack Spacing

Bike racks should be placed in parallel rows spread 5 metres apart to create an orderly flow of competitors in and out of the transition area. The gap should be 7 metres for elite draft legal races as they tend to start and finish the bike leg together and converge on transition area in large groups.

Sufficient bike racks should be provided so that each competitor has a storage area 550mm wide to contain shows and equipment directly beneath their bike. A smaller width will create overcrowding and make it difficult for competitors to rack their bike at the end of the bike leg.

Competitor Access to Transition Area

At all times, only competitors should be permitted in the transition area. Before the registration commences, entry and exit points should be blocked until officials arrive to conduct helmet checks and bike security measures.

Competitors should be informed that they may not remove their bike once they enter the transition area. This means a competitor cannot subsequently do a cycling warm up on roads outside the transition area. The Race Referee may relax this restriction at smaller races, provided the competitor submits to another helmet check on re-entering the transition area. This will not usually be permitted, as it is unreasonable for officials to carry out an excessive number of inspections and risk causing a delay in the start of the race. Competitors may do warm-ups using wind trainers erected next to their bike storage area.

Non Competitors in Transition Area

The transition area should be a place reserved for competitors before, during and after a race. Access by non-competing parties is not permitted.

Access to the transition area should be consistently and strictly enforced by all officials, particularly at large races where overcrowding can have serious consequences. It is important that the Race Director and Race Referee liaise before the race to agree and communicate the approach to be taken on this issue. The rule may be relaxed at smaller and less formal races, but not during the race

| Swim Course | Comments | Deadline | Person | Done |
| --- | --- | --- | --- | --- |
| Set up Swim Course | NA | 11/03/12 | Gavin Butler |  |
| Water Safety | NA | 11/03/12 | Gavin Butler |  |
| Start/Exit Zone |  | 11/03/12 | Gavin Butler |  |
| Accurate distance/measure |  | 11/03/12 | Gavin Butler |  |
| Passage from exit to transition |  |  |  |  |
| Water quality/temperature | NA |  |  |  |
| Time Start | 10am | 26/02/12 | Jonothan Hardy |  |
| Wave starts | yes to be finalised | 26/02/12 | Jonothan Hardy |  |

| Cycling Course | Comments | Deadline | Person | Done |
| --- | --- | --- | --- | --- |
| Mount/Dismount Area/Line |  | 11/03/12 | Jo Carman |  |
| Race marshals |  | 11/03/12 | Pippa Keith |  |
| Course direction/clean corners |  | 11/03/12 | Jo Carman |  |
| TQ Officials |  | 11/03/12 | Andrew Butler/Luke Johnson |  |
| Draft Officials |  | 11/03/12 | Andrew Butler/Luke Johnson |  |
| Police |  | 11/03/12 | Jonothan Hardy |  |
| Communications |  | 11/03/12 | Matt Carman |  |

| Run Course | Comments | Deadline | Person | Done |
| --- | --- | --- | --- | --- |
| Race marshals |  | 11/03/12 | Anthony Lucas |  |
| TQ officials | N/A | 11/03/12 | Anthony Lucas |  |
| Communications |  | 11/03/12 | Anthony Lucas |  |
| Water stations |  | 11/03/12 | Anthony Lucas |  |
| Course layout, size, efficiency |  | 11/03/12 | Jonothan Hardy |  |
| First Bike | NA |  |  |  |
| Last Competitor Bike | NA |  |  |  |

| First Aid Area | Comments | Deadline | Person | Done |
| --- | --- | --- | --- | --- |
| Medical Tent position/visibility | At registration/finish line | 11/03/12 | Jonothan Hardy |  |
| Medical Staff/quantity | 2 | 11/03/12 | Jonothan Hardy |  |
| Secure Area | yes | 11/03/12 | Jonothan Hardy |  |
| Ease of access | yes | 11/03/12 | Jonothan Hardy |  |

Medical Area

The medical area is the base from which medical personnel issue first aid to injured competitors and other patrons at the race venue. The medical area should be:

• Located where there is a direct and clear path for distressed competitors to be escorted from the finish line to the medical area.

• Accessible by an ambulance so that seriously injured competitors can be evacuated to a hospital.

• Enclosed and partitioned so that first aid can be provided in relative privacy and protected from adverse weather ie. a tent, medical van, building or ambulance.

| Penalty Box | Comments | Deadline | Person | Done |
| --- | --- | --- | --- | --- |
| Technical Official | NA - no penalty box |  |  |  |
| Signage | NA |  |  |  |

| Water Station | Comments | Deadline | Person | Done |
| --- | --- | --- | --- | --- |
| Volunteers |  | 26/03/12 | Pippa Keith |  |
| Location | At finish line | 26/03/12 | Pippa Keith |  |

| Volunteers | Comments | Deadline | Person | Done |
| --- | --- | --- | --- | --- |
| Information |  | 11/03/12 | Pippa Keith |  |
| Task allocation |  | 11/03/12 | Pippa Keith |  |
| Briefing |  | 11/03/12 | Pippa Keith |  |

## Event Equipment

| Transition Area | Comments | Deadline | Person | Done |
| --- | --- | --- | --- | --- |
| Entry/Exit gates |  |  |  |  |
| Bike racks (in trailer) |  |  |  |  |
| Signage-gates/entry/exit (in trailer) |  |  |  |  |
| Barrier legs (in trailer) |  |  |  |  |
| Brooms (in trailer) |  |  |  |  |
| Cable ties (ensure sufficient quantity) |  |  |  |  |
| Electricity supply |  |  |  |  |
| Flag Bunting (in trailer) |  |  |  |  |
| Microphone handsets |  |  |  |  |
| Rope |  |  |  |  |
| Star pickets |  |  |  |  |
| Star pickets caps |  |  |  |  |
| Traffic cones |  |  |  |  |
| Vests for marshals/volunteers |  |  |  |  |
| Gaffa Tape |  |  |  |  |
| Barrier netting or fencing (in trailer) |  |  |  |  |
| Sponsorship Signage |  |  |  |  |
| Numbering for Racks |  |  |  |  |

| RecoveryArea | Comments | Deadline | Person | Done |
| --- | --- | --- | --- | --- |
| Chairs (in trailer) | In Trailer |  |  |  |
| Cutting board | Purchase club utensils |  |  |  |
| Extension lead |  |  |  |  |
| Toilets | NA -use pool facilities |  |  |  |
| Knives/Cutters | Purchase club utensils |  | Pippa Keith |  |
| Garbage bins | Purchase bins |  |  |  |
| Ice – Medical |  |  | Pippa Keith |  |
| Tables (in trailer) | In Trailer |  |  |  |
| Fruit |  |  | Pippa Keith |  |
| Water/Nutritional Drink | Fill water containers |  |  |  |
| Gloves | Purchase |  | Pippa Keith |  |

Post-Race Food and Drink

Once competitors have passed the timing area and have been medically assessed, they should be directed to a recovery area containing refreshments. This area should be partitioned, however, friends and family may enter the area if sufficient space and refreshments are available. Where possible, the recovery area should be shaded and located within close proximity to water taps and other amenities. Massage therapists may erect tables in the recovery area and treat competitors free of charge.

Plain tap water must be supplied in paper or plastic cups. Drink sponsor product must not be the sole or exclusive drink supplied after or during a race, as many competitors prefer plain water. All drinks should be dispensed in to cups from plastic vessels containing lids and taps. Clean plastic garbage bins may be used provided they are lined with disposable plastic bags.

- A typical selection of refreshments provided free of charge after a race includes plain tap water, apples, bananas and oranges. Subject to finances, additional refreshments such as watermelon, rockmelon, grapes and energy drinks may be provided.

- The quantity of fruit needed will depend on the taste or how ripe the fruit is, how hot the weather is and the availability of other free refreshments. A typical provision may comprise 3 orange quarters and 2 banana halves per competitor.

- Fruit should be cut into small portions to economise, minimise waste and for ease of consumption.

- Fruit may be cut the evening before a race, provided it is kept in a cool storage area overnight. Otherwise a team of cutters with sharp knives and cutting boards should complete the task on the race day before the first individual competitor completes the race.

- Relay team swimmers and cyclists should have access to refreshments as soon as they complete their leg.

- One must ensure the availability of refreshments to all competitors. One’s race time should not impinge on the availability of providences.

| Swim Course | Comments | Deadline | Person | Done |
| --- | --- | --- | --- | --- |
| Swim Caps | NA |  |  |  |
| Buoys (in trailer) | NA |  |  |  |
| Traffic cones (in trailer) |  |  |  |  |
| Star pickets | Purchase Plastic ones |  |  |  |
| Star pickets cap | Purchase |  |  |  |
| Vests for marshals/volunteers (in trailer) |  |  |  |  |
| Barrier netting or fencing (in trailer) |  |  |  |  |
| Water Safety Gear (inflatable, surf rescue) | NA |  |  |  |
| Signage (in trailer) |  |  |  |  |

| Cycling Course | Comments | Deadline | Person | Done |
| --- | --- | --- | --- | --- |
| Signage |  | 11/03/12 | See Jo Carman |  |
| Sweep vehicle |  | 11/03/12 | JC |  |
| Crowd controls, barricades |  | 11/03/12 | JC |  |
| Motor Bike Riders |  | 11/03/12 | JC |  |
| Chalk |  | 11/03/12 | JC |  |
| Carpet (for railway lines) |  | 11/03/12 | JC |  |
| Vests for marshals/volunteers |  | 11/03/12 | JC |  |
| Signage |  | 11/03/12 | JC |  |

| Run Course | Comments | Deadline | Person | Done |
| --- | --- | --- | --- | --- |
| Vests for marshals/volunteers |  | 11/03/12 | See Anthony Lucas |  |
| Brooms |  | 11/03/12 | AL |  |
| Signage |  | 11/03/12 | AL |  |
| Radios |  | 11/03/12 | AL |  |
| Traffic cones |  | 11/03/12 | AL |  |
| Chalk/Spray |  | 11/03/12 | AL |  |
| Fencing |  | 11/03/12 | AL |  |
| Hammer |  | 11/03/12 | AL |  |

| First Aid Area | Comments | Deadline | Person | Done |
| --- | --- | --- | --- | --- |
| Medical Tent |  | 11/03/12 | JH |  |
| First Aid Kits |  | 11/03/12 | JH |  |
| Stretcher |  | 11/03/12 | Jh |  |

| Penalty Box | Comments | Deadline | Person | Done |
| --- | --- | --- | --- | --- |
| Traffic Cones/Barricades | NA |  |  |  |
| Vest for Technical Official | NA |  |  |  |
| Violation List | NA |  |  |  |

| Water Station | Comments | Deadline | Person | Done |
| --- | --- | --- | --- | --- |
| Cups |  | 11/03/12 | Pippa Keith |  |
| Water |  | 11/03/12 | Pippa Keith |  |
| Gloves |  | 11/03/12 | PK |  |
| Water Container |  | 11/03/12 | PK |  |

| Event Staff | Comments | Deadline | Person | Done |
| --- | --- | --- | --- | --- |
| Water | Purchase water bottles |  | Pippa Keith |  |
| Food Packs | NA |  |  |  |
| Event Shirts | NA |  |  |  |
| Volunteer Packs | NA |  |  |  |
| Sunscreen | Purchase |  | Pippa Keith |  |
| Event Operation Manuals | Not yet developed |  |  |  |

| Registration | Comments | Deadline | Person | Done |
| --- | --- | --- | --- | --- |
| Table/Chairs |  |  |  |  |
| Marquee |  |  |  |  |
| Banners/Flags |  |  |  |  |
| Paper, Pencils & Pens |  |  |  |  |
| Sharpener |  |  |  |  |
| Clipboard |  |  |  |  |
| Permanent Marker |  |  |  |  |
| Duct/Sticky Tape |  |  |  |  |
| Blue Tac |  |  |  |  |
| Highlighter |  |  |  |  |
| Cable Ties & Safety Pins |  |  |  |  |
| White Out |  |  |  |  |
| Scissors |  |  |  |  |
| Petty Cash tin & Key | Organise from Bank | 09/03/12 | Matt Carman |  |
| Petty Cash $150 of $5 notes $100 of $10 notes $50 of gold for BBQ float | Organise from Bank | 09/03/12 | Matt Carman |  |
| Rubber Bands |  |  |  |  |
| Pencil Case |  |  |  |  |

## Other Important Race Operational Items

Competitor Rules and Violations

All incidents involving questionable competitor behaviour and rule violations must be referee to the Race Referee to decide on a penalty, if any e.g. Disqualification or warning. The rules require strict procedures to be followed by the Race Referee to effect a valid disqualification. Similarly, some rule violations can only be dealt with by accredited Technical officials who are trained in the proper procedures.

Officials – Assistance to Competitors

Marshals and other officials not only assist with safety, but also play a critical role in ensuring the race is fair. Consequently, the way in which officials and marshals help competitors can result in a competitor being disqualified, even if the competitor did not ask for the assistance given. An official must not provide assistance in the following circumstances:

- Assistance which is not given to provide for the welfare of all competitors or the public e.g. Verbally advising a competitor of the size of a lead (time or distance) held by another competitor.

- Assistance that constitutes an unfair advantage e.g. A drink station marshal cannot save a limited supply of food or drink for a favoured competitor, in so doing denying other competitors who would have otherwise received the sustenance.

- Assistance which is not consistent with an official’s area of responsibility e.g. A marshal whose job it is to indicate a direction of a course must not provide sustenance, massage or help change a tyre.

Spectator Areas and Routes

Triathlon is an exciting sport, particularly when watched from close range. Like most public events, triathlon spectators tend to gather where they choose, unless physically prevented from doing so. Spectators should be controlled to minimise their risk of interfering with the race eg. colliding with or blocking the passage of competitors. A Race Committee also has the duty to care for the safety and comfort of spectators, particularly near start, finish and transition area.

The extent to which spectators can and should be controlled must be balanced against the following constraints:

- Limited supply of crowd control equipment available to a Race Committee

- General layout of the course, roads and residences that may make it impossible to physically partition spectators from competitors

- Many kilometres of roads and paths that comprise a course, on which spectators can gather

- The need to allow spectators the ability to move freely in and around a race venue

- The right of non triathlon public to access the race venue and adjacent properties

- The effect of road closures and partitions on surrounding businesses

- The desire of spectators to move around a race venue to watch different stages of the race eg. swim shoreline to transition area, to run course

- The unpredictable tendency for people to put themselves at risk by entering onto the course eg. young children

A Race Director must prioritise the use of crowd control equipment and marshals to ensure:

- The progress of competitors is not unduly impeded by crowds of spectators

- The size of a crowd does not create an imminent risk of spectators being forced into the path of moving competitors.

| Crowd Control Equipment and Measures |
| --- |
| Free standing grated steel barriers | Signage |
| Road barriers and legs | Traffic cones |
| Single strand flagged bunting or tape | Marshals (with loud hailers) |
| Parra-webbing and star pickets | Frequent warning from the race announcer |
| Reusable fencing wire eg. 7 strand fencing |  |

Note: If spectator areas are bisected by the course, a single pedestrian crossing, controlled by marshals, should be created to concentrate spectator movement and risks at one location.

# Post Event

Post Event Tasks

| Post Event Tasks | Comments | Deadline | Person | Done | Cost |
| --- | --- | --- | --- | --- | --- |
| Presentation of awards |  |  |  |  |  |
| Site Pull Down |  |  |  |  |  |
| Announce the results on the website |  |  |  |  |  |
| Volunteer Officials –reward and recognition |  |  |  |  |  |
| Media Release |  |  |  |  |  |
| Survey Competitors |  |  |  |  |  |
| Event Evaluation |  |  |  |  |  |
| Final Report |  |  |  |  |  |
| Compare Budget to Actual Cost |  |  |  |  |  |
| Start Again!!! |  |  |  |  |  |

APPENDIX A – Event Budget Template

| Item | Debit | Credit |
| --- | --- | --- |
| Super Sprint - est 30 x participants @ $30 | $ - | $ 900.00 |
| Sprint - est 40 participants @ $30 | $ - | $ 1,200.00 |
| Junior(U16)-est 15 participants any event @ $20 |  | $ 300.00 |
| Member discount ($10) - estimate 35 members | $ 350.00 | $ - |
| Police | $ 250.00 | $ - |
| Council | $ - | $ - |
| Advertising (Newspaper) | $ 400.00 | $ - |
| Ribbons/Prizes/Trophies | $ 300.00 | $ - |
| TA sanctioning | $ 270.00 | $ - |
| TA Services fee ($1.70 x 84) | $ 150.00 | $ - |
| First Response | $ 600.00 | $ - |
| Signs (portion of numbers already purchased) | $ 35.00 | $ - |
| Fruit and Ice/Rehydration | $ 150.00 | $ - |
|  | $ - | $ - |
| Expenses /Income Totals | $ 2,505.00 | $ 2,400.00 |
| Profit/Loss |  |  |
| Cost per participant to break even | $ 30.00 |  |

APPENDIX B – Risk Management Plan

| Risk Management Framework | Consequence |
| --- | --- |
|  | Catastrophic | Severe | Major | Moderate | Minor |
|  | Most objectives may not be achieved or severely affected. Fatality | Most objectives threatened, or one severely affected. Serious injury/Disablement with long term effects | Some objectives affected, considerable effort to rectify. Serious injury without long term effects (e.g. unconscious) | Easily remedied, with some effort objectives can be achieved. Medical Treatment | Very small impact, rectified by normal processes. First Aid or no treatment |
| Likelihood | Almost certain | EXTREME | EXTREME | EXTREME | MEDIUM | MEDIUM |
|  | Will probably occur, could occur several times per season | 1 | 1 | 1 | 3 | 3 |
|  | Likely | EXTREME | EXTREME | MAJOR | MEDIUM | MINOR |
|  | High probability, likely occur once a year | 1 | 1 | 2 | 3 | 4 |
|  | Possible | EXTREME | EXTREME | MAJOR | MEDIUM | MINOR |
|  | Reasonable likelihood that it may arise over a five year period | 1 | 1 | 2 | 3 | 4 |
|  | Unlikely | MAJOR | MAJOR | MEDIUM | MINOR | MINOR |
|  | Plausible, could occur over a five to ten year period | 2 | 2 | 3 | 4 | 4 |
|  | Rare | MEDIUM | MEDIUM | MEDIUM | MINOR | MINOR |
|  | Very unlikely but not impossible, unlikely over a 10 year period | 3 | 3 | 3 | 4 | 4 |
| Risk Priority |  |
| 1. EXTREME – Likely to arise and have potentially serious consequences requiring urgent attention |
| 2. MAJOR – Likely to arise and have potentially serious consequences requiring urgent attention or investigation |
| 3. MEDIUM – Likely to arise or have serious consequences requiring attention |
| 4. MINOR – Risks and low consequences that may be managed by routine procedures |

| Potential Risk | Likelihood | Severity | Risk Rating | Controls | Resources | Responsible Person | Actions |
| --- | --- | --- | --- | --- | --- | --- | --- |
| SWIMMING | This category includes all of those risks associated with the conduct of racing or training where the participants are swimming. Swimming risks will vary depending upon the nature of the activities, experience of participants and organisers and the location(s) in which they are conducted |
| GENERAL |  |  |  |  |  |  |  |
| Unforseen weather changes (including electrical storms) resulting in athletes and volunteers being exposed during training & events |  |  |  | Lake swim with safety officers. Cancel event if electrical/severe storms |  | RD |  |
| Insufficient supervision of juniors/novice athletes resulting in accidents or personal injury |  |  |  | Adopt TA age restrictions. Marshalls on course. Race briefing | Marshalls Briefing TO in transition | RD |  |
| Personal injury to selves or others as a result of inexperienced athletes participating beyond their capacity |  |  |  | Sprint race distance. Lake swim - calm waters | Course design First aiders present | RD |  |
| Personal injury resulting from athletes participating beyond their physiological capabilities |  |  |  | Sprint race distance. Lake swim - calm waters | Course design First aiders presen | RD |  |
| Drowning from insufficient supervision or safety equipment |  |  |  | Sprint race distance. Lake swim - calm waters- water safety officers - bronze | Lifesaver | RD |  |
| Lack of safety/rescue equipment for training and events |  |  |  | Sprint race distance. Lake swim - calm waters- water safety officers - bronze | Marshalls. Radioes, phones |  |  |
| Loss of communication resulting in not being able to provide effective rescue services. |  |  |  | Mobile phone and radioes | Mobile phone. Radioes | RD | Ensure sufficient charge |
| Sun stroke/ sunburn / dehydration to athletes or volunteers |  |  |  | Briefing, sunscreen provided to volunteers. |  | RD |  |
| SPECIFIC | The risk associated with triathlon programs will vary between clubs and locations. Here is for risks that you have identified specific to your club for the SWIMMING category |
| CYCLING | This category includes all of those risks associated with the conduct of racing or training where the participants are cycling. Cycling risks will vary depending upon the nature of the activities, experience of participants and organisers and the location(s) in which they are conducted |
| GENERAL |  |  |  |  |  |  |  |
| Collision with stationary objects resulting in personal injury |  |  |  | Course review on day of event. Briefing on any obstacles |  | RD |  |
| Collision with motor vehicles resulting in personal injury |  |  |  | Briefing to notify open roads and rules apply. Signage along roads. marhsalls, Police, and traffic controllers | Signage. marhsalls, Police, traffic controllers, briefing | RD |  |
| Collision with other cyclist resulting in personal injury |  |  |  | Briefing, course design, |  | RD |  |
| Collisions within transition area, leading to damage of equipment |  |  |  | Course design, mount/dismount line and marshall | Marshall | Mount/Dismount line marshall |  |
| Uneven or loose surface leading to personal injury |  |  |  | Sealed roads, briefing, course check before event | briefing | Cycle course set up marshall |  |
| Poor repair or breakage of cycling equipment resulting in personal injury |  |  |  | Individual responsible for own equipment, TO in transition to check | TO | TO |  |
| SPECIFIC | The risk associated with triathlon programs will vary between clubs and locations. Here is for risks that you have identified specific to your club for the CYCLING category |
| RUNNING | This category includes all of those risks associated with the conduct of racing or training where the participants are running. Running risks will vary depending upon the nature of the activities, experience of participants and organisers and the location(s) in which they are conducted |
| GENERAL |  |  |  |  |  |  |  |
| Collision with motor or other vehicles resulting in personal injury |  |  |  | Signage, dead end street,briefing, use of footpaths where possible. | Signage | Run Course marshall, RD |  |
| Personal injury resulting from poor running apparel/equipment |  |  |  | Individuals responsible for own equipment |  | Competitors |  |
| Loose or slippery surface leading to personal injury |  |  |  | Course layout and review on day of event |  | Run course marshall |  |
| SPECIFIC | The risk associated with triathlon programs will vary between clubs and locations. Here is for risks that you have identified specific to your club for the RUNNING category |
| PRE & POST EVENT | This category refers to the risk involved in activities, which precede and follow competition or training activities. The set up and retrieval of athlete equipment and preparation activities of race organisers should all be considered. It also focuses on the club and surrounding environments which are utilised by members, participants and in some circumstances, the general public. |
| General |  |  |  |  |  |  |  |
| Theft or damage of participants bikes or gear due to poor security or storage of equipment |  |  |  | Transition open on morning of race. Bike numbers | Bike numbers | Registration desk |  |
| People or Vehicles passing through transition or preparation areas resulting in personal injury to athletes or public, or property damage |  |  |  | Transition park - grassed area- block access |  | Transition Marshall |  |
| Equipment left lying around inappropriately resulting in personal injury |  |  |  | Post clean up. Pre event sweep of area |  | Marshalls RD |  |
| Inappropriately stored equipment resulting in personal injury or property damage. Equipment not tied down during transit resulting in personal injury or property damage |  |  |  | Trailer storage for all gear |  | Marshalls RD |  |
| Careless loading/unloading and laying of event and course equipment may result in specific and chronic injuries to athletes or volunteers |  |  |  | Course maps. Experienced (at least one) course set-up marshalls, briefing |  | RD |  |
| Slippery surfaces resulting in personal injury or equipment damage (water/wood/tiles/concrete) |  |  |  | Post clean up. Demarcate areas of concern using witches hats |  | Marshalls, RD |  |
| Insufficient attendance to spills and breakages which may result in personal injury |  |  |  | Marshalls to monitor |  | Marshalls |  |
| Non compliance with permits/regulations/sanctioning resulting in penalties and personal injury claims |  |  |  | Follow race manual and document issues |  | RD, Marshalls |  |
| SPECIFIC | The risk associated with triathlon programs will vary between clubs and locations. Here is for risks that you have identified specific to your club for the PRE & POST EVENT category |
| Stakeholder and community complaints |  |  |  | Signage, monitor complaints and investigate |  | RD |  |
| PERSONNEL | This category includes club members, officials, participants, parents and spectators who may be involved in triathlon activities. The club owes a duty of care to those people who may be affected by its actions and therefore should ensure that it takes steps to manage the risks which may confront club personnel, in addition to those risks which arise as a result of their conduct |
| General |  |  |  |  |  |  |  |
| Volunteers appropriately qualified and current blue card holders |  |  |  | Briefing. only blue card holders in positions where interacting with juniors |  | RD |  |
| Insufficient communication processes for members to alert club officials of harassment or incidents |  |  |  | Briefing, TA policies |  | RD |  |
| Harassment of participant/ members from officials or other members |  |  |  | TA policies |  | RD, TO |  |
| Poor promotion of emergency procedures and contact numbers to club members |  |  |  | Triple zero to be used. Briefing to volunteers |  | RD |  |
| Lack of appropriate first aid equipment available to treat injuries or accidents as they occur |  |  |  | first Response present | First aid kit | RD, Medical team |  |
| Poor communication to emergency service providers of club location and access details resulting in delay in emergency treatment |  |  |  | Race manual, notify Qld Ambulance |  | RD |  |
| Poor induction of volunteers and communication of responsibilities and duties resulting in confusion and possible neglect of tasks |  |  |  | Volunteers lists. Volunteer briefing |  | RD |  |
| Poor food management and handling procedures in catering and canteen areas of club may breach regulations (more in-depth risk assessment required by appropriate club personnel) |  |  |  | Follow council guidelines |  | BBQ volunteers |  |
| SPECIFIC | The risk associated with triathlon programs will vary between clubs and locations. Here is for risks that you have identified specific to your club for the PERSONNEL category |
| Volunteers affected by infectious diseases |  |  |  | Gloves available. First aiders to wear gloves | Gloves | First aiders |  |

APPENDIX C – Traffic Management Plan/Course Maps

LAKE TINAROO TRIATHLON  MARCH 2012  SWIM COURSE

- SUPER  SPRINT -350M- ONCE AROUND BUOY B

- SPRINT – 750M- TWICE AROUND THE BUOYS THEN BACK TO SHORE

- SHORE TO A – 75M

- A-B , B-C. C- A-- 100M

LAKE TINAROO TRIATHLON  MARCH 2012  BIKE COURSE

- 10KM LOOP

- SUPER SPRINT – 1 LOOP(10KM) AND SPRINT 2 LOOPS (20KM)

- BIKE TRANSISTION – LAMB ST, BIKE TURNAROUND – LAKE TINAROO RD.

- REFER TO TURNAROUND  DETAIL  DRAWINGS  FOR TRAFFIC FLOW AND CONTROL

BIKE COURSE TURNAROUND – LAKE TINAROO RD

- TRAFFIC CONTROL BY QUEENSLAND POLICE WITH ASSISTANCE FROM CAIRNS CROCS MARHSHALL AS REQUIRED

- “BIKE TURNAROUND SIGNS ON APPROACHES FROM BOTH DIRECTIONS WITH “BIKE ON ROAD SIGN ALONG THE COURSE.

BIKE COURSE TURNAROUND – TRANSITION- EXIT AND ENTRY

- ENTICERS – 1 LOOP  THEN PROCEED DOWN BIKE ENTRY TO TRANSITION

- SUPER SPRINT – AFTER FIRST LOOP PROCEED AROUND BOLLARD .

BIKE COURSE TURNAROUND – TRANSITION- EXIT AND ENTRY

TRAFFIC MANAGMENT PLAN

BIKES

TRAFFIC FLOW

MARSHALLS

Bike Route Description

- Leave Transition and head along Lambs Road for approx 50 metres, a Marshall we positioned at the exit of transition and Lambs road.

- After turning onto Tinaroo falls dam Road , again another Marshall will positioned on TFD road to make flowing traffic behind aware of cyclists on road, head out of the township for 5km.

- The turnaround is positioned along TFD road approx 1km before the Exploration Rd, see attached.

- Turnaround is positioned on a long straight with good visibility for approaching traffic in both directions.

- A Marshall and signage will be located approx 100m from the turnaround to advise riders to slowdown.

- Signage will also be position 200m approaching to the signage in both directions warning vehicles of oncoming turnaround and that cyclists are on the road.

- A sign will also be placed at the Kairi primary school advising of cyclists.

- Signage will be placed intermittently throughout the courses make the public aware that cyclists are on the road.

- The TFD Rd. turnaround will be controlled by Queensland police.

- After cyclists round this point they will ride back into Lambs St., approx- 5km.

- Signage will be placed at Russel Road and TFD rd making vehicles aware of cyclists ahead also on other approaching road form the dam side.

- The second turnaround for the course will be located to the side of the road/car park 9 see attached) next to transition, The 10km course does not turnaround but will head straight into transition , same traffic management applies.

- Turnaround and transition Entry manned by 2 Marshalls within eyesight of each other and approaching cyclists and traffic.

- Traffic Flow on TFD Rd and Lamb St will be stopped when required to give right of way to cyclists .

- A leeterbox drop will be conducted to make residents aware of event.

- Sprint – 2 loops of bike course- 20km

- Super sprint – 1 loop of bike course- 10km.

LAKE TINAROO TRIATHLON  MARCH 2012  RUN COURSE

- 2.5KM LOOP

- SUPER SPRINT – 1 LOOP(2.5KM) AND SPRINT 2 LOOPS (5KM)

Runners  will leave transition  and run the course anticlock wise on the attached route.

Turnaround

Marshall

APPENDIX D – Media Release

APPENDIX E – Road Closure Announcement

APPENDIX F – Notification to local Residents/Businesses

APPENDIX G – Notification to Bus l

APPENDIX H – Race Day Briefing

Welcome and thank sponsors, competitors and volunteers

Notify of distances

Swim Course

Explain swim course

T1

Find bike, helmet on first

If first time, take your time in transition

Run/walk bike to mount line

Cycle course

Details of course outlay

Bike course – open roads (not closed roads), be aware of cars and obey normal road rules, keep to left

No two abreast riding unless overtaking – Marshal’s will be watching for this

Road rules apply – you must give way to traffic as if you were going for a normal Sunday ride.

Additional care taken when crossing roads – turning right.

Police will be – you must obey all direction by the police officer.

Slow down for turnaround point.

T2

Rack bike same place – helmet off last thing

No drafting- 7m apart (car length), will be TO out on course

Again take your time

SES will be on slowing traffic but not stopping traffic - Take care in these areas

Run Course

Details of course outlay

laps

Each time you come in and out of transition call out your number so you make sure you get splits

Rules Other

Presentations at the end – age group placing and random draws

BBQ – 1 free per competitor, spectators to purchase

APPENDIX I – Volunteers List

| Role | Numbers Required (from Traffic Mgt Plan) | Name(s) | Contact Details |
| --- | --- | --- | --- |
| Registration set up | 1 | Rego persons |  |
| Cycle Course set up | 2 |  |  |
| Transition set up | 4 |  |  |
| Run course set up | 1 |  |  |
| Cycle Course Marshalls | 3 |  |  |
| Traffic Control | 2 |  |  |
| Transition Marshall | 1 |  |  |
| Water/Aid station | 4 |  |  |
| Swim exit assistant | 2 |  |  |
| Cycle course sweeper | 1 |  |  |
| Timing officials | 2 |  |  |
| Race Referee | NA |  |  |
| Technical Official | 1 |  |  |
| Registration | Min. 2 4 |  |  |
| Body Marking | 2 |  |  |
| BBQ cook | 1 |  |  |
| BBQ helper | 1 |  |  |

# Text boxes

Transition

TRANSITION

BIKE ENTRY

TURN AROUND -SPRINT

BIKE EXIT

Transition

Buoy A

Buoy C

Buoy B