Caritas MADDO

(The Development Commission of Masaka Diocese)

Five Year Strategic Plan: 2007-2011

Programme for Spearheading Sustainable Development for Poverty Reduction and Improved Life in Masaka

Address:

Caritas MADDO

Masaka Diocese

P O Box 14 Masaka

Ddungu Wing, Kitovu Cathedral Road

Tel: 256-481-420976

Email: maddo@africaonline.co.ug

July 2007

TABLE OF CONTENTS

Overview of Program	iii

List of Acronyms	iii

List of Acronyms	iv

Acknowledgements	v

Foreword	vi

Executive Summary	vii

1.0 INTRODUCTION	- 7 -

2.0 BACKGROUND: SOCIO-ECONOMIC CHARACTERISTICS	- 7 -

2.1 Country Profile	- 7 -

2.2 Profile of the area Masaka Diocese covers	- 8 -

2.3 Natural Environment	- 8 -

2.4 Water Resources Availability: Demand and Usage	- 9 -

2.5 HIV/AIDS	- 9 -

2.6 The Dimensions of Poverty in Masaka	- 10 -

2.7 National Poverty Strategies	- 11 -

3.0 BACKGROUND: Reviewing the Past Five Years	- 11 -

3.1 Overview of Strategic Plan 2001-2006	- 11 -

3.2 Critical Analysis of  The Masaka Synod V on Development	- 12 -

3.3 Rapid Community Assessment	- 13 -

3.4 Critical Analysis of the Health Function	- 15 -

3.5 General Implementation Gaps in the SP (2001-06)	- 15 -

4.0 ANALYSIS OF ORGANIZATIONAL ISSUES	- 16 -

5.0 The Current State of the CBO Sector at Grassroots Level	- 17 -

6.0 Summary of Key Issues relevant to the New Strategic Plan	- 18 -

7.0 THE NEW STRATEGIC DIRECTION (2007-2011)	- 19 -

7.1 Vision	- 19 -

7.2 Mission	- 19 -

7.3 Organisational Values	- 19 -

7.4 Goal	- 19 -

7.5 Objectives	- 19 -

7.6 Target Population	- 24 -

7.7 Other Components	- 24 -

8.0 Monitoring and Evaluation:	- 24 -

9.0 Financing	- 25 -

10.0 Sustainability Issues	- 26 -

Annex1:  Organizational Chart for Caritas MADDO:	- 27 -

Annex 2: The Logical Framework (2007-2011)	- 30 -

Annex 3: Budget	- 55 -

3.1: Budget Notes	Error! Bookmark not defined.

3.2 Budget Summary	Error! Bookmark not defined.

# Overview of Program

Cross cutting Issues: HIV/AIDS Mainstreaming, Gender mainstreaming

List of Acronyms

ABY	Abstinence, Be Faithful Project for the Youth

AIDS		Acquired Immunity Deficiency Syndrome

CBO		Community Based Organisation

CEDAW	Convention for Elimination of Discrimination Against Women

DHB		Diocesan Health Board

DHU		Diocesan Health Unit

GDP	Gross Domestic Product

GNP	Gross National Product

HC		Health Centre

HIV		Human Immuno-deficiency Virus

HOD		Head of Department

HOSEAP	Household Support to Eradicate Absolute Poverty

HRM/D	Human Resources Management/ Development

HRMIS	Human Resources Management Information System

HUMC	Health Unit Management Committee

IMF	International Monetary Fund

IMR		Infant Mortality Rate

LC		Local Council

LEDEWO	Legal Defence for Widows and Orphans

MADDO	Masaka Diocesan Development Organisation

MDG	Millennium Development Goals

MFI	Micro Finance Institutions

MHCP		Minimum Health Care Package

MIS		Management Information System

MMR		Maternal Mortality Rate

MMT		Middle-level Management: Technical

MOV		Means of Verification

MR		Mortality Rate

MSC		Masaka Social Centre

NGO		Non Governmental Organisations

NMR		Neonatal Mortality Rate

NRM		Natural Resources Management

OSID	Organisational Strengthening and Institutional Development

OVC       	Orphans and Vulnerable Children

PEAP	Poverty Eradication and Alleviation Program

PHC		Primary Health Care

PHH	Post Harvest Handling

PNFP		Private Not for Profit

PO		Program Officer

PRSP	Poverty Reduction Strategy Paper

ROM		Results Oriented Management

SAMADI	Sustainable Agriculture for Masaka Diocese

SHUPO	Sickness, Hunger and Poverty Alleviation

SMA		Senior Management: Administration

UCMB		Uganda Catholic Medical Bureau

UNDP	United Nations Development Program

WASIP	Water, Agriculture and Sanitation Integrated

Acknowledgements

The strategic plan is a result of reflection, consultations and discussions by community partners, collaborating organizations/individuals, development partners and Caritas administration and staff. Caritas MADDO has no adequate words to thank the funder Aidlink who is always willing to support the organisation in its road to self reliance.  Indeed Caritas MADDO is very appreciative for the support of Aidlink who funded this process.

Caritas MADDO recognises the contribution of the many community partners who support the work of the organisation based on a spirit of volunteerism.  Volunteers scattered in all corners of our Diocese have always been supplementing scarce resources both in various ways, be it time, social and financial terms.  Caritas MADDO is indeed very grateful for their work.

Sincere gratitude and appreciation to all local partners and the staff of Caritas MADDO not only  for the active participation in the process of developing this plan, but also the support in the work of the organisation all over the diocese.

If there is anything at all that we have achieved in 25 years, it is no other than the Bishop’s plan and efforts.  The work of the office of the Bishop can be compared to a coach of a team who recruits and selects players, trains them, sends them, watches them while playing, directs them and again plans for the success of his team.

We thank the Bishop and all staff in the chancery for the good work you do for us. Lastly Caritas MADDO thanks Mr. John Kizito and his team for the work well done as the facilitator of this whole exercise.

Foreword

This five year strategic plan has been prepared with the participation of key Caritas MADDO stakeholders including administration, staff, beneficiaries and resource persons from other development organizations that collaborate with Caritas MADDO.  This process was externally facilitated.  It is a forward looking strategic plan that embodies the aspirations of the organization to contribute to an inclusive world and the improvement of the livelihoods of the people in the districts of Masaka, Kalangala, Ssembabule, Rakai and Lyantonde.

The programme components outlined in the plan are built on achievements and adjustments based on key issues arising from various learning processes within the programme in the past.

Important development issues within the organizational and Ugandan context are integrated as cross-cutting issues.  Despite the achievements Caritas MADDO has made there remains glaring challenges in improving livelihoods of the rural men and women in Masaka Diocese.

Erstwhile, the main strategy has been direct support to individuals, the programme has evolved over time based on the wealth of experience the organization has gained. In the next five years, Caritas MADDO intends to progressively groom and reach the beneficiaries through Community Based Organizations/institutions.   Caritas MADDO, together with the Community administrations will progressively identify nascent Community Based Organizations and groom them to co-implement programs at the community level and carry on when the organization moves to other areas. We hope to invest more in organizational strengthening and Institutional development support to community based organisations as an important strategy in the implementation of our programme and nurture the growth and development of strong vehicles for development initiatives in Masaka Diocese.

Sustainable development can only be achieved through the process of empowerment and capacity building/development of all stakeholders that are involved. This ensures a participatory development process and leads to need-driven development rather than demand driven development.

The Chinese have a proverb which says; “If a snake bites you it is an accident.  If the same snake bites you twice you are fool”.  Stakeholders will be right to blame us – Caritas MADDO staff if we fail to improve our performance after supporting us with a lot of ideas in this exercise.  We promise to aim higher and we appeal to all our partners and stakeholders of Masaka Diocese in your respective capacities, to support us in making the implementation of strategies detailed herein a success.

Fr. Raphael Semmanda

Development Coordinator

Executive Summary

After five years, it was important for the organisation to undergo a deep reflection and analysis of its core purpose and mode of operation.  Quite a number of issues emerged form the critical self assessment that guided this strategic plan. For instance a need to correct existing management anomalies was identified and in order to be more effective, there is need to find a way continuously re-assessing the organisational resources and revitalising them.

It was also found important to redefine Caritas MADDO’s coverage and consider decentralization of some aspects e.g. Caritas MADDO facilitating Community-based initiatives rather than compete with them All organisation documents and policies need to be reviewed and updated. All Caritas MADDO focal areas and programs should include cross cutting areas of HIV/AIDS, environment, and not forgetting gender issues which does not seem to be the case now.

Inspired by the vision to see the people of Masaka Diocese attain holistic development through stimulating and directing sustainable development Caritas MADDO will stimulate and direct sustainable development among the people of Masaka diocese regardless of religious affiliation, with the goal of improving the standards of living for their standards of living.

This Plan will focus on the following major focal areas: Ensuring Food security, increasing peoples’ incomes through sustainable agribusiness; Organisational Strengthening and Institutional Development; Preventive and curative health for development; promotion of human Rights and Good Governance Strategies; and Promote the value of working together to assist the needy in our communities. Gender and HIV/AIDS will be mainstreamed in all programs

Caritas MADDO will disseminate skills in sustainable agriculture practices and technologies: Agro forestry; modern crop and animal management; environmental protection; appropriate technology; management of small IGAs and food processing and preservation. Caritas MADDO will also support farmers add value to farm products for better income.

Under social services the organisation will endeavour to uplift the socio-economic barriers of the socially handicapped and marginalised members of society through provision of basic amenities, counselling, education and protection of widows’ and orphans’ rights. Caritas MADDO will sensitise the community on the spirit of assisting the needy in their communities.  The organisation will also offer both curative and preventive health services.  It will also be of prime importance to improve community access to water and better sanitation.

Strategically, Caritas MADDO will gradually change the operational framework from direct implementation to supporting and working in partnerships with parishes and local organizations implementing programmes at the grassroots.

Caritas MADDO, through the program officers, will design a comprehensive monitoring and evaluation framework based on the indicators during project development and operational planning, regularly visit projects and sub projects and hold quarterly meetings with parish-based partner organisations.

# 1.0 INTRODUCTION

It is not easy to define “Development” just because it is a multi-dimensional process which involves a lot of economic and social systems, including customs and beliefs.  However, we can borrow a definition by Kotze D.A. (1997) when he defines it as “a positive social, economic and political change in a country or community”.  In other words, development is concerned with positive change in existing human societies and the success of development efforts is measured by the results seen in history.

Development work can be said to have started with the creation of the world.  As we read in the book of Genesis 1:1 – 31 we see God accomplished everything.  During the time of Jesus Christ our Lord we see a magnetic touching hand in trying to see that human beings enjoy life in full.  This is explicitly seen when Jesus healed the sick (Matt.  14/ 34-36); Jesus fed the hungry	(Matt 14/ 13-21). Since that time Christianity has spearheaded development in all sectors of human development all over the world.  We remember very well here in Africa with the arrival of missionaries they instituted three main key components in human development:- the introduction of alphabetical literacy; healing ministry through hospitals, and promotion of human dignity by condemning all forms of slavery.

In 1981 driven by the need and professional desire to stimulate more development a separate office for social services and development (SSD) was instituted in Masaka Diocese.  With support from international and national donors, the organization has initiated projects in the sectors of agriculture, animal husbandry, water and sanitation, medical care, environmental protection, care and the protection and support of orphans and widows. It was never assumed it would be easy going.  It was not until 1988 the name MADDO (Masaka Diocesan Development Organization) was born.  MADDO like a deep rooted tree that is firm and cannot be easily blown down by the wind it has up to this time stood firm to stand challenges.  In 2000 the name was changed to Caritas MADDO to promote the spirit of giving and receiving as related to love, compassion and solidarity.

Since that time – a period of 26 years now – Caritas MADDO has depended much on funding from Northern NGO’s in Europe and USA.

Caritas MADDO has accordingly supported infrastructure development of most of the diocesan projects and parishes in all sectors.

# 2.0 BACKGROUND: SOCIO-ECONOMIC CHARACTERISTICS

## 2.1 Country Profile

Uganda is a landlocked country in East Africa. Its borders are formed by Lake Victoria on the south and south east, Kenya on the east, Sudan in the north, the Democratic Republic of Congo and Rwanda to the west and Tanzania in the south. The estimated population number is 28.2  million with an average annual growth rate of 3.4% Despite strong economic growth, averaging around eight per cent per annum over the past decade, Uganda remains amongst the world’s twenty most poorest countries.

Almost all of Uganda’s social indicators remain below the average for sub-Saharan Africa.  Uganda’s population is largely characterized by low levels of literacy particularly among women (83% of men, and just 59% of women), high morbidity (28%), high maternal and infant/child mortality rates (505/100,000, 88/1000 and 69/1000 respectively), poor child nutritional status (39% stunting), poor access to health facilities (6 km on average) and poor quality of health services, low accessibility to safe water (15% of the population do not have access to safe water), and high/stagnating HIV infection rates (6.5% of the adult population), with high unemployment and underemployment leading to low income and poverty.

Uganda’s per capita income is US $330, which is far below the average for sub-Saharan African countries (US$470).  Uganda is ranked 141st out of 162 poorest countries on the UNDP Human Development Index.  Life expectancy has dropped to 43 years, down from 48 years in the mid-1980s.

## 2.2 Profile of the area Masaka Diocese covers

Masaka Diocese covers the southern part of Uganda on the shores of Lake Victoria a few degrees south of the Equator, covering five administrative districts, namely, Masaka, Rakai, Kalangala, Lyantonde and Ssembabule, comprising of 48 mainly rural Catholic parishes.

Masaka’s economy is heavily dependent on agriculture.  About 80% of the labour force is engaged in agriculture, many of whom are subsistence-level farmers.  Agricultural output comes almost exclusively from these smallholders, 80% of whom have less than two hectares of land each.  Most residents of Masaka owe their survival to the informal agricultural sector and most wage earners depend on their small plots for home food supplies.  Food crop production is by far the most important economic activity, accounting for 64% of agricultural GDP (including bananas, maize, beans, groundnuts, sweet potatoes and cassava) with livestock products accounting for another 19%.

Although Masaka’s agricultural sector is slowly growing, farm productivity and indeed income is still very low and vulnerable to drought, flooding, plant pests and diseases and changes in agricultural commodity prices.  The area’s main cash export commodities include coffee and fish.  Traditionally exclusive food crops are now produced both for domestic consumption, and cash.

## 2.3 Natural Environment

Masaka Diocese has an abundant natural resource base, though the quality of these resources is steadily declining under serious threat from degradation due to population pressure, over grazing, deforestation, siltation of water bodies, clearing and drying of wetlands, and poor agricultural practices including over-use of agrochemical.  These environmental problems are exacerbated by poverty, uncoordinated policies and poor enforcement of regulations.

Declining soil fertility and productivity of land, land degradation, depletion of fish species and stocks, wetlands encroachment and reclamation, and pollution of water sources all contribute significantly to increased economic vulnerability and poverty for the already poor populations, Environmental degradation imposes severe costs on the poor: their heavy dependence on environmental resources means they are highly vulnerable to sudden shocks and changes in their physical environment.  With a lack of alternative choices, poor people resort to further exploitation of natural resources for activities  such as firewood, brick making, charcoal burning, craft making, and stone quarrying.  Although these activities provide safety nets for the poor, they are environmentally unfriendly and unsustainable.  These activities fetch low returns, which mean that people have to repeatedly exploit the natural resources, which leads to depletion. Forests in Masaka Diocese are disappearing at a rate of 2% per year.

Although the government has in place a legislative framework and regulatory system for environmentally sound development and responsible use of natural resources, institutional weaknesses have undermined enforcement.  In addition, policies intended to eradicate poverty pay insufficient attention to poverty-environment linkages, and fail to promote the development of affordable and sustainable choices to the poor that would help reduce negative environmental practices.

## 2.4 Water Resources Availability: Demand and Usage

In the Diocese, rural households have an average of 7 to 10 people putting the daily demand to at least 50 litres of water per day. Accelerated demand will most likely occur with the increased farm activities putting the demand at 120 litres of water per household per day. The main source of water for the communities in the area is the few water bodies, swamps and natural springs and wells. In some of the drier areas of Rakai, Lyantonde and Ssembabule, many residents thrive on water collected in water dams and valley tanks which collect run off water during the rainy seasons and run dry towards the dry season.

Rakai, Lyantonde and Ssembabule are water stressed areas with an annual average rainfall of 916mm received in two rainy seasons separated by a three to four months dry season. Recent geological studies have shown that the Rakai, Lyantonde and Ssembabule area has a two aquifer system the top most being at a minimum depth of at least 45 to 75 metres. When one further drills in the overburden one encounters more fractured zones at 90 to 120 metres such aquifers have a satisfactory water potential.  Over the last 5 years Rakai, Lyantonde and Ssembabule have faced serious droughts which have led to the drying of the semi permanent sources making it hard for the communities to access water. Some of the individuals have to walk up to 2 to 3 kilometres to get water for domestic uses.

Water in the households is mainly used for Cooking, laundry and watering livestock. In most cases the quality and quantity of water determines the sanitation and the kind of development project a household can engage in.

## 2.5 HIV/AIDS

This scourge which started to manifest itself in this country in this area is still prevalent with adverse effects on human resources, national resources and household incomes.  An estimated 1 million Ugandans, mainly from the economically productive age groups, have died of AIDS since the beginning of the epidemic, another 1 million-plus are currently living with HIV/AIDS.  Food insecurity, degraded livelihoods, increased vulnerability and adverse socio-economic impacts have been identified in many instances as both factors and consequences of HIV/AIDS.  Some of the most significant social and economic consequences include:

- Reduced labour supply and productivity, especially amongst the most productive segment of the population, resulting in the loss of skilled labour and the agricultural knowledge base that is particularly critical in rural areas.

- High opportunity costs, including the loss time and money attending to the sick, poor job performance by those already infected, and the cost of burials.

- Increased dependency rations due to the large number of orphans left behind placing excessive burdens on remaining individuals (often the elderly) and on household economies.

- Loss of assets as household resources and land are liquidated to meet medical and other costs.

- Low investment in the agricultural sector as limited household resources are diverted to caring for the sick and for funeral expenses.

- Reduced market production due to loss of agricultural labour and lack of agricultural inputs.

## 2.6 The Dimensions of Poverty in Masaka

Despite Uganda’s considerable economic recovery over the past 17 years, there is still widespread poverty especially in the rural areas and, progress against poverty has been slow.

Poverty in this context is a lack of basic needs and services such as food, clothing, bedding, shelter, basic health care, education and communication, in addition to the lack of opportunities for survival and employment, and lack of productive assets such as land and farm tools

Poverty in Masaka Diocese is characterized by lack of skilled labour, limited land for cultivation, lack of production inputs, low literacy particularly amongst women.  Other manifestation of poverty include malnutrition, high morbidity and infant mortality, low household income, poor housing and poor general living conditions, few livelihood opportunities, social exclusion, and lack of access to information and to social and other public services.  Poor households are not able to deal with problems of poverty on their own because of structures and conditions within society and the economy.  In rural areas, poverty is particularly associated with lack of productive assets, locally known as ‘capital’

Ill health and disease are the most frequently cited causes of poverty in Uganda’s Participatory Poverty Assessment reports, but ill health and disease are also recognized as consequences of poverty.  Lack of access to quality health and education services, poor nutritional practices and limited nutritional choices, lack of information, lack of resources to take action, the impact of HIV/AIDS, and continuing high fertility and high population growth rates particularly in Masaka Diocese are all inter-dependent contributing factors in this cycle of poverty.

Limited access to land ranks second among the most frequently cited causes of poverty.  Amongst the poor and most vulnerable sectors of the population, land ownership is decreasing significantly as a result of problems linked to large families, evictions, internal migration, and gender inequities.  And where land is available, lack of access to markets, low market prices, the impact of pests and disease, and vulnerability to drought and other extreme climatic conditions are highlighted as key factors leading to poverty.

For women, the lack of control over productive resources remains one of the root causes of poverty.  Although women are responsible for the vast majority of agricultural production in Masaka Diocese, it is the male head of household who controls land ownership, the crops and livestock produced from women’s labour, and the financial gains from a market sales, and women often have little or no say in household decision-making.  This situation is even worse in widow/orphan headed households.  These households are often even more impoverished because in-laws take over the land and assets when a husband dies.

## 2.7 National Poverty Strategies

Rosy as the national statistics may paint the picture, the economic reforms programmes implemented by the Uganda government over the last twenty years have not had profound impact on the livelihoods of the majority of Ugandans.  The limited economic growth that has been achieved has largely contributed to filling gaps caused by years of chaos and economic decline.  Uganda’s revenue/GDP ratio of 11.3% is one of the lowest in the world, well below the sub-Saharan average of 18%.

Recognising these shortcomings, a new phase of economic reform was launched in 2000. The strategy, The Poverty Eradication and Alleviation Program (PEAP) provides an overall framework for development by promoting rapid economic growth and structural transformation to ensure good governance and security, to directly increase the ability of the poor to raise income, and to directly increase the quality of life of the poor.  This program fits snugly in the MDGs.

# 3.0 BACKGROUND: Reviewing the Past Five Years

## 3.1 Overview of Strategic Plan 2001-2006

The critical programme areas of the last five years included redefining MADDO as the implementing agency; Parishes as the intermediary agencies; Households as the target groups organised under sub-parishes. Hence programme and project designs and implementation were to take into account the three levels and necessary organisational and programme interventions with clearly defined easy to monitor indicators.

The Inter-Commission Planning and Coordinating Committee was planned to be instituted within the broadened mandate of the Diocesan Pastoral Executive Committee to strengthen linkages among commissions in order to streamline and professionalize Diocesan planning.

A Caritas MADDO Board of Directors was to be set up to provide policy and programme direction to organizational development and programming issues of MADDO as the supreme management and policy making organ of Caritas-MADDO.

In order to professionalize and strengthen management an Executive Management Committee (EMC) was planned to be instituted with the following technocrats; Diocesan Director, Director to strengthen institutional capacity to internalize and broadly define modern programme and management principles with a national and international outlook.

A competitive remuneration structure was proposed and a corresponding staff development strategy structure was strongly advised.

The Program was segmented into a crossed set of three thematic areas, which entails: -

i) Economic empowerment:

- Sustainable agriculture;

- Financial intermediation

- Entrepreneurial skills development and appropriate technology; and

- Small-scale enterprises development and institutional (focal-points) development.

(ii) Social Services

- Public heath and health institutions support;

- Community water supply and sanitation improvement services;

- HIV-AIDS interventions;

- Gender mainstreaming and family support

- Community welfare development

(iii) Advocacy and Networking

- Policy analysis and advocacy;

- Political participation and human rights;

- NGOs empowerment and networking;

- Publicity and information dissemination; and

- Transparency and Accountability monitoring.

iv) Support-Areas:

- Data generation; processing and dissemination;

- Transport and logistical support; and

- Pastoral orientation

The crosscutting thematic areas included evangelization and gender mainstreaming and the core programme area is poverty reduction within a national and international perspective. The theme of the last strategic period was “Caritas MADDO in a challenging World”

## 3.2 Critical Analysis of  The Masaka Synod V on Development

Every about 10 years, the Diocese of Masaka convenes a council of all stakeholders (the religious, the clergy, the laity and the youth) in the Diocese to review the previous period and chart the general framework for the next period.  During the last Synod which convened in August 2003, a number of issues were raised about development and the performance of Caritas MADDO that are pertinent to this strategic planning.

The Synod noted that Masaka Diocese strives hard to put in place development strategies not only for Catholics, but all people to enable them to enjoy good health, access all basic necessities in their day to day lives and to fulfil their obligations both to the church and state.

It was noted that this Southern Central part of Uganda that makes up Masaka Diocese used to be an economically vibrant area and was fast growing.  This area used to be the food basket of the country.  A big chunk of the national coffee production came from this area in the 1950s and 1960s.  Not anymore and the area has been overtaken by the western region as the food basket of Kampala.  The participants of the Synod attributed this scenario to the following factors:

- Ignorance

- A heavy disease burden especially HIV/AIDS

- Negative attitudes towards development especially among the young

- Lack of knowledge on the utilization of the available resources to create wealth

- Lack of planned development strategies

- An increasing dependency syndrome.  Many people are used to being given from donors

- Getting used to poor living conditions

- Lack of a saving culture

- Poor utilization of the scarce resources

- Poor or lack of markets for agro produce

- Lack of industrialization

- Lack/no modern machinery

- Rampant environmental degradation and rampant sale of natural resources and assets like land/forest

- Lack of entrepreneurial skills on the side of management of some diocesan projects

The Synod also noted that many training workshops have been provided and development projects started by Caritas MADDO; nonetheless these initiatives have not been as productive as expected.  The developmental support is not well distributed and the criteria for distribution is not clear.  Furthermore the impact of these widely spread projects is very minimal.

The synod made note of some outstanding bottlenecks to development.  These included:

- Failure to carry forward projects initiated by predecessors

- A lot of church land is not surveyed.  It could be lost

- How to carry on projects started in the wake of the ever-increasing donor fatigue

- Lack of seriousness in the way some projects are done

- Some global thinking that detracts some followers

- Environmental degradation in the area

- Big increases in the number of children needing help

- The current educational system overemphasizing academics at the expense of vocational education

### 3.2.1 Synod Suggestions

The synod made some suggestions towards more enhanced development.  Among them were:

- Looking for startup development capital from MFIs

- Instituting a forum for integrating staff and managers of all Commissions

- Always involving the local stakeholders when starting a project in any parish, and at all project levels planning, management, monitoring and evaluation

- Considering employing lay people to manage some  Diocesan Commissions and departments

- Putting projects  in the hands of competent people to run them properly

- Revamping cooperatives for development.  A special committee for this purpose should be established

- Putting emphasis on micro projects which the poor can sustain e.g. piggery, horticulture and micro businesses

- Making sure that the Diocese has a good policy of staff development in the different departments

- Making Masaka Social Centre a fully fledged hotel

- Every parish should have arrangements to generate income  and food (Parish Strategic Plans)

- Planting at least 1300 acres of tree in five years

- Closely monitoring inflows and outflows and provide reports to the Diocese through the right forums

- Urging all Christians to wake up and work for development to uplift their standards of living

## 3.3 Rapid Community Assessment

As part of the process of developing this strategic plan, Caritas MADDO utilised the services of an external resource person to carry out some rapid assessment of its performance in the beneficiaries at parish level.  Below are results of this assessment.

### 3.3.1 Community Perception of Caritas MADDO

The Rapid assessment found a considerably fair knowledge about Caritas MADDO in the community.  The organisation is generally known as the Masaka Diocese establishment that facilitates integrated human development.  Nevertheless the community perception of Caritas MADDO was not found to be uniform.  Some people’s perception of MADDO was found to be limited to the services they either have received themselves or have seen being done by the organisation.

The strongest community perceived presence of Caritas MADDO projects is the agricultural interventions followed by the promotion of good governance and human rights.  Caritas MADDO support of needy groups of widows and orphans in protection of their property rights and education and basic needs and protection of water sources and health education for HIV/AIDS were also mentioned by many

Caritas MADDO has, reportedly, led a revolution in the agricultural sector.  Farmers have benefited from modern farming methods training and now practice better methods of farming with the result that they now get better yields leading to increased food security and some income from their farms.

According to the community the Water and Sanitation sector is also Caritas MADDO’s star because there are very few NGOs dealing in this crucial issue in Masaka Diocese.    Another star is the promotion of participation in the democratization process through the good governance, making the community more politically literate. Caritas MADDO touches and benefits all people in the catchment area regardless of race, religion. This characteristic has made Caritas MADDO very popular and influential across the population

Furthermore the community avows that Caritas MADDO was quite spot-on to target the agro economy to alleviate poverty and strategies are fitting snugly not only in the PEAP goals, but also the MDGs.  They are dead right because agriculture in Masaka Diocese 80% of people directly live off the agro economy

Nevertheless the community contends that projects are many times started without proper needs assessment.  In addition, the criteria of distribution of inputs and identification of beneficiaries of the usually limited support is not clear.  The community also opined strongly that the organisation has eventually spread itself too thin…that impact is minimal.  Caritas MADDO virtually works in all the parishes in the Diocese…an area traversing 5 districts.  This has led to the fact that many times handouts are extremely insufficient. There is need to rethink the mode of implementation and reach more people with the same resources

Follow up monitoring is not sufficient and efficient, because it is centralised and charged on the same people who plan, implement and evaluate the projects.  It is not enough.

### 3.3.2 Community Suggestions (verbatim)

- Caritas MADDO should always plan with the beneficiaries before embarking on any project for best results

- More monitoring and follow up of interventions should be done

- The organisation should mobilise resources and inputs e.g. seeds and planting materials from nearby farmers.  Some planting materials from afar reach the farmers in very poor shape.  This could be achieved by grooming model farmers or mother gardens in the community

- Caritas MADDO should be elaborate in carrying out their work, instead of jumping here and there with few and insufficient projects.  Set priorities for the different areas e.g. piggery in Bukoto, brick making in Butende, carpentry in Kyamuliibwa, depending on the comparative advantage and identified need of  each area

- Provide microfinance to enable farmers to effect the knowledge acquired in the trainings

- Caritas MADDO should promote the culture of better utilisation of available resources through strategies like saving and prioritisation a little bit more among its beneficiaries

- Finally Caritas MADDO should sensitise the community about its work

The community were asked to mention and prioritise the needs they would have wanted Caritas MADDO to intervene in.  The priority needs and in order of priority were given as follows:

- Support of OVCs

- Support of Poverty reduction

- HIV/AIDS

- Water

- Provision of agricultural knowledge and inputs

- Access to marketing for agro products

- Control of other diseases

- Environmental Hygiene

## 3.4 Critical Analysis of the Health Function

To make the health services more accessible for the less privileged, most of the units have made an effort to reduce the user fees.  However Caritas MADDO’s efforts to maximize the use of available resources have not yielded results.

Most of the units have relatively good structures. It is only three units with structures below the minimum standards. Also most of the units have the basic equipments, however the following equipment are still needed: 7 microscopes, 19 solar power systems, 6 delivery beds, 142 Hospital beds, and 19 solar power systems. The overall quality of care has declined since 2004 due to decline in the number of qualified staff, lack of motivation on the side of the medical staff, and due to lack of the necessary equipments.

Quite a number of Units could attract the nearby sister institutions to improve on access, staff productivity and sustainability. It is unfortunate to find that some of the nearby sister institutions are seeking services from private practitioners allegedly looking for better terms, when at times the service provided at these units  is more expensive and of less quality as compared to that in diocesan units.

Masaka Diocesan Units need to tap opportunities that accrue from getting integrated into the public sector health service delivery systems. Many Diocesan Health Units would benefit from the support supervision carried out by local government officials to improve.

At the top of the Health Services of the Diocese is a board. The diocesan Health board is composed of able men and women specialised in a wide range of disciplines with vast experience. This Board was duly instituted through newly adapted and adopted policy documents, that is, the Diocesan manual of employment and the constitution for the Diocesan Health Office.

## 3.5 General Implementation Gaps in the SP (2001-06)

Some of the strategies and activities planned for in 2001-2006 could not take place. These were examined and the reasons that led to their non-implementation identified.  Due to funding gaps some policies and systems were not established.

Generally parishes were not taken up as intermediary agencies.  The organisation has maintained the direct implementation approach

Some programs identified as crucial in the last strategic plan were not prominently taken care of.  These include economic empowerment through Financial intermediation, Policy analysis and advocacy; CBOs empowerment and networking; Publicity and information dissemination; and

# 4.0 ANALYSIS OF ORGANIZATIONAL ISSUES

The strategic planning process further analysed Caritas MADDO with a purpose of finding out the strengths, challenges and gaps (diseases) that need “therapy”.

Caritas MADDO has a strong historical background, as pioneer of development for the rural poor in Southern Central Uganda, which makes it credible at, local, national and international levels.  It has access to information about external environment and strong links with different actors in the external environment.  Its programs are compliant with PEAP, MDGs and NEPAD goals

Caritas MADDO’s Core Competences:

- Technical skills enhancement in agriculture development and for food security.

- Infrastructural development for safe and clean water and hygienic environments

- Strategic planning, programme reviews, developing monitoring and evaluation systems.

- Supporting group dynamic and growth and leadership capacity development.

Caritas MADDO also has a strong asset base and its strategic model supports the various projects

The management and policy making organ (the board) is in place but without a governing document informing it of its functions and roles, it is certainly not a well-constituted management organ to initiate and review policies and policy execution.

The mechanisms to work with lower level church structures i.e. Deaneries, Parishes and sub parishes are clearly well-defined in the synod booklet and the last strategic plan but are not fully utilised in the project cycle. Lower level structure have largely been used for mobilisation.

There is a structural mismatch between the organizational capacities and service-delivery demands.  The Diocese is so big with a skeleton coordinating office and support staff.  There has been no realistic relationship and appraisal of organizational capacities vis-avis programme development.  The organization is donor-project driven not built on internal capacity development arrangements.  The skills base and staff-size are inadequate to cope with organizational- corporate development demands. This mode of operation is therefore dysfunctional and weak.  This phenomenon is not news to Caritas MADDO.  It was observed during the strategic planning in 2001, but nothing was done to address it.

Caritas MADDO has a relatively well-trained work force and has instituted recruitment systems and training programmes. Compared to other Diocesan Commissions it has a better remuneration structure and terms and conditions of service.  It has a relatively strong management team with realistic planning and implementation processes. This team has contributed to the growth and programme expansion of MADDO. There are basic skills in agriculture management, development work, social services, health, water and sanitation.

Nevertheless, in the absence of a HRM/D policy, and a fully fledged HR manager there is lack of adequate and effective job-selection criteria, manpower development strategies, and job-evaluation and appraisal systems. Whereas there is a procedure for recruitment it appears that there is no indexing of selection criteria indicating job-specification, qualifications, expertise, age and professional experience.  The officer in-charge of personnel could be better utilized in other areas (Water and Sanitation) where he is more relevant and qualified.   There is no consistent staff development policy.  Therefore the capacity building needs of the staff are not regularly identified, planned and/or budgeted for as a basis for developing an efficient work force.  There does not seem procedure for job-description reviews.  Outputs for tasks are not stipulated and there are no performance indicators set against which performance can be evaluated. The systems for promotion, dispute and discipline settlement and contract terms are a disincentive to job-stability and motivation.  There do not seem to be mechanisms for grievance expression and constructive criticism.  There are limited opportunities to build up possibilities, for horizontal and vertical mobility.

Mechanisms for staff performance measurement and assessment are weak.  This is further weakened by the poor remuneration mechanisms and centralization of authority.  The staff remuneration is so poor relative to pay-rates in the NGO sector whereby in most cases it is less than 30% of comparative rates elsewhere

All the projects under MADDO have had some kind of external evaluations, which has strengthened the programming processes and organizational capacities. External reporting and accountability is efficient and tracking of resources is well balanced.

Sufficient infrastructure development for office facilities is in place. The organization has a relatively efficient transport system with enough vehicles for the current programmes and running computers and communication equipment.

The vital function of Caritas MADDO in coordinating all diocesan programmes since it is the core manager of external –funding is not well developed.  It’s planning and coordinating functions for all donor-funded projects have not been fully developed except with respect to recommending projects and accounting to donor.  Some sectors are so much decentralized to the extent that there is no supervisory, planning and reporting linkage like in case of hospitals and health-centres, and projects managed by religious organizations. There is need to re-define these functions with respect to corporate development, programming efficiency and coordination of programmes.

# 5.0 The Current State of the CBO Sector at Grassroots Level

There is a multitude of Community Based Organisations (CBOs) in the Diocese including privately initiated ones, faith-based associations, community associations and other interest groups.  Nevertheless their capacity to co-deliver services with Caritas MADDO is quite limited.  Many of them only go as far as providing relief services to their members during emergency and unexpected occurrences like funerals. The springing up of CBOs has been contributed to by the liberalization policy, which encourages the private or informal sector to take up more roles and support government in development process.

Many of the Diocesan parishes and associated CBOs however are confronted with a number of problems that constrain them from playing steadfast roles of promoting development to effectively contribute to poverty reduction.  They are characterized by:

- Insufficient leadership and managerial skills and systems required to operate.

- Insufficient understanding of operating principles and guidelines.

- Unclear tasks, roles position in the society, limited coverage and variable quality of work resulting into difficulties for CBOs to develop their identity.

- Unclear policies, systems and procedures

- Many do not have impact on society; do not have local support base or clear constituency.

- Inadequate technical and functional skills required in executing development programmes

- Internal relations are bureaucratic, not creative.

- Weak sustainability strategy

However there are some nascent ones that can be groomed to co-implement activities with Caritas MADDO

# 6.0 Summary of Key Issues relevant to the New Strategic Plan

In light of the above analysis Caritas MADDO is still relevant in a changing environment.  However the environment has changed considerably from what it was at the time of formulation of the last Strategic Plan in 2001. It has brought forth fresh local and global challenges that impact on the issues that Caritas MADDO is trying to address thus necessitating the organisation to engage differently.  The organisation had to undergo a deep reflection and analysis of its purpose, mandate and procedures.

There is need to correct existing management anomalies by strengthening the policy making body of the organisation. The board, through strategies like formation of board sub-committees to support the staff in the planning and budgeting of organization programs.

In an attempt to cover the whole diocese as widely as possible, without growing commensurately in terms of capacity, Caritas MADDO has spread itself too thin to have any meaningful impact.  It is therefore pertinent to redefine Caritas MADDO’s coverage and consider decentralization of some aspects. The operational area of Caritas MADDO needs to be reviewed, as the organization had stayed “long” in some areas; and seems to be doing more in some parishes than others. The criteria of this coverage is not clear. Caritas MADDO should carry out organizational mapping to identify which organization is where and doing what to avoid duplication of efforts and competition yet trying to achieve similar goals and objectives.

At the grassroots, many other development-focused initiatives have emerged over the years. In fact some parishes are already receiving their foreign financial aid through Caritas MADDO.  This is a positive development, and a window of opportunity. Caritas MADDO should position itself as a facilitator and mentor and not a competitor to such initiatives.

All organisation systems and policies should be reviewed and updated to be in line with the contemporary NGO, national and local government legal framework.  This especially pertains to- human resource management and development; systems of finance, networking, guidelines on beneficiary recruitment , monitoring and evaluation, phase out and phasing in, fundraising,  communication and impact assessment among others.

Further still there is need for development of a staff capacity enhancement plan – In-house, External training/courses, attachments for exposure and experience sharing. The plan should be based on the current and the core/immediate needs of the organization especially based on the organization’s strategic plan and planned human resources audit.

All Caritas MADDO focal areas and programs should include cross cutting areas of HIV/AIDS, environment

# 7.0 THE NEW STRATEGIC DIRECTION (2007-2011)

In order to work towards better livelihoods for men and women in Diocese, the Caritas MADDO program contributes to the PEAP Pillar Two by working to improve agricultural production at household level.  It also contributes to PEAP Pillar 4 by strengthening democracy promoting corrupt free leadership and human rights.  Furthermore, the program contributes to PEAP Pillar 5 by provision of healthcare, increasing access to safe water, investing in children’s education to increase their skills and options to give them an opportunity to lead a better life.

This program contributes to the MDGs too, especially to reduce extreme poverty and hunger

## 7.1 Vision

To see the people of Masaka Diocese attain holistic development

## 7.2 Mission

To stimulate and directing sustainable development among the people of Masaka Diocese regardless of their religious affiliation.

## 7.3 Organisational Values

In the next five years, Caritas MADDO’s will be guided by the following values:

- Transparency efficacy and cost efficiency

- Enhancing people’s capacities

- Belief in mutual co-existence with all humankind

- Synergising, respecting each other’s contribution, realizing and appreciating that we need each other

- Equal opportunity to all

## 7.4 Goal

Improved Standards of living for the people living in Masaka Diocese

## 7.5 Objectives

This Caritas MADDO Strategic Plan will focus on the following major focal areas: (these encompass running programs and planned strategies to address emerging issues)

- Food security, increased incomes through sustainable agribusiness

- Gender Mainstreaming

- HIV/AIDS Mainstreaming

- Organisational Strengthening and Institutional Development

- Preventive and curative health for development

- Human Rights and Good Governance Strategies

- Promote the value of working together to assist the needy in our communities

### 7.5.1 Focal Area: Food Security, Increasing Incomes through Sustainable Agribusiness

Objective 1: 	Increase the capacity of poor resource beneficiary households to effectively practice sustainable agro-economic activities

Objective 2:	 Increase food security and environmental conservation practices at household level

Support will be provided to organised farmers organizations/associations to have the capacity to effectively provide services to individual farming households in their areas of operations to access agricultural inputs, to improve their farming practices, increase their agricultural based income, taking into considerations different and complimentary roles of male and female farmers in order to ensure food security and increased income.

Emphasis will be in the following areas:

#### 7.8.1.1 Agricultural Extension

- Support of participatory extension approaches with an important role of farmer organizations as intermediaries

- Search for new partnerships between government extension system and CBOs/NGOs as well as farmer organizations On farmer to farmer learning and exchange

- On improved access to extension systems based on cost sharing and revised roles of extension agents and farmers

- Revitalise traditional crops, in addition to new crops

- Collaboration with research institutes

#### 7.8.1.2 Input Supply

- Support of farmer controlled input supply schemes

- On increased access to resource-by poor farmers to improved seeds and basic tools

- On sustainability of input-supply schemes through improved management and accountability

#### 7.8.1.3 Agricultural Marketing

- Support of farmer controlled collective marketing schemes

- On improved harvest and post harvest handling of produce

- Promotion of small scale agro processing and value addition to produce

- On research, collection and dissemination of market information to farmers

- Support the farmers acquisition of agribusiness skills

- Facilitate farmers linkage to national, regional and international markets and better negotiations with traders

- Advocating for improvement in market infrastructures and favourable prices for farmers produce

- On changing economic power relationships between farmers and traders

- On retaining food stocks for food security at household level

- On women’s involvement in decision making and income benefits

- Collaboration with research institutes

#### 7.8.1.4 Rural Savings and Credit

- Support rural savings mobilization through sensitisation and supporting the opening of savings accounts

- Support and encourage specialized financial intermediaries to provide appropriate credit to resource poor but developmental beneficiaries particularly households where the women team up strongly with men.

#### 7.8.1.5 Appropriate Technology

- Support of appropriate technology development and dissemination in agricultural production and post harvest activities and agro-processing

- On low-cost labour saving technologies

- On added value technologies for agricultural produce

#### 7.8.1.6 Natural Resources Management

- On sustainable intensification of cropping systems through improved soil protection and fertility management practices

- Support of improved environmental management and protection practices through promotion of alternative income generating activities and sustainable land-use methods e.g. afforestation, energy saving cooking systems

- Participatory Implementation Monitoring

- Collaboration with research institutes

7.5.2 Focal Area: Gender Mainstreaming

Objective 3: 	Caritas MADDO and partner parish programs are gender responsive

The capacity of Caritas MADDO and partners at parish level will be continuously strengthened to ensure that gender is mainstreamed in Caritas MADDO and participating organisations policies and programs

7.5.3 Focal Area: HIV/AIDS Mainstreaming

Objective 4: 	Caritas MADDO and partners programs and strategies HIV/AIDS responsive

Mainstreaming HIV/AIDS is hoped to reduce the vulnerability of people at risk or affected and it enables care, treatment and support of those affected by HIV/AIDS.  Mainstreaming will take a multi-sectoral approach; at the work place, within the organization, programmes and collaboration with AIDS service organizations.  This will improve the ability of the organization and staff to anticipate, minimize and cope with illness and death associated with the pandemic.

Caritas MADDO HIV/AIDS intervention will focus on two strategic areas: creating and maintaining awareness and mitigation.  The core strategy will emphasize:

- Staff and community awareness (regular updates on HIV/AIDS trends and implications);

- Caritas MADDO will empower both staff and community with HIV/AIDS related information and support in order to reduce vulnerability.

- Adequate budgeting and planning for HIV/AIDS intervention over long periods;

- Consideration of long-term implication on human resources.

- Development of a staff health policy (promoting HIV/AIDS education – prevention, care, confidentiality) and medical insurance scheme;

- Anticipation of employee absenteeism, illness death, staff turnover, recruitment costs and time and demands on employee’s  benefits

Establish collaboration with AIDS service organizations to provide information and other therapy (involving prevention, care and treatment).

7.5.4 Focal Area: Organizational Strengthening and Institutional Development

Objective 5: 	Caritas MADDO and participating parishes have sustainable requisite organisational capacity to carry out activities

### Caritas MADDO Level

#### Management

The board, which is the policy making body will be strengthened by clearly documenting its role (more than the outline in the Synod booklet) and mainstreaming the management of the various health services and functions. Management sub-committees will be revitalised to support the management in the fundraising, budgeting and planning of organization programs. The Synod V provides for 6 management committees as follows:

- Social and Economic Development Committee

- Cooperative Committee

- Health Management Committee

- Social Welfare Committee

- Transport Committee

- Projects Committee

The Synod is however silent on the functions of these committees.  The functions of each of these board sub-committees will be laid down in the cardinal organisation document to be prepared

#### Policies and Systems

All organisation documents and policies will be reviewed and updated to be in line with the contemporary NGO, national and local government legal framework.  This especially pertains to- human resource management and development (recruitment, staff induction, appraisal, knowledge and skills development, remuneration, other benefits, etc). All job descriptions and key result areas for all staff will be reviewed; and an organization skills and knowledge audit carried out to identify who suits where among the current team.

Other relevant management policies and systems e.g. partnership, finance, networking, monitoring and evaluation, fundraising, communication etc. will be put in place in this strategic period

#### Human Resources

The implementation of this strategic plan can only be realized through a motivated and capable staff who share the vision of Caritas MADDO.  Caritas MADDO has a team of qualified and experienced professional.  The team has been completely built to facilitate technical, organization/institutional learning and development and to effectively mobilize, network with Civil Society organizations and other actors to engage in development work.  The present staff will be the core resource persons in the implementation of this strategic plan.  Occasionally however, input will be drawn from external resource persons especially in specialties where in house skills are limited.

Nevertheless Caritas MADDO is a learning organization that evolves in a quickly changing environment.  In this regard, the organisation will ensure that its personnel get the opportunity to develop along with the organization.  Opportunities for training will be offered.  And the personnel policy will, as much as possible, take into account the possibilities for personal growth and development inside the organization.  Caritas MADDO will continuously adjust its human resource needs and strengthen its capacity to be able to implement the programme and adjust its roles and strategies.

#### Equipment:

Caritas MADDO will not have heavy investments in equipments required for implementation.  Currently Caritas MADDO has ample pool of programme vehicles, computers, photocopiers, internet e-mail connection and fax as basic facilities for effective programme implementation.  This equipments will eventually though need replacement due to wear and tear and gradually they will have to be replaced and new ones added especially as the programme expands.

### OSID: Community Based Organisations at Parish level

Caritas MADDO will facilitate nascent Community Based Organisations/Initiatives at parish level to improve their organizational effectiveness to provide relevant, gender responsive and quality services to other members of the community through an integrated, group centred approach, which addresses the identified issues in a systemic and sustainable way.  This will be by:

- Strengthening the strategic and operational capacities at parish and  CBOs and promote better understanding of organizational change processes for improved operational performance in terms of clear managerial aims, governance by rules, norms and collective values.

- Organizational support to strengthen the internal organization, managerial skills in administration, financial management as well alternative financing and strategic planning capacity through facilitation of organizational analysis and training of professionals and decision-makers;

- Increasing the means and prospects of individuals, groups and organizations for better quality of their service delivery and clear impacts at grassroots level.

- Facilitating structural change of institutions in order for them to adapt to the changing development context and become sustainable.

- Promotion of equal participation in development by men and women.

- Enhancing capacity of parishes and associated CBOs to meaningfully participate in development work.

- Punctual methodological support to parishes and associated CBOs to start relationships with organizations with the potential to develop into effective partnerships.

- Orient beneficiaries and CBOs towards savings and credit

#### Financial support to Community Based Initiatives:

Caritas MADDO will remit financial and in-kind resources to support activities in which parishes have comparative advantages for impact.  Partnerships for specified periods will be working relationship with Caritas MADDO.

Funding of personnel expenses and other institutional costs will require prior discussions with parish leaders to discuss strategies to reduce external financial dependency and to elaborate internal financing of personnel and overhead costs.

For programs involving micro-credit, funds for credit programmes in the form of revolving credit funds will not be provided directly to parishes.  Instead, Caritas MADDO will assist in linking CBOs with specialized credit institutions.

7.5.5 Focal Area: Preventive and Curative Health for Development

Objective 6:  	Contribute to the well being of the people through increased access to health services both curative and preventive

Objective 7: 	To increase access to sustainable safe water and sanitation facilities rural poor communities

Under the Health program, Caritas MADDO will improve the functioning of the Diocesan Health Services through, sustainability, better range and quality of services; improved governance, management, and accountability structures; the capacity of the frontline service providers will be continuously assessed and remedial action taken

The Diocese will improve net working within the diocesan health institutions as well as improve data and information management and research.

In order to increase access to sustainable safe water and sanitation facilities rural poor communities regardless of religious affiliations, Caritas MADDO will continue to improve the skills of beneficiary communities to manage protected public water point sources in their areas. Communities will be supported to access nearby protected water point sources; to adopt the right hygiene and sanitation behaviour coupled with acquiring sanitary latrine facilities in all homes. Caritas MADDO will establish and train community based institutions which are able to operate and maintain water supply and sanitation facilities in a sustainable way, especially through collecting rainwater to run throughout the dry days.

7.5.6 Human Rights and Good Governance Strategies

Objective 8: 	To unchain widows and orphans from exploitation and discrimination

Objective 9: 	To promote good governance and leadership that addresses gender concerns

Caritas MADDO will promote good governance and leadership through democracy monitoring from a gender perspective; promoting effective peoples engagement in multi-party politics and increasing women’s participation in politics, strategic leadership and decision-making

The organisation will also endeavour to unchain widows and orphans from exploitation and discrimination, Caritas MADDO intends to protect and prevent violation of widows’ rights and discrimination against widows and girl children.  Marginalised groups will continue to be provided with opportunities to take control of their lives, and live meaningful livelihoods.

7.5.7 Promote the value of working together to assist the needy in our communities

Objective 10: 	Increased access to social services and welfare for disadvantaged and vulnerable groups

The organisation will continue to mobilise people to help one another and not always look for aid externally.  Caritas MADDO will continue to collect and coordinate aid for the poor, the needy and orphans. Caritas MADDO will also organise the Annual Caritas Day in Masaka Diocese, on which a major part of the local contribution is raised.

It will also be a major strategy to study and analyse the problems of vulnerable population groups like street children and prostitutes and devise strategies to support them out of their destituteness. The organisation will liaise with the education commission to support needy orphans’ access education.

Under this component, Caritas MADDO will spearhead the Diocese’s preparedness for disasters.

## 7.6 Target Population

The target groups will continue to be resource poor people in the Diocese.  These are beneficiaries with limited access to resources such as capital, land, and other services such as credit, extension, input-supply and marketing.

## 7.7 Other Components

Caritas MADDO will continue to provide the people of Masaka and beyond with prime but affordable conference facilities in Masaka Social Center.  This facility will be operated as any other commercial hotel in Masaka town and contribute to the sustainability of the organisation

# 8.0 Monitoring and Evaluation:

Caritas MADDO has employed the Logical Framework model in formulating projects out of this strategic plan. This will streamline the monitoring and evaluation as all the main components of the program have been presented in a logical way. Monitoring will be a process activity and will take the following forms:

- All project outputs will be continuously monitored. Comprehensive but user friendly tools will be developed for that purpose. Relevant records of quantitative and qualitative data concerning activities of the various programs will be kept

- Regular Field visits by Caritas MADDO programme staff to ensure that planned activities are taking place, monitor the institutional changes agreed upon and that resources are utilized for the intended purpose.

- Quarterly meetings between Caritas MADDO and parish partners to review the progress of work against work plans and programme purpose.  These meetings will examine completed/uncompleted activities, outcomes and cost-effectiveness on an ongoing basis.  It is on the basis of these meetings that new interventions may be designed.

- Review workshops will be held once a year with each Community Based Organisation to measure progress towards the achievement of the agreed results.  Participatory techniques (timelines, flowcharts, and self-assessment) will be used in this exercise.

- Quarterly and annual reports; narrative and financial reports will be produced by partners and will be analyzed/ discussed with Caritas MADDO.

Both Caritas MADDO and parish partners will give due considerations for drawing lessons and experiences for institutional learning and programme improvement. For this, participatory evaluation exercises will be conducted after five years for parish partners and Caritas MADDO.

# 9.0 Financing

Currently Caritas MADDO’s budget is 78% donor financed and only 22% locally funded.  It is noted that for quite a long time to date Caritas MADDO has been funded greatly by foreign grants. That funding has never been constant; they fluctuate year after year as it is indicated below. Local contribution has always been far below 50%.

#### 9.1 Donor Funding As A Fraction Of Caritas MADDO Budget For 5 Years – Flash Back

- 2001/2002	57.9.3%

- 2002/2003	65.20%

- 2003/2004	72.50%

- 2004/2005	60.72%

- 2005/2006	78.26%

The strategies contained herein will also be financed from the same sources but progressively the organization will work towards increasing the local contribution by utilizing locally available resources and cutting down on handouts and increasing on cost sharing.  Where and when possible, contributions towards the cost of services will be carefully established and maintained Caritas MADDO will fully explore the possibility of user fee, however small. One option is to institute a stratified service.  Something that able beneficiaries are encouraged to pay for and those who cant do not.  The proceeds will be reploughed into the program or other projects. Nevertheless income-generating activities are strengthened and new ones like MADDO Diaries are being established. Income-generating activities are strengthened and new ones like MADDO Diaries are being established.

# 10.0 Sustainability Issues

The organisation is going to embark on new sustainability strategy of grooming viable Parish- Based Institutions to co-implement the projects on behalf of MADDO.  Caritas MADDO will progressively  work closely with each parishes for a considerable period of time preferably five years but certainly not exceeding ten years, unless under exceptional circumstances.  Collaboration with some parishes may be for shorter periods on specific activities.

For each Parish, the date for disengagement of support shall will be discussed, determined and explicitly stated from the beginning. It will also be continuously discussed at every stage of the programme cycle, particularly during monitoring and evaluation.  However, Caritas MADDO will facilitate the partners to generate resources and access support from other development agencies.

No project will be complete without a comprehensive sustainability strategy. Furthermore, In order to propagate community ownership, all projects will be conceived in a participatory manner.  Caritas MADDO will attentively and actively listen to the beneficiaries at all project levels: planning, management, monitoring and evaluation.  All projects will be need-based rather than demand based.  Program priorities will always be identified by communities.  In order to increase ownership and build capacity, the approach used by MADDO will be to facilitate rather than directly implementing project activities. A critical element in any community program is the community structure.   Volunteers will always be identified by the parishes

Caritas MADDO has developed capacity over many years. The organization already has some resources that can bring in some income.  These include commercial trucks, a warehouse, and the Masaka Social Center. The proceeds of these resources will be re-ploughed into developmental projects.  Plans will be made to sell its expertise to other programs in form of training, planning, monitoring and evaluation.  Also, in the community, Caritas MADDO will always avoid to start things that the community might find difficult to continue.  For instance the organization will always find it more easier to utilize less sophisticated and less expensive technologies, materials and logistics.

# Annex1:  Organizational Chart for Caritas MADDO:

### Annex 1.1 Policy Making Organ

The supreme authority of Caritas MADDO is vested in the Board of Directors, which is the policy making body. The board will provide policy and programme direction to the organization on behalf of the appointing authority. The board may establish sub committees from among its membership, and where need be co-opted members as well as task forces to handle special assignments on its behalf. The Synod V provides for 6 committees as follows: Social and Economic Development Committee; Cooperative Committee; Health Management Committee; Social Welfare Committee; Transport Committee and Projects Committee

### Annex 1.2 Senior Management: Administration

The Day to day administration of Caritas MADDO will be the charge of the Development Coordinator as the Chief Executive Officer. The Development Coordinator will provide technical, moral, pastoral guidance in addition to exemplary leadership to all members of staff. This responsibility will also cover putting in place and maintaining a well-motivated staff.

The Coordinator will be responsible for designing medium strategies for the organization operations, taking into account of the changing socio-economic environment in the Diocese and country and then facilitate program re-formulation if need be; technical back stopping and on-going monitoring and evaluation of  operations

The Coordinator will also perform secretarial duties for the board, prepare technical papers and reports and call for all scheduled and impromptu meetings as required.

The Coordinator will ensure constructive collaboration and synergies are established with relevant stakeholders. The Coordinator will ensure that deadlines with stakeholders, especially donors are always met and resources are utilized for what they were planned for and cost effectively. The Coordinator will be the fulcrum of all external communications to and from Caritas MADDO. He is the spokesperson of the organization.

The Assistant Coordinator and the Management Team (MT) will support the Coordinator in these functions. The MT will be constituted by all Program Officers, Manager Social Center, the Development Coordinator, Assistant Development Coordinator, the Senior Program Officer and the Senior Internal Auditor.  The deliberations of MT will inform middle level managers, senior administration and even the board.  Each Program Officer will produce and present a brief monthly report about his/her own program to the MT.  The report will entail planned activities, achievements, challenges, strategies to overcome them and plans for the new month.

### Anne 1.3 Middle Level Management: Technical

The technical officers (Program Officers) will be the frontline managers as per program.  Program Officers will be the Chief Executives of each given program. The POs will be responsible for programming, formulating proposals, work plans and budgets; overseeing the implementation of work under each program.  Although the organization will continue to work in an integrated manner, all projects and project components of for example HIV/AIDS will be the charge of the PO/Health.

Each PO will have an assistant.  It is not necessary to hire new faces.  The assistant may be identified among the existing staff.  It is important that the PO is involved in identifying his/her assistant.

The Senior Program Officer will be responsible for overall coordination of the program, manage personnel issues, ensure adequate monitoring and compliance to plans, ensure that deadlines are met and resources are expended in accordance with work plans and budgets, and documentation i.e. reports are made on time, integrated and disseminated to the relevant stakeholders. The SPO will also ensure that the crosscutting issues of HIV/AIDS and gender are mainstreamed.

The new proposed structure of PO-Organizational Development will be responsible all Institutional Development both at Caritas MADDO and partner CBO levels. Specifically the POOD will;

- In collaboration with the board, oversee the development of missing policies and organizational documents, e.g. constitution, partnership policy etc...

- Identify gaps for organizational strengthening within Caritas MADDO

- Identify CBOs for partnering with Caritas MADDO

- Assess the capacities of CBOs in all aspects before partnership.  This will focus on the CBOs working knowledge of the communities that Caritas MADDO is targeting.  This will be intended just to understand the potential partner CBOs from the beginning.  If there are pertinent issues it is intended to tackle them at the early stage.  The findings of all assessments will be presented and discussed with CBO managers

- Develop capacity building programs of both the identified CBOs, and Caritas MADDO depending on the gaps identified

- Monitor the institutional development of selected partner CBOs

### Annex 1.4 Senior Internal Auditor

This structure will support the work of the senior management administration and the board to examine and analyse all transactions, documents and reports and relay independent findings to the relevant management level. The auditor may make inspections at any time and submit unsolicited reports to whatever level, as he deems necessary at any time without risking to be accused of not observing protocol.

### Annex 1.5 Community

Each program will reach the beneficiaries through the Diocesan Parishes

# Annex 2: The Logical Framework (2007-2011)

#### Ensuring Food Security, Increasing Incomes through Sustainable Agribusiness

| Objective 1 | Indicator | Means of verifications | Assumption |
| --- | --- | --- | --- |
| Increase the capacity of poor resource beneficiary households to effectively practice sustainable agro-economic activities | 70% of farmers trained in sustainable agriculture are practicing farming that is characterised by minimum use of off farm inputs, recycling of products and no crop stunting. 70% of farmers trained in sustainable agriculture are practising soil and water conservation using mulching, trenching crop rotation at the minimum. | Annual program reviews | Favourable weather conditions prevail Incentives for production using sustainable agricultural practices prevail |
| Output 1.1 | Indicator | Means of verifications | Assumption |
| Knowledge and skills of farmers households in sustainable agriculture strengthened | At least 90% of trained farmers have gained knowledge and skills in sustainable agriculture | Annual program reviews Evaluation Reports | Female members will be able to participate effectively in all training increased security of land tenure |
| Activities | Timing | Expected Results | MOV |
| Carry out training needs assessment on sustainable agriculture | 2007, 2009 | Training needs of each parish is documented. | Reports of needs assessment |
| Update existing training materials and develop new ones | 2007, 2009 | Training manual for sustainable agriculture for developed | Training manual |
| Conduct a training of trainers (TOT) for farmers in sustainable agriculture | 2007-2011 | 5 TOT per partner parish | Training report |
| Train farmers in sustainable agricultural practices. | 2007 -2011 | At 100 farmers trained per parish | Training reports |
| Establishment of Demo. farms | 2007 -2011 | At least one demonstration established per parish | Demonstration farms |
| Conduct refresher courses for farmers’ TOTs on new technologies | 2008 -2011 | 5 TOT per partner parish | Training reports |
| Collect and disseminate information on sustainable agriculture practices to partner | 2007 0nwards | Information collected and disseminated annually | Documented info available with farmers |
| Establishment of resource centres at parish level | 2009 -2011 | At least each partner parish has a resource centre | Resource centres in use |
| Train farmers groups leaderships in information management | 2008 and 2010 | 5 TOT per partner parish | Training reports |
| Facilitate study tours/exchange visits for farmers | 2007-2011 | Participating farmers go for at least 1 study tour/exchange visit to research institutions or agricultural shows per parish | Study tour reports |
| Provide technical backup and monitor | 2007-2011 | At least 2 visits per parish a year | Monitoring reports |
| Output 1.2 | Indicator | Means of verifications | Assumption |
| Participating farmers in the parishes actively involved in development and distribution of planting material | 50% of trained farmers practise new agricultural technologies (tools and planting materials) | Annual program reviews | Researchers will be willing to involve our farmers in technology development |
| Activities | Timing | Expected Results | MOV |
| Make an inventory of agricultural technologies available in Uganda appropriate in this region | 2007 -2011 | An inventory of technologies made by 2008 and updated every year | Updated inventory of agricultural technologies |
| Translate inventory into local languages and disseminate to participating parishes | 2007-2011 | Inventories translated into Luganda and Lunyankole | Popularised version of the inventories |
| Train TOT in Participatory Technology Development | 2007 -2011 | 5 Tots per parish | PTD training reports |
| Train farmers organisations in PTD | 2007 -2011 | 5 groups per parish | Annual program reviews |
| Facilitate participating farmers to access and evaluate technologies according to need | 2007 -2011 | At least one technology identified and evaluated per parish per year | Annual program reviews |
| Facilitate collaborating parishes to disseminate technologies through demonstrations (green and dry shows) | 2007 -2011 | At least 1 show (green or dry) per parish per year | Annual program reviews |
| Facilitate farmers to multiply technology according to need | 2007 -2011 | At least 2 new technologies multiplied per parish per year | Activity reports Monitoring and evaluation reports |
| Monitor the performance of PTD | 2007 -2011 | The performance of the PTD program monitored every year | Annual program reviews |
| Document and share experiences about PTD within Caritas MADDO and with other stakeholders | 2007 -2011 | Journal of experiences in PTD shared amongst stakeholders annually | Documented information on PTD developed |
| Output 1.3 | Indicator | Means of verifications | Assumption |
| Increased information sharing between researchers TOTs, farmers and the agri-business sector | At least 90% of the participating parishes have strong collaboration with research extension providers | Annual program reviews | Stakeholders effectively collaborate and provide information |
| Activities | Timing | Expected Results | MOV |
| Establish linkages with agric. research institutions | 2007 -2011 | Collaboration established with DATIC | Meeting minute and reports of collaborative activities |
| Identify progressive parishes to collaborate in the implementation of research extension linkages | 2007 -2011 | At least 5 parishes (one per district) identified for collaboration | List of parishes |
| Facilitate parishes to mobilize farmers groups to participate in research extension | From 2007-2009 | Parishes mobilise on average at least 5 farmer groups and 3 agribusiness entrepreneurs | List of groups |
| Sensitise participating parish farmer groups | 2007 and 2008 | At least one workshop on agricultural systems held each year per parish | Workshop reports |
| Facilitate farmers to learn the importance of research extension through study tours to research stations, agricultural shows | 2007 -2011 | 15 members of the participating parish farmers groups | Reports of study tours |
| Facilitate information exchange among farmers through farmer to farmer visit | 2007 -2011 | All participating parish farmers have shared information through at least one exchange visit to other innovative farmers | Group reports |
| Document and disseminate farmers experiences between indigenous knowledge and research | 2007 -2011 | Indigenous knowledge and research experiences from farmers documented and disseminated | Documentation available |
| Conduct research stakeholders workshops to share information and experiences | 2007 -2011 | One central research workshop each year to share experiences | Workshop report |
| Monitor the research extension program | 2007 -2011 | The performance of the research extension program monitored | Monitoring report |
| Document and disseminate experiences about the program to Caritas MADDO partners | 2007 -2011 | The research program documented and experiences shared amongst stakeholders annually | Documented information Research Extension reports |
| Objective 2 | Indicator | Means of verifications | Assumption |
| Increase food security and environmental conservation practices at household level | At least 80% of households of participating farmers are food secure as indicated by 80% of the children not being stunted | Annual program reviews | Favourable weather No outbreak of disease |
| Output 2.1 | Indicator | Means of verifications | Assumption |
| Knowledge and skills of partners on appropriate Post Harvest Handling (PHH) and processing techniques strengthened | 80% of participating farmers report improved harvesting, storage and drying, and that minimises wastage and quality loss | Annual program reviews | Beneficiaries effectively attend trainings |
| Activities | Timing | Expected Results | MOV |
| Train farmers groups in PHH and processing techniques | 2007 -2011 | All participating farmers groups have knowledge and skills in PHH for their major crops | Evaluation reports |
| Train collaborating parish farmer groups and participating farmer groups on agribusiness management | 2007 -2011 | Farmers gain knowledge and skills in agribusiness management by 2011 | Training reports |
| Facilitate farmers to organise themselves into groups for collective marketing | 2007 -2011 | At least 70 % of participating farmers groups market their produce collectively | Annual program reviews |
| Facilitate Caritas MADDO staff to participate in refresher courses on PHH and processing | 2007, 2009 | Staff update their knowledge and skills in appropriate PHH and processing | Annual program reviews |
| Document and disseminate relevant information on PHH and processing techniques | 2007 -2011 | Relevant information on appropriate PHH and processing of farmers produce documented and disseminated by 2010 | Documented PHH information |
| Output 2.2 | Indicator | Means of verifications | Assumption |
| Knowledge and skills of farmers on appropriate energy sources and their utilisation strengthened | At least 80% of the members of parish partners have access to appropriate energy sources and sustainably utilise them | Annual program reviews | Adequate and appropriate energy sources affordable by farmers |
| Activities | Timing | Expected Results | MOV |
| Collect information on appropriate energy sources and their utilisation methods | 2007 - 2007 | Information on appropriate and sustainable energy sources and their utilisation collected and updated every year | Documented information on sustainable energy sources |
| Facilitate training for Caritas MADDO staff on sustainable energy | 2007, 2008 | Caritas MADDO staff update their knowledge and skills in appropriate energy sources and utilisation | Training reports |
| Train partners in parishes on sustainable energy sources | 2008 -2011 | 70% of participating parishes gain knowledge and skills in sustainable energy sources and utilisation methods | Monitoring and evaluation reports |
| Document and disseminate farmers’ experiences on sustainable energy sources | 2008 -2011 | Experiences on the utilisation of appropriate energy sources documented and disseminated to all farmers organisations | Documented information |
| Output 2.3 | Indicator | Means of verifications | Assumption |
| Member of participating parishes have increased access to micro finance services for off farm activities | 80% of members of participating farmers groups have been linked to a micro finance institution and have an off farm IGA Beneficiary farmers have increased their income evident in ability to meet basic need such as paraffin, dressing, school fees and healthcare | Annual program reviews | Favourable MFI rates MFIs are willing to work with poor resource farmers |
| Activities | Timing | Expected Results | MOV |
| Conduct TOTS for community resource persons in entrepreneurial and business skills | 2007, 2009 | 2 TOTs per parish | Annual program reviews |
| Collect and disseminate to partners existing sources of funding | 2007 -2011 | Information disseminated every year | Documented information |
| Establish collaboration with MFI to provide services to members of local development associations | 2007 -2011 | 75% participating local development associations collaborating with at least 1 microfinance institution | Signed collaborative agreements |
| Document and share experiences on working with MFIs | 2007 -2011 | Experiences on working with MFIs documented and disseminated to all farmers organisations | Workshop report |

#### Gender Mainstreaming

| Objective 3 | Indicator | Means of verifications | Assumption |
| --- | --- | --- | --- |
| Caritas MADDO and partner CBOs programs are gender responsive | Policies, programs, procedures, budgets, and practices in Caritas MADDO and participating parishes all show commitment to promote equal opportunities for both men and women | Program documents and reports | Stakeholders appreciate as an important element for development |
| Output 3.1 | Indicator | Means of verifications | Assumption |
| Capacity of Caritas MADDO and partners at parish level in gender issues strengthened | Caritas MADDO and 70% of its parish partners acquire more skills and knowledge in gender mainstreaming and this is evident in their attitudes and practices | Annual program reviews | Male stakeholders who are the majority of stakeholders appreciate gender mainstreaming and participate in trainings |
| Activities | Timing | Expected Results | MOV |
| Conduct training needs assessment for Caritas MADDO staff, participating parishes | 2007/08 | Gender training needs assessment report highlighting the gaps and possible interventions | Needs assessment report |
| Develop suitable materials for gender training | 2007 | Tailor made gender training materials developed for Caritas MADDO by end of 2008 | Training manual |
| Facilitate gender training for Caritas MADDO staff and participating CBOs | 2008 -2011 | Staff and partners of Caritas MADDO equipped with gender mainstreaming skills | Training report Monitoring report |
| Strengthen gender analysis skills through refresher training workshops | 2008 -2011 | Staff and partners of Caritas MADDO update their gender analysis skills | Training report |
| Output 3.2 | Indicator | Means of verifications | Assumption |
| Gender mainstreamed in Caritas MADDO and participating partner parishes’ policies and programs | Caritas MADDO and participating partners are implementing gender responsive policies and programs | Policies and program documents | Stakeholders value gender as an important element for development |
| Activities | Timing | Expected Results | MOV |
| Review all Caritas MADDO policies and programs to identify gender gaps | 2007 | Gender gaps in all policies of Caritas MADDO and parish partners identified | Policy review reports |
| Update and mainstream gender in all Caritas MADDO policies | 2008 | Gender mainstreamed in all policies and systems | Engendered policy documents |
| Facilitate parish partners to mainstream gender in their systems | 2008 -2011 | 90% participating parish partners have mainstreamed gender in their systems | Partners engendered program reports |
| Facilitate partners to implement their engendered policies and programs | 2007 -2011 | 90% participating parish partners implementing engendered policies and their programs | Monitoring reports |
| Monitor and evaluate the implementation of partners gender mainstreamed policies and programs | 2007 -2011 | At least one monitoring and evaluation visit made to each parish every year | Monitoring and evaluation reports |
| Organise reflection meetings for partners to discuss and share experiences on gender mainstreaming | 2007 -2011 | At least one reflection meeting held with partners every year | Minutes of reflection meetings |
| Document and share experiences on gender mainstreaming within Caritas MADDO | 2007 -2011 | Experiences on gender mainstreaming documented and shared at least once a year | Documentation |
| Network with organisations with competencies in gender mainstreaming | 2007 -2011 | Collaboration established with at least 5 institutions | Records of networking activities |
| Establish Gender Disaggregated Data system | 2007 -2011 | Caritas MADDO and all stakeholders use disaggregated data system | GDD reports Evaluation reports |

#### HIV/AIDS Mainstreaming

| Objective 4 | Indicator | Means of verifications | Assumption |
| --- | --- | --- | --- |
| Caritas MADDO and partners programs and strategies HIV/AIDS responsive | By 2009, policies, programs, procedures, budgets, and practices in Caritas MADDO and participating CBOs all show commitment to reducing the impact of HIV/AIDS among staff and community | Program documents and reports | All stakeholders and partners appreciate HIV/AIDS as an important issue for development |
| Output 4.1 | Indicator | Means of verifications | Assumption |
| HIV/AIDS mainstreamed in Caritas MADDO policies and programs | All policies and programs are HIV/AIDS responsive | Progress reports, Policy documents Annual Program Reviews | Other health sector service providers extend their service to the beneficiaries |
| Activities | Timing | Expected Results | MOV |
| Sensitise Caritas MADDO staff and parish-based partners on HIV/AIDS | 2007 -2011 | One sensitisation workshop held for all staff and partners each year | Sensitisation workshop reports |
| Collect gender disaggregated data on HIV/AIDS and how it impacts CM programs and partners programs | 2007 -2011 | All program reports of CM and partners contain gender disaggregated data on HIV/AIDS and impact | Monitoring reports |
| Review all Caritas MADDO policies and programs to identify HIV/AIDS gaps and concerns | 2007 | HIV/AIDS responsiveness gaps identified in all Caritas MADDO policies and programs | Caritas MADDO policy and programs review reports |
| Monitor and evaluate the mainstreaming of HIV/AIDS in CM and partner organisations | 2007 -2011 | 1 visit to each parish per year to monitor HIV/AIDS mainstreaming CM programs reviewed annually assess HIV/AIDS mainstreaming | Monitoring reports Review report |
| Document and share experiences on HIV/AIDS mainstreaming | 2007 -2011 | Experiences documented and shared every year | Documentation and information shared |
| Output 4.2 | Indicator | Means of verifications | Assumption |
| Caritas MADDO and partner parishes network with HIV/AIDS organisations | Caritas MADDO and each parish effectively collaborating with at least one HIV/AIDS organisation and shown in communications, minutes of meetings and activity reports | Annual program reviews | partners appreciate HIV/AIDS as an important issue for development |
| Activities | Timing | Expected Results | MOV |
| Identify institutions and organisations dealing with HIV/AIDS | 2007 -2011 | At least one institution dealing with HIV/AIDS is identified for collaboration at each parish level | Minutes of meetings |
| Collaborate with organizations and institutions dealing with HIV/ | 2007 -2011 | Caritas MADDO and each of the parish partners collaborates with at least one service provider to access prevention counselling and mitigation | Collaborative agreements Annual program reviews |

#### Organisational Strengthening and Institutional Development

| Objective 5 | Indicator | Means of verifications | Assumption |
| --- | --- | --- | --- |
| Caritas MADDO and participating parishes have sustainable requisite organisational capacity to carry out activities | Activities are implemented as planned and cost effectively | Annual program reviews | Effective partnership between Caritas MADDO, partner parishes and networks |
| Output 5.1 | Indicator | Means of verifications | Assumption |
| Partner parishes have the organisational and institutional capacity to manage their programs | 70% of Partner parishes successfully implemented their action plans Partner parishes have management systems; plan and review activities ; and reports are timely and accurate | Annual program reviews | Parish leaders are open and willing to accept institutional change |
| Activities | Timing | Expected Results | MOV |
| Carry out organisational and institutional audit for the parish capacities | 2007 -2011 | At least 5 parishes undergo an organisational audit per year | Organisational audit reports of each organisation |
| Develop elaborate parish leadership capacity building programs | 2007 -2011 | Capacity building program elaborated | Capacity building plan |
| Facilitate organisational strengthening and institutional development processes for all partners | 2007 -2011 | Every participating parish facilitated to undergo organisational change process for development | Reports of organisational and institutional development exercises |
| Carry out baseline surveys for the new partner parishes through a participatory process | 2007-2009 | Socio-economic information in the areas of operations for the new partner parishes established | Survey reports |
| Facilitate strategic and action planning for those partner parishes | 2007 -2011 | Every participating parish has in place an elaborate strategic plan | Copies of farmers strategic plans |
| Facilitate the development of participatory monitoring and evaluation systems for participating partners | 2007 -2011 | Every participating parish has an elaborate monitoring and evaluation system | Monitoring systems |
| Provide specific training in such areas identified in 5.1.1 | 2007 -2011 | All participating partner parish leadership trained in areas like governance, management, group dynamics according to need | Training reports |
| Train partners in participatory approaches | 2008 and 2010 | One training conducted in 2008 and 2010 attended by key development personnel from partner parishes | Training report |
| Train partners in knowledge management | 2008 and 2010 | One training conducted in 2008 and 2010 attended by key development personnel from parishes | Training report |
| Support partner parish leaderships to develop systems and procedures for effective program management | 2007-8 | Every partner parish has in place effective systems and procedures for development activities | Management systems and procedures |
| Hold partner parishes meetings to share experiences and information about each others program | 2007-2011 | Partners learn form each other and improve on program implementation | Partner Meeting reports |
| Follow up partners programs implementation and provide backstopping | 2007-8 | Every partner parish visited once annually | Follow up, review and evaluation report |
| Output 5.2 | Indicator | Means of verifications | Assumption |
| Caritas MADDO has adequate capacity for implementing this strategic plan | At least 80% of planned activities implemented All requisite Caritas MADDO staff in place and competent enough to implement the programs | Personnel files and staff assessment reports Annual program review | Adequate resources to implement the program mobilised There is no significant staff turnover |
| Activities | Timing | Expected Results | MOV |
| Institute a professional Personnel officer | 2007 | Human Resources Manager in place | Organisational structure Staff List |
| Conduct human resources audit | 2007-2011 | Human resources audit conducted in 2007 and 2009 | HR audit report |
| Carry out internal organisational learning and change processes on a regular basis | 2007 and 2009 | Internal reflections and organisational learning processes conducted quarterly | Internal reflection reports |
| Review and adjust the human resources policy | 2007 | Comprehensive and competitive Human Resources Policy in place | Reviewed Human resources policy |
| Conduct/attend refresher courses to equip staff with the necessary contemporary knowledge and skills | 2007 -2011 | By 2011 every staff member has undertaken at least 2 short courses in line with their work | Feedback training reports |
| Formulate cardinal organisational terms of reference | 2007 | Clear organisational document spelling out the organisational values, vision, mission, mandate, roles and functions of the all stakeholders from the board to the community level | Constitution or whatever name CM might choose to call it |
| Formulate partnership policy | 2007 | Partnership policy formulated and operational detailing how Caritas MADDO will be start, nurture and wean partnerships | Partnership policy |
| Review and adjust existing policies | 2008 | All existing policies have been reviewed and updated | Updated policies |
| Develop a comprehensive resource centre | 2007 -2011 | Caritas MADDO resource centre in place and operational | Existence of resource centre |
| Hold stakeholder meetings to adjust the program to the changing context | 2007 -2011 | The organisation strategy reviewed and updated annually | Updated strategic plan |
| Conduct operational planning workshop for Caritas MADDO | 2007 -2011 | Action plans with clear targets and outputs laid down for each of the program key strategies annually | Annual Action plans |
| Carry out regular staff appraisals | 2007 -2011 | Appraisals organised for all staff once annually | Appraisal reports |
| Document, publish and share work experiences with stakeholders, partners and other Caritas agencies in other Dioceses | 2008 -2011 | At least one newsletter every year | Copies of documentaries produced |
| Carry out annual program review | 2007 -2011 | Progress of program implementation established and strategies reviewed | Annual program review report |
| Institute a scholarship fund for staff | 2007 -2011 | Functional scholarship fund | Annual program review report |
| Output 5.3 | Indicator | Means of verifications | Assumption |
| Capacity of parish partners to mobilise and manage financial resources strengthened | 80% of the parish partners have transparent financial systems in place | Annual program review | Parish partner realise the importance of financial management |
| Activities | Timing | Expected Results | MOV |
| Conduct needs assessment on financial management among identified parish partners | Annually | Detailed assessment of financial needs for all partners carried out | Needs assessment report |
| Design a training curriculum based on identified needs | From 2007 -2011 | A detailed training curriculum fro financial management training in place | Training curriculum |
| Train partners in book-keeping | From 2007 -2011 | All parish partners trained in bookkeeping | Training report |
| Prepare financial guidelines for parish partners for CM operations | From 2007 -2011 | All parish partners have financial guidelines for CM operations | Partner financial guidelines |
| Monitor and assess internal control systems and provide backup support on financial management issues for each parish partner | Continuous from 2007 | One discussion with management of each parish partner per year on internal controls | Minutes of the discussion |
| Conduct training on alternative funding for parish partners | Continuous from 2007 | At least one centralised training per two years | Training report |
| Establish a donor database and disseminate information to parish partners | 2008 | A popularised version of donor database in place and distributed | Lists of donors |
| Coordinate and facilitate external audits for parish partners with substantial funding | Annually | External audits conducted for partners with substantial funding | External audit reports |

#### Preventive and Curative Health for Development

| Objective 6 | Indicators | MOV | Assumptions |
| --- | --- | --- | --- |
| Contribute to the well being of the people through increased access to health services both curative and prevention | Reduced morbidity from major causes of ill health and reduction in disparity | Annual program reviews | Resources and facilities continue to be available |
| Output 6.1 | Indicators | MOV | Assumptions |
| Improved sustainability, range and quality of their services for body and soul | Presence of operational independent management structures and systems Budgets are strictly followed and reports available on time | Annual program reviews | Staff realise the importance of the strategy |
| Activities | Timing | Expected Results | MOV |
| Cooperate with public health authorities to revitalise and maintain primary health care | 2007-2011 | Routine Immunisations carried out Mass immunisation drives Distribution of malaria control nets | HMIS Annual program reviews |
| Improve access to - and equity in – health care for vulnerable groups are actively pursued by health units | 2007-2011 | The standard units of out put has increased or taken a neutral trend. | Progressive reports |
| Implement quality of care and management parameters in the process of accreditation | 2008-2009 | Establish at least criteria for quality of care and management for accreditation | Criteria in place |
| Enhance the capacity to provide Pastoral Care of the Sick | 2008-2011 | At least 20 Pilot Spiritual “Hope” teams have been formed and trained in 20 parishes. | Spiritual teams in place |
| Enhance capacity to provide basic mental health care | 2008-2009 | At least three units in Masaka report provide of mental health services | Annual program review |
| Increase the capacity to provide Natural Family Planning (NFP) in our units has been | 2008 | Provision of NFP is reported in 50% of health centres level 3 | Annual program review |
| Ensure that units comply with Emergency Obstetric Care criteria |  | All units have the basic equipments to provide the EMOC services. |  |
| Improve accounting practices and transparent financial accountability in Masaka Diocesan units | 2008 | Improved financial management and sustainability | Improved financial reports |
| Train HUMC to assess financial sustainability of own units | 2008 | HUMC trained to assess financial sustainability of own units and decide upon the scope of the care package offered | Training report |
| Institute standard financial management guidelines/manuals | 2007 | The financial management guidelines/manuals are in use in the Diocesan Health units | Guidelines in resource centre and partners |
| Ensure efficient utilisation of resources | 2007-2011 | HUMC are making efficient use of their resources | Financial reports are consistent with budgets |
| Objective 7 | Indicator | Means of verifications | Assumption |
| To increase access to sustainable safe water and sanitation facilities rural poor communities | By end of 2011, 70% of targeted communities have access to safe water. | Annual program review | Beneficiaries put into practice what they learn |
| Output 7.1 | Indicator | Means of verifications | Assumption |
| Improved skills of beneficiary communities to manage protected public water point sources in their areas. | By end of 2011, 40% of targeted communities can testify to maintaining a safe water chain right from the source to the household | Annual program review | Beneficiaries put into practice what they learn |
| Activities | Timing | Expected Results | MOV |
| Strengthen the knowledge and skills of the community to maintaining safe water through health education | 2007-11 | At 5 TOTs trained per parish | Activity reports |
| Equip the community with Operation and maintenance skills and knowledge | 2007-11 | At 100 members of the community trained per parish | Activity reports |
| Follow up monitoring and technical support | 2007-11 | One visit per target parish per year | Activity reports |
| Output 7.2 | Indicators | MOV | Assumptions |
| Communities supported to access nearby protected water point sources | at least 60%of households in target parishes can obtain water within 1.5 km | Annual program review | Resources are available |
| Activities | Timing | Expected Results | MOV |
| Protect water sources as the situation warrants | 2007-11 | 20 water points per year | Activity reports |
| Output 7.3 | Indicators | MOV | Assumptions |
| To uplift awareness of to adopt the right hygiene and sanitation behaviour | 80% of target communities have and use latrines proper | Annual program review | People appreciate the importance of managing human waste |
| Activities | Timing | Expected Results | MOV |
| Carry out training needs assessment on household sanitation | 2007-2009 | Household knowledge, attitudes and practices of the community on sanitation of each parish is documented. | Report of needs assessment |
| Develop tailor made training materials | 2007-2009 | Training manual for sanitation | Training manual |
| Conduct a training of trainers (TOT) for parish partners in sanitation | 2008 | 5 trained TOTS gain knowledge and skills in sanitation | Training report |
| Train communities to strengthen their knowledge and skills for proper hygiene and sanitation behaviour. | 2007 -2011 | 80% Beneficiaries trained in proper hygiene and sanitation behaviour | Annual program review |
| Conduct refresher courses for parish TOTs on hygiene and sanitation | 2008 - 2011 | 5 TOTs update their knowledge on Water and sanitation every year. | Training reports |
| Collect and disseminate information on Water and sanitation practices to parish partners | 2007 0nwards | Information on Water and sanitation collected and disseminated at least once a year | Library list for Caritas MADDO and CBOs Progressive reports |
| Facilitate study tours/exchange visits for hygiene and sanitation TOTs | 2007-2011 | Each beneficiary visits at least one other household to learn about better sanitation | Study tour report |
| Output 7.4 | Indicators | MOV | Assumptions |
| Strengthen household capacity to collect rainwater and maintain a safe water supply throughout the dry days | 70% of targeted households have access to water due to exploitation of rainwater | Annual program review | Beneficiaries put new knowledge into practices |
| Activities | Timing | Expected Results | MOV |
| Strengthen the knowledge and skills of the community to trap rainwater through affordable appropriate technology | 2007-2011 | 80% of targeted beneficiaries trained in management of rainwater | Training report |
| Equip the community with Operation and maintenance skills and knowledge pf the rainwater catchments system | 2007-2011 | In each target community 5 TOTs trained | Training report |

#### Human Rights and Good Governance Strategies

| Strategic objective 8 | Measurable indicators | MOV | Assumptions |
| --- | --- | --- | --- |
| To unchain widows and orphans from exploitation and discrimination | Reduction in cases of exploitation and discrimination | Annual program review | Political security No cultural and social interruption |
| Output 8.1 | Indicators | MOV | Assumption |
| Strengthen capacity to protect and prevent violation of widows’ rights and discrimination against widows and orphans | Number of human rights activists trained | Annual program review | Social and political security in the program areas |
| Activities | Timing | Expected results | MOV |
| Situation analysis to identify existing forms of violation of widows’ rights and discrimination against widows and orphans | 2007 | Research conducted and findings documented and disseminated through radio talk shows, booklets, newspaper articles and workshops | Analysis Report |
| Empower the public on CEDAW and widows’ rights | 2007 – 2008 | Key community stakeholders e.g. local leaders, school community, police enlightened on widows’ and girl children rights | Training Report |
| Empowering women to demand and protect their rights at all levels | 2008– 2011 | Women leaders trained to handle issues of discrimination against widows | Training Report |
| Remedial measures taken to enable vulnerable orphans and children access education | 2007– 2011 | Vulnerable orphans supported in school | Activity Reports Statistics of beneficiaries |
| Provide legal protection and defence against property and personal rights to widows and orphans | 2008– 2011 | Orphans and widows represented to ensure justice to their property | Annual program review |
| Establish community structures capacity to undertake activities in protection of widows and orphans | 2007– 2011 | The writing of wills promoted Activists trained in protection of widows and orphans rights Committees of widows and orphans volunteers formed | Annual program review |
| Objective 9 | Indicator | MOV | Assumption |
| To promote good governance and leadership that addresses gender concerns | Positive changes influenced (in terms of policy, budget and program) at local governmental level | Annual program review | Absence of political interference , conducive environment for operations |
| Output 9.1 | Indicator | MOV | Assumption |
| Strengthened democracy monitoring from the gender perspective as precursor for development | Election monitoring reports with gender disaggregated data | Annual program review | Absence of political interference , conducive environment for operations |
| Activities | Timing | Expected results | MOV |
| Carry out civic education | 2007-2011 | The target community sensitised on civic duty | Activity report |
| Skills development for monitoring with a gender perspective | 2007-2009 | Monitoring capacity for monitoring government programs and democracy in place | Training report |
| Monitoring institutions that are supposed to foster democracy | 2007-2011 | Activities of Electoral Commission, District and sub county Councils , political parties and courts of law monitored | Analysis reports |
| Election monitoring | 2007-2011 | All elections closely monitored | Analysis reports |
| Advocate for policies that promote good governance and for the enforcement of the existing policies but addressing gender concerns | 2007-2011 | Increased gender concerns in the promotion of good governance and leadership | Annual program review |
| Output 9.2 | Indicator | MOV | Assumption |
| Citizen’s effective engagement in multi-party politics enhanced | No of people participating in electoral processes at all levels Increased debates on issues like corruption, misappropriation of public funds, government programs | Annual program review | Continued conducive policy environment where there is freedom of speech |
| Activities | Timing | Expected results | MOV |
| Conduct consultations to identify pertinent issues | 2007 – 2011 | Consultative meetings conducted and information about multi-party party politics documented | Minutes of meetings and issues identified |
| Educate citizens about multiparty politics, decision making and the electoral process | 2007 – 2011 | Civic education seminars, posters/fliers made and distributed | Seminar reports IEC materials available at resource centres and at partner level |
| Capacity building of citizens on leadership to enable them hold their leaders accountable | 2007 – 2011 | Infomercials, Radio programmes about citizens and multi-party politics and drama skits conducted Information sharing workshops | Numbers of IECs materials produced |

#### Promote the value of working together to assist the needy in our communities

| Objective 10 | Indicators | MOV | Assumptions |
| --- | --- | --- | --- |
| Increased access to social services and welfare for disadvantaged and vulnerable groups | Numbers of beneficiaries | Annual program reviews | People realise that real development will come form changed attitudes |
| Output 10.1 | Indicators | MOV | Assumptions |
| Increased local contribution to initiatives like Caritas MADDO development program | Positive change in the amounts raised by the Diocese on Caritas day | Annual program reviews | People realise that real development will come form changed attitudes |
| Sensitise the community about the work of Caritas MADDO | 2007-2011 | Wider cross-section of People in Masaka Diocese and beyond aware of what Caritas MADDO stands for and does | Annual program reviews |
| Mobilise people to assist the disadvantaged and vulnerable people in their own communities | 2007-2011 | Increased incidences of community self-help initiatives | Annual program reviews |
| Mobilise the community for self help on Caritas Day | 2007-2011 | Increasing collection for development | Annual program reviews |
| Output 10.2 | Indicators | MOV | Assumptions |
| Strengthened institutional capacity to respond to problems of the disadvantaged groups | Increased number of interventions to support the needy | Annual program reviews | Facilities and resources available |
| Activities | Timing | Expected Results | MOV |
| Carry out studies to analyse problems of the vulnerable groups | 2007-2011 | Problems of vulnerable groups like street children, single mothers, orphans documented | Study reports |
| Devise strategies to respond and support the vulnerable and disadvantaged | 2007-2011 | Interventions to support : Orphans AIDS patients Street children Youths Single mothers Prostitutes | Number of Projects developed |
| Prepare for disaster | 2007-2011 | Potential for disaster foreseen and prepared for, including but not limited to, storms, hurricanes, earthquakes, locusts and God forbid, war | Availability of resources |

# Annex 3: Budget

The following assumptions were made concerning financial resources for this strategic plan

- Each intervention will be implemented in  25 parishes

- Investments will include purchase of 3 four wheel drive vehicles, 6 motorcycles and one boat

- This plan does not include salaries and wages

# Footnotes

Uganda Bureaux of statistics 2006-09-07

In this discussion, Masaka is equivalent to Masaka Diocese

Adapted from Uganda Participatory Assessment Report, 2005

Participatory Technology Development (PTD)

# Text boxes

Program Goal:

Improved Standards of Living for all people living in Masaka

Intermediate Results:

Food security and poverty reduction through increased production and productivity; decreased morbidity

Program Output 5

Strengthened institutional capacity to implement activities

Program Output 4

Good governance and human rights for all promoted

Program Output 2

Improved Diocesan Health Services

Program Output 1

Households empowered to effectively practice sustainable agro-economic activities

Program Output 5

The spirit of assisting the needy in our communities promoted

Program Output 2

Communities enabled to avoid preventable diseases

Components

- Strengthen structures

- Better policies and systems

- Well motivated staff

- Empower Parishes to co-implement

Components

- Improve quality and quantity of services

- Improve management

- Continuously assess service  and act

Components

- Democracy monitoring

- Promote participation in politics,

- Unchain widows and orphans from exploitation and discrimination

Components

- Agricultural Extension

- Input Supply

- Agricultural Marketing

- Rural Savings and Credit

- Appropriate Technology

- Natural Resources Management

Components

- Increase access to safe water and sanitation

- Improve hygiene and sanitation behaviour

- Promote Immunization

- Promote better nutrition

Components

- Mobilize  local contribution

- Analyze problems of vulnerable groups

- Devise strategies to support vulnerable groups

- Prepare for disasters

BOARD OF DIRECTORS

Development Coordinator

Assist. Dev’t Coord.

Senior Program Officer (HR)

PO-Finance & Admin.

PO- Water and Sanitation

PO-Organisational Development

PO-Social Services

PO-Agric. And NRM

Manager MSC

APO

APOFA

Accountant

Cashiers

Bookkeepers

Dep.  Man

Housekeepers

Waiters

Caterers

Secretary

Cooks

APO

Agrics

Vets

Dairies

Transport

Receptionists

Storekeeper

Cleaners

APOSS

Children’s desk

Welfare desk

Senior

Internal Auditor

APOOD

CATHOLIC PARISHES

BENEFICIARIES

PO-Health

APE/Health

HIV Desk

PHC