# REPUBLIC OF CAMEROON

# Peace – Work – Fatherland

# MINISTRY OF AGRICULTURE AND RURAL DEVELOPMENT

REGIONAL DELEGATION FOR THE SOUTH WEST

DIVISIONAL DELEGATION FOR MEME

(January – December 2013)

Submitted to: THE REGIONAL DELEGATE, MINADER, S.W.R

Prepared by: Richard MOLUA NEBALE

(Agro-Environmentalist)

Divisional Delegate, Meme

December 2013

TABLE OF CONTENTS

|  | EXECUTIVE SUMMARY | 2 |
| --- | --- | --- |
|  | SECTION 1: MONOGRAPHIC AND METEOROLICAL DATA | 4 |
| 2.1. | Monographic Data | 5 |
| 2.2. | Metrological Data | 5 |
|  | SECTION 2: ADMINISTRATION AND FINANCE | 7 |
| 3.1. | Personnel Situation | 7 |
| 3.2. | Finance | 13 |
| 3.3 | Infrastructure and equipment | 18 |
| 3.3.1. | Infrastructure | 18 |
| 3.3.3. | Equipment | 19 |
|  | SECTION 3: TECHNICAL REALISATION | 21 |
| 4.1. | Partner Activities | 33 |
|  | SECTION 4: PROBLEMS AND CONSTRAINTS | 34 |
|  | ANNEXES | 35 |
|  | ANNEXE I: BIP projects for MINADER IN 2013 | 35 |
|  | Annex 2: Cocoa production form LBAs and some Producers organisations | 36 |
|  | Annex 3: Production figures for perennial crops | 37 |
|  | Annex 4: Production figures for food crops | 37 |
|  | Annex 5: Comparative food crop production figures for the past 4 year | 39 |
|  | Annex 6: Comparative cash crop production figures for the past 4 year | 39 |
|  | Annex 7: Prices of Agricultural Inputs in Kumba Main Market | 40 |
|  | Annex 8: Prices of Agricultural tools/equipment in Kumba Main Market | 41 |

EXECUTIVE SUMMARY

- The Divisional Delegation of Agriculture and Rural Development Meme Division has as main mission to plan, implement and evaluate Government policies and action in the domain of Agriculture and Rural Development in the Division. The activities of the delegation are carried out under 4 major intervention programmes:

- Improve productivity and competitiveness in the agricultural sector  - the acquisition and distribution of quality seeds, fertilizers, pesticides and spray equipment;

- Modernisation  of rural infrastructure and production – improving farmers access to agricultural financing, equipments and rural infrastructures (including farm to market roads)

- Capacity building and institutional development – training for sustainability of producers organisations and staff

- Sustainable management of natural resources related to agriculture –promoting and  implementing sustainable agricultural practices to conserve forest, water and soil resources

- To achieve these mission and goals the Divisional Delegate (Coordinator) is supported by 8 Divisional Chiefs of sections - each performing a definite but complementary function. At the lower level, its activities are ramified and implemented by 5 Sub-Divisional Delegations, 02 CEACs and 24 Agricultural Posts

To further facilitate the activities of the staff, the Division has equally be carved into 27 NAERP zones and 22 ACEFA zones. Two Agricultural training schools exist– REDSTS and CDSTS and 01 MINADER projects  - (Cocoa-Coffee Seedling Project (CCSP)) operating within the Division

- The Delegation and its affiliate services have a total of 56 staff. There exist 17 vacant posts.

- In terms of buildings (infrastructure), of the 29 structures required, only 09 have been constructed of which 01 require total rehabilitation (SDDARD Mbonge). DDARD and SDDARD Kumba I have been rehabilitated under the 2013 PIB.

- The service if equipped with 02 non-functional PNVRA vehicles (01 presently undergoing repairs); 30 motorcycles (07 completely bad); 04 computers and 04 printers.

- Though insufficient, all the services within the Division have functioning credits.

- Technical realisations. The following results were achieved under the different intervention programmes:

IMPROVE PRODUCTIVITY AND COMPETITIVENESS IN THE AGRICULTURAL SECTOR

  - Multiplication ploys/nurseries

05 Ha of cocoa clonal seed garden, 0.5Ha cassava and 0.5Ha plantain multiplication plots, 13 cocoa and 02 Robusta coffee nurseries were established

(b) Improved planting materials

99 340 cocoa pods, 340 880 coffee cuttings, 469 733 cocoa seedlings, 4350 oil palm seedlings, 340 citrus plants, 6850 kg of maize seeds, 111500 cassava cuttings and 875 plantain suckers were distributed. All were given for free except for maize seeds and oil palm seedlings that were delivered at subsidised prices

(c) Fertilizers

55 tons mineral fertilizer (1100 bags) and 13.5 (270 bags) tons of organic fertilizer distributed to 24 farmers organisations

(d) Pesticides/spray equipments

65300 sachets contact/systemic fungicide were distributed 48 Cooperatives. This was accompanied by the distribution of 07 atomisers, 09 knapsack sprayers and 23 protective kits

(e) 2013 Regional Agro-pastoral Show

35 farmers participated winning 53 prizes – Kumba I (8 prizes); Kumba II (11 prizes); Kumba III (10 prizes); Konye (12 prizes) and Mbonge (10 prizes). Though Meme registered an increase in performance, the number of exhibits reduced due to the poor nature of roads especially from the Konye Sub-Division

MODERNISATION OF RURAL INFRASTRUCTURE AND PRODUCTION

- There exist 10 village barns with a total membership of 1550, a volume of savings of 40,286,870 FCFA and volume of loan of 32,311,000 FCFA. Savings has increased by 8.3% and loans by 13.9% compared to last year same time. Loans for agricultural purposed is highest with 55.8% followed by Socials (22.9%); commerce (16.7%) and for construction (4.6%). However, these figures are still to be updated

- 10 out of 17km Dikome – Madie road rehabilitated

- DDARD, SDDARD I and Agric Post Bai Grass rehabilitated; SDDARD Konye constructed

- 32 point of use filters (bio-sand filters) constructed and distributed to 32 household in the Lake Barombi Mbo village

- 4km road at Banga mile 40-Moungo road rehabilitated

CAPACITY BUILDING AND INSTITUTIONAL DEVELOPMENT

Young Farmers Settlement Site

- 12500 (50%) of improved cocoa and 1550 (78%) oil palm seedlings distributed to 18 Young Farmers

- 05 semi-apartments constructed ( 04 fro BIP 2012 and 01 for BIP 2013)

- Construction of borehole and warehouse is ongoing at 90% and 60% respectively

- SOWEFCU and its 29 affiliate Cooperatives have been restructured in compliance with OHADA uniform Act and 01 workshop organised for 10 cooperatives on Administrative Management and accounting

- 14 statistical reports produced and 01 agric survey carried out

- 03 sensitisation meetings organised for small holder rubber farmers on formation of cooperatives

- 101 FFS and 07 FBS created, graduating 2155 and 188 farmers respectively

- For NAERP, 81 training sessions carried out on 29 different topics involving 50 POs. 162 Production projects developed and monitored

- For ACEFA, 126 projects were monitored and 05 handed over

- 35 sensitisation meetings and 06 workshops organised by CEACs

- For production figures see table on page 23 in report

SUSTAINABLE MANAGEMENT OF NATURAL RESOURCES RELATED TO AGRICULTURE

02 POs received each a subvention of 4800000 FCFA under the IVDP. Service provider still to develop the 02 sites

- Major problems the absence of a functional vehicle for the Divisional Delegate; difficulty in getting production figures from LBAs; inadequate functioning credits and  the complete absence of office buildings for many chiefs of agric pots.

- The present report covers the period from January to June 2013. It is sub-divided into 05 sections:

  - Section 1: Monographic data;

  - Section 2: Administration and Finance

  - Section 3: Technical realization;

  - Section 4: Constraints and difficulties encountered;

  - Section 6: The Annexes

This section presents some basic or technical information about the Division

1.1. Monographic data

The table below presents the distribution of some monographic parameters for the five Sub-Divisions found in Meme Division.

Table1: Tentative distribution of Meme population and surface area per sub-division.

| Sub division | No of villages | Total surface area (sq km) | Total population | Active farming population | Total area cultivated in 2013 (Ha) |
| --- | --- | --- | --- | --- | --- |
| Kumba I | 9 | 150 | 37731 | 10610 | 7567 |
| Kumba II | 6 | 95 | 53508 | 13117 | 5045 |
| Kumba III | 10 | 120 | 39446 | 16472 | 8409 |
| Konye | 38 | 2230 | 79474 | 42804 | 81695 |
| Mbonge | 70 | 3374 | 211860 | 121494 | 175024 |
| TOTAL | 133 | 5969 | 422019 | 204497 | 277740 |

Source: DCS-ASS, SDDARDs and CAPs/ZEWs field note books

  - Meteorological data

There exist 3 meteorological stations in the Division (IRAD Barombi Kang, CDC Mukonje and CDC Mbonge) but only that is CDC Mukonje is functional. The data presented below are those of CDC Mukonje.

Table 3: Qualitative appraisal of temperature and rainfall

|  | FIRST CYCLE | CHARACTERISTICS | SECOND CYCLE | CHARACTERISTICS |
| --- | --- | --- | --- | --- |
| TEMPERATURE | GENERAL APPRAISAL |  | GENERAL APPRAISAL |  |
|  | Low |  | Low |  |
|  | Normal | x | Normal | x |
|  | raised |  | raised |  |
| RAINFALL | GENERAL APPRAISAL |  | GENERAL APPRAISAL |  |
|  | Insufficient |  | Insufficient |  |
|  | Normal | x | Normal |  |
|  | excessive |  | excessive | x |
|  | APPRAISAL AT THE BEGINNING |  | APPRAISAL AT THE BEGINNING |  |
|  | Early | x | Early | x |
|  | Normal |  | Normal |  |
|  | Late |  | Late |  |
|  | APPRAISAL AT THE END |  | APPRAISAL AT THE END |  |
|  | Early |  | Early |  |
|  | Normal | x | Normal |  |
|  | late |  | Late | x |
|  | APPRAISAL OF THE DISTRIBUTION |  | APPRAISAL OF THE DISTRIBUTION |  |
|  | Irregular |  | Irregular |  |
|  | regular | x | Regular | x |

This table shows that the temperatures were normal during the year, irrespective of the season. Rains were regular. It started earlier and ended late as compared to the previous year.

Table 3: Mukonje Meteorological data

Rainfall

| Months | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No days | 1 | 6 | 11 | 13 | 10 | 10 | 25 | 26 | 18 | 19 | 11 | 6 | 156 |
| Rainfall(mm) | 8.1 | 74.5 | 266 | 202 | 273.5 | 207 | 266.5 | 256 | 254 | 320 | 167.5 | 85 | 2380.1 |

R humidity

| Months | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RH% | 7504 | 6570 | 9335 | 7508 | 7511 | 7519 | 7459 | 8250 | 7221 | 7052 | 7829 | Na | 7614 |

Sunshine

| Months | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No of hours | 162.3 | 140.8 | 123.5 | 119.7 | 142.5 | 95.8 | 44.1 | 43.3 | 79.9 | 113.3 | 121.3 | Na | 107.8 |
| No days sunshine | 28 | 26 | 24 | 20 | 26 | 28 | 15 | 14 | 24 | 26 | 23 | NA | 254 |

Temperatures

| Months | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Max ( 0c) | 31.43 | 33.12 | 32.11 | 31.01 | 31.04 | 30 | 27.83 | 27.20 | 29.2 | 29.93 | 20.25 | Na | 29.37 |
| Min (0c) | 23.17 | 22.75 | 21.45 | 21.7 | 21.98 | 22.1 | 20.74 | 21.27 | 22.4 | 20.98 | 14.3 | NA | 21.16 |

Source: CDC Mukonje	F= faulty	  NA= Not available

Table 3: Rainfall data from rain gauge at DDARD

| Rainfall | months | Total |
| --- | --- | --- |
|  | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec |  |
| No rainy day | 3 | 3 | 19 | 10 | 12 | 17 | 19 | 18 | 22 | 21 | 16 | 6 | 166 |
| Rainfall (mm) | 29 | 32 | 202 | 140 | 198 | 392 | 516 | 271 | 249 | 333.5 | 207 | 126 | 2695.5 |

Source: DS/ASS Meme

Observations

From these two tables we can observe that:

- The highest rainfall was recorded in October for Mukonje (320mm), while July was the highest for DDARD station (516mm). A total rainfall is 2695.5mm for DDARD station as against 2380.1mm for Mukonje. This is the proof of the necessity to have weather station in every production basin.

- Rainfall witnessed the highest this year as compared to the past 05 years (see Annex 1)

- Rain fell for 51 days of 61 for the months of July and August, representing 83% of rainy days. As a result many cocoa farms suffered heavily from black pods diseases during that period.

This section presents

- The personnel situation of the entire Division

- Finances (office credits, BIP and other investments)

- Inventory of infrastructure, movable and electronic equipments

## 2.1. Personnel Situation

2.1.1. DIVISIONAL DELEGATION MEME

2.1.1. DIVISIONAL DELEGATION MEME

| No | Names and Surname | Date and place of Birth | Sex | Grade | Matricule Number | Category/Index | Date of entry into Adm | Probable retirement date | FUNCTION |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Actual | Supposed |  |  |  |
|  | Richard Molua Nebale | 01/06/64 Victoria | M | I.A | 538849-X | A2/1115 | A2/1140 | 17/07/1989 | 2019 | DIVISIONAL DELEGATE |
|  | Tekombo Zangue Jean Claude | 11/02/59 Dschang | M | IPTA | 368875-Y |  |  | 10/7/1985 | 2014 | DCS-AD/ DS PNVRA/CTD ACEFA |
|  | Kemgne Timothee | 20/11/59 | M | IPTA | 171758-F |  |  | 15/07/83 | 2014 | DC - FIMAC |
|  | Kuefouet Benoit | 01/01/1970 Santchou | M | I.A | 559785-A |  |  | 7/11/1997 | 2025 | DCS/ASS |
|  | Nzene Sylvester Enongene | 10/06/63 Bangem | M | TPA | 174397-Z |  |  | 01/07/85 | 2018 | DSC-COOP/CIG |
|  | Feh Benjamin | 01/12/66 Bali Nyonga | M | ATGR | 530555-S |  |  | 17/07/89 | 2021 | DCS-RE |
|  | Leah Wobe Bitasme | 16/12/59 Kumba | F | TA | 153660-G |  |  | 15/07/82 | 2014 | DCS-PB (Acting) |
|  | Misodi nee Ngowo Regina Ndive | 04/06/60 Victoria | F | T.A | 365063-E |  |  | 18/11/85 | 2015 | CBAF (Acting) |
|  | Kamgwa Richard | 15/09/62 Douala | M | IPTA | 523866-U | 940 | 1050 | 20/07/87 | 2017 | Staff DDARD- CTS/PV ACEFA |
|  | Njoache Gregory Ezeah | 01/01/64 Esoh Atah Fontem | M | ITA | 516 753-U | A1/560 | A1/580 | 20/06/1988 | 2019 | Staff Div section Phyto Brigade |
|  | Tita Raymond Fon | 09/09/1985 Ekona | M | IT | 740537-W | CAT 10 | ECH 1 |  | 2030 | Staff Div Section of Agric surveys/statistics |
|  | Assah Jerome Musong |  | M | ITGR | 172156-M |  |  |  |  | Staff Div Section R/E |
|  | Evet Aboh Fomboh |  | F | CDT | 741961-E | CAT 8 | ECH I |  |  | Acting chief of Section CD/LD Meme |
|  | Ekolle Ayisi Wilson | 18/09/58 Madie Ngolo | M | CO | 124899-M | cat. 9/8 |  | 10/3/1988 | 2013 | Staff CD/LD (SICK) |
|  | Chia Flora Futelia |  | F | TA | 727674-I |  |  |  |  | Staff Div Section COOP/CIG |
|  | Nambangi Victor Ote Musongo | 05/07/65 Kumba | M | TA | 513741-J | 505 |  | 9/2/1989 | 2019 | Staff Div Section Support to Project |
|  | Mbunh Mbiakop Charles Franklin |  | M | TPGR | 765182-B | Cat B | 335 |  |  | Staff Div Section R/E |
|  | Makem Assembo Claude Francois | 07/06/1983 Mboebo | M | I A | 734325-P | CAT 111 | ECHELON 1 | 08/12/2011 | 2033 | CGE ACEFA |
|  | Ndassie Philippe | 11/11/74 Kumba | M | SA | 673354-Y |  |  | 1/1/2009 | 2024 | Yard Man |
|  | Lobe Franklin Mokube | 05/04/85 Dikome Balue | M | SA | 6672210-Q |  |  | 1/1/2009 | 2035 | Night watch |

2.1.2. SUB DIVISIONAL DELEGATION  - KUMBA I

| No | Names and Surname | Date and place of Birth | Sex | Grade | Matricule Number | Category/Index | Date of entry into Adm | Probable retirement date | FUNCTION |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Actual | supposed |  |  |  |
|  | Njukang nee Mbetcha Tongwa Grace | 02/02/66 Lebailem | F | ITA | 530662-H | A1/650 | A1/740 | 03/07/89 | 3/7/2021 | ACTING SDDARD KUMBA I. |
|  | Tekombo nee Mantoh Jeannette | 13/06/60 Babadjou | F | TPA | 369422-Z | B2 | B2 | 10/12/1985 | 2015 | SUPPORT STAFF KUMBA I |
|  | Ngwa Jesenta Azinwi | 09/12/85 Manyemen | F | ATA | - | C | C | 16/03/2010 | 2040 | SUPPORT STAFF KUMBA I |
|  | Atemkeng Leduina | 25/07/82 Kumba | F | ATA | 723536-Z | 740 |  | 2010 | 2032 | SDDARD KUMBA I. |

2.1.2. SUB DIVISIONAL DELEGATION  - KUMBA II

| No | Names and Surname | Date and place of Birth | Sex | Grade | Matricule Number | Category/Index | Date of entry into Adm | Probable retirement date | FUNCTION |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Actual | supposed |  |  |  |
|  | Keubou Jean | 08/05/60 Fongo T. | M | TPA | 369206-N | 505 |  | 10/7/1985 | 08/04/2015 | SDDARD Kumba II / CAP Kosala |
|  | Masama Annie E | 14/02/1975 kumba | F | SA | 781362-Y | 3/1 |  | 2011 | 14/02/2025 | OFFICE DUTIES Kumba II |

2.1.3. SUB DIVISIONAL DELEGATION - KUMBA III

| No | Names and Surname | Date and place of Birth | Sex | Grade | Matricule Number | Category/Index | Date of entry into Adm | Probable retirement date | FUNCTION |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Actual | supposed |  |  |  |
|  | Kome Njalla Leopold | 13/08/64 Mbouroukou | M | TPA | 530 597-M | B2/405 | B2/420 | 3/7/1989 | 08/2019 | SDDARD Kumba III / |
|  | Dubila Florence Levla | 17/09/63 Nkar - Jakiri | F | TA | 519 994-M | C/310 | B1 | 01/02/1989 | 09/2018 | CAP Malende |
|  | Anki Nancy Mambo | 13/12/89 Ekondo Titi | F | CO | 746 514-M | Cat 81 | 8 | 11/11/2011 | 2044 | Office Duties |
|  | Tembi Malta | 15/12/81 | M | T.A(CO) | 742309 | Cat 81 | 8 | 2011 | 2036 | Extension Barombi Kang |

2.1.4. MBONGE SUB - DIVISION

| No | Names and Surname | Date and place of Birth | Sex | Grade | Matricule No | Category/Index | Date of entry into Adm | Probable retirement date | FUNCTION |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Actual | supposed |  |  |  |
|  | Ndip Wilson Defang | 22/06/62 Difang Mamfe | M | TPA | 174395-Z | 610 | 685 | 15/06/87 | 2017 | Sub-Divisional Delegate |
|  | Neba Samuel Shu | 06/08/62 Bafut | M | TPA | 376716-R | 540 | 610 | 1998 | 2017 | CAP Ediki |
|  | Nzambu Gabriel | 07/09/61 Bamenda | M | TA | 376668-C | 370 |  | 27/06/87 | 2016 | CAP KWAKWA |
|  | Awungacha Nju Tamo | 13/09/73 L. Fontem | M | IA |  |  |  | 29/06/2011 |  | (PNVRA) Ekombe CAP |
|  | Njonty Scolar Manyor | 1/4/1982 Mamfe | F | ATA | 700779-I | 180 |  | 20/04/210 | 2037 | Acting Zew CAP/Banga bakundu |
|  | ZONG PETER |  | M | ATA |  |  |  | 2012 |  | ZEW CAP, Boa Bakundu |
|  | NENKEP FLORIAN | 15/03/1984 MOUMEE | M | ATA |  |  |  | 20/04/2010 |  | PNVRA) AP KOTTO BAROMBI |
|  | Nkeng Michael Zangwa | 10/07/67 Muyuka | M | TA | 513677-L | 235 |  | 20/06/88 | 2022 | CAP MUNDONGO |
|  | Etone Loveline Mekolle | 04/04/65 Mwambong | F | CO | 501094-O | Cat 8/9 |  | 27/06/86 | 2020 | DIR CEAC Mbonge |
|  | Vincent Chinsal | 1977 | M | TSA |  | B2 |  | 2011 |  | CAP BEKONDO |
|  | Ndipso Pauline | 21/11/1985 | F | ATA | 764128-E | C |  | 2012 |  | ZEW AP - BIG BUTU |
|  | Besong Philip Eta | 01/11/1980 kembong-Mamfe | M | TA | 749376-H | B1 |  | 2012 |  | ZEW AP - BAI GRASS |
|  | Ngukang Constance |  | F | ATA | 737551-V | B1 |  | 2012 |  | ZEW AP - BIG BEKONDO |
|  | Mrs Fon Florence | 1968 mbengwi | F | TPA | 547529-A | B2 | 610 | 1993 | 2023 | CAP AP - BAI PANYA |
|  | Mbilleufeh Usmanou Nozieunoh | 20/03/1973 Bafanji-Ndop | M | TSA | 734520-I | B2 |  | 2012 |  | ZEW – Nganjo |
|  | Tigdon Tyson Irene | 03/11/77 | F | SA | 719937-A | Cat5/1 |  | 1/12009 | 2027 | ZEW – Bai Panya |

3.1.5. KONYE SUB DELEGATION

| No | Names and Surname | Date and place of Birth |  | Grade | Matricule No | Category/Index | Date of entry into Adm | Probable retirement date | FUNCTION |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Actual | supposed |  |  |  |
|  | Ngeh Humphrey | 31/12/60 Kupe Muaneguba | M | TPA | 361933-Q | B2/505 | B2/595 | 1/7/1986 | 2016 | SDDARD Konye |
|  | Nzifack John | 26/06/60 Dschang | M | TPA | 368973-I | B2/575 | B2/595 | 10/7/1985 | 2014 | CAP Matoh Konye |
|  | Tezoh Lawrence | 22/09/67 Fosimondi | M | TA | 538866-R | B1/505 | B1/505 | 17/07/89 | 2022 | CAP Lobange |
|  | Mbah Felix Achah | 26/05/65 Mpundo Balong | M | TA | 519845-P | B1/370 | B1/405 | 1/7/1988 | 2020 | CAP Kurume |
|  | Visa Charles Webedmon | 15/09/62 Babanki Tungo | M | TA | 352812-V | B1/445 | B1/450 | 1/7/1985 | 2017 | CAP Konye |
|  | Daniel Mamme Nkwelle | 10/01/66 – Ehom Tombel | M | TA | 365296-J | B1/335 | B1/335 | 1/7/1986 | 2021 | CAP Kokobuma Konye |
|  | Cabinda nee Basebang Jane | 22-03-64 Bamessing | F | TPA | 372268-N | B2575 | B2/595 | 19-06-87 | 2019 | Ass. coord PIAJA CAP Ikiliwindi konye |
|  | Moufor Bernabeh | 16/01/1962 Santa | M | TPA | 509853-Y | B2/595 | B2/595 | 1986 | 2016 | ZEW |
|  | Njozing Pauline Ndonge | 25/02/62 Muyuka | F | S/A | 361885- B | Cat 6/9 |  | 1/7/1984 | 2012 | Director CEAC Mbakwa SUPE |
|  | Moffo Barnabe | 15-01-62 Santa Akum | M | TPA | 509853-Y | B2 | 595 | 21/07/86 | 2016 | ZEW Matondo |

Table: Summary Data of staff in the Division

| Service | I.A | IPA | ITA | IPTA | IPGR | ITGR | TSA | TSGR | TPA | TA | ATA | ATGR | C.O | S.A | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Divisional Delegation | 3 | 0 | 1 | 3 | 1 | 1 | 0 | 1 | 1 | 4 | 0 | 1 | 2 | 2 | 20 |
| SDDARD Kumba I | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 04 |
| SDARD Kumba II | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 01 | 0 | 0 | 0 | 0 | 1 | 02 |
| SDDARD Kumba III | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 01 | 2 | 0 | 0 | 1 | 0 | 03 |
| SDDARD Mbonge | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 2 | 3 | 5 | 0 | 0 | 1 | 15 |
| SDDARD Konye | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 05 | 4 | 0 | 0 | 0 | 0 | 09 |
| CEAC Mbonge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 01 |
| CEAC Mbakwa Supe | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 01 |
| CEAC Kotto Barombi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 00 |
| Total | 03 |  | 03 | 03 | 01 | 01 | 02 | 01 | 12 | 14 | 07 | 01 | 05 | 04 | 56 |
| A.T.A : Agent Technique d’Agriculture A.T.G.R: Agent techniques du Génie Rural CB : Chief of Bureau | C.O: Contract Officer T.A: Technicien d’Agriculture DCS : Divisional Chief of Section | I.A: Ingénieur d’Agriculture S.A: State Agent or Agent de L’Etat T.S.A: Technicien Supérieur d’Agriculture |

Table : Vacant Post – Total No. = 17

| DIVISIONAL DELEGATION | SDDARD 1 | SDDARD 2 | SDDARD 3 | MBONGE | KONYE |
| --- | --- | --- | --- | --- | --- |
|  | Bureau for Agric Dvpt | Bureau for Agric Dvpt | Bureau for Agric Dvpt | Bureau for Agric Dvpt | Bureau for Agric Dvpt |
|  | Bureau for Rural Dvpt | Bureau for Rural Dvpt | Bureau for Rural Dvpt | Bureau for Rural Dvpt | Bureau for Rural Dvpt |
|  |  |  |  | Agric Post Big Ngwandi | Night watchman |
|  |  |  |  | Agric Post Pete Bakundu | Yard man |
| Total 0 | 02 | 02 | 02 | 04 | 04 |

  - FINANCE

    - ALLOCATION AND EXECUTION OF RUNNING CREDITS FOR 1st SEMESTER 2013.

| STRUCTURE:…DIVISIONAL DELEGATION MEME |  |
| --- | --- |
| VOTE HOLDER: RICHARD MOLUA |  |
| N° | OBJECTIVE | IMPUTATION | CREDIT ALLOCATED | AMOUNT EXECUTED | % LEVEL OF EXECUTION | OBSERVATIONS |
|  | ACH. FOURN. ET. ENT. BUR | 47304519256101 | 1 089 900 | 1 089 900 | 100% | GOOD |
|  | CARB. ET. LUB. VEH. AUTOMO | 47304519256121 | 1 499 850 | 1 499 850 | 100% | GOOD |
|  | INDEM DE MISSION INTER | 47304519256171 | 1 887 750 | 1 527 750 | 20% | GOOD |
|  | INTER-DEPAR/MISSION | 47304519256171 | 450 000 | 450 000 | 100% | GOOD |
|  | VEHICLE REPAIRS AND FUEL (PNVRA) | 45304519251661 | 765 000 | 765 000 | 100% | insufficient |
|  | MISSION ORDER (PNVRA) | 473045192561711 | 1 620 000 | 1 620 000 | 100% | insufficient |
|  | STATIONERIES (PNVRA) | 473045192561011 | 450 000 | 450 000 | 100% | Insufficient |

    - STRUCTURE: SUB-DIVISIONAL DELEGATION KUMBA I AND ITS AGRICULTURAL POSTS

| Structure | Vote Holder | Budget Head | Imputation | Credit allocated | Amount spent | % level of execution | Observation(s) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| SDDARD KUMBA I | NJUKANG NEE MBETCHA GRACE | MISSION ORDER | 47304719306171 | 630,000 | 630,000 | 100% |  |
|  |  | STATIONERIES | 47304719306100 | 702,000 | 702,000 | 100% |  |
|  |  | FUEL | 47304719306121 | 540 000 | 540 000 | 100% |  |
| AP KAKE II | MBETCHA GRACE | MISSION ORDER | 473057193061712 | 315 000 | 50% | 100% |  |
|  |  | SMALLL OFFICE EQUIPMENT | 473057193061002 | 323 100 | 50% | 100% |  |
|  |  | FUEL | 43057193061212 | 315 000 | 50% | 100% |  |

    - Structure: SUB-DIVISIONAL DELEGATION KUMBA II AND ITS AGRICULTURAL POSTS

| Structure | Vote Holder | Budget Head | Imputation | Credit allocated | Amount spent | % level of execution | Observation(s) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| SDDARD KUMBA II | KEBOU JEAN | MISSION ORDER | 47304719306171 | 630,000 | 315,000 | 100% |  |
|  |  | STATIONERIES | 47304719306100 | 702,000 | 702,000 | 100% |  |
|  |  | FUEL | 47304719306121 | 540 000 | 540 000 | 100% |  |
| AP KOSALLA | KEBOU JEAN | MISSION ORDER | 4673057193061713 | 315 000 | 315 000 | 100% |  |
|  |  | OFFICE EQUIPMENT | 473057193061003 | 323 100 | 100% | 100% |  |
|  |  | FUEL | 473057193061213 | 315 000 | 100% | 100% |  |

    - STRUCTURE: SUB-DIVISIONAL DELEGATION KUMBA III AND ITS AGRICULTURAL POSTS

| Structure | Vote Holder | Budget Head | Imputation | Credit allocated | Amount spent | % level of execution | Observation(s) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| SDDARD KUMBA III | KOME NJALLA LEOPOLD | MISSION ORDER | 47304719276171 | 630,000 | 630,000 | 100% | Not sufficient |
|  |  | STATIONERIES | 47304719276100 | 702,000 | 702,000 | 100% | Not sufficient |
|  |  | FUEL | 47304719276121 | 540 000 | 540 000 | 100% |  |
| AP MALENDE | Dubila Florence | MISSION ORDER | 473057193061715 | 630 000 | 630 000 | 100% | Not sufficient |
|  |  | STATIONERIES | 473057193061005 | 446 100 | 446 100 | 100% | Not sufficient1 |
|  |  | FUEL | 473057193061215 | 630 000 | 630 000 | 100% |  |

    - STRUCTURE:  MBONGE SUB DIVISION AND ITS AGRICULTURAL POSTS

| SRTRUCTURE | VOTE HOLDER | OBJECTIVE | BUDGETARY IMPUTATION | CREDIT ALLOCATED | AMOUNT EXECUTED | % LEVEL OF EXECUTION | OBSERVATIONS |
| --- | --- | --- | --- | --- | --- | --- | --- |
| SDDARD MBONGE | NDIP WILSON DEFANG | STATIONERIES | 47304719286100 | 351,900 | 351,900 | 100% | Not sufficient with respect to workload |
|  |  | FUEL | 47304719286121 | 810,000 | 810,000 |  |  |
|  |  | MISSION ORDER | 46304719306171 | 315,000 | 315,000 |  |  |
| AGRIC POST EDIKI. | NEBA SAMUEL | STATIONERIES | 463057193061212 | 323,100 | 323,100 | 100% | Not sufficient with respect to workload |
|  |  | FUEL | 463057193061002 | 315 000 | 315 000 |  |  |
|  |  | MISSION ORDER | 463057193061213 | 315 000 | 315 000 |  |  |
| AP BANGA BAKUNDU | SDDARD MBONGE | STATIONERIES | 473057192861004 | 323,100 | 323,100 | 100% | Not sufficient with respect to workload |
|  |  | FUEL | 473057192861214 | 315 000 | 315 000 |  |  |
|  |  | MISSION ORDER | 473057192861714 | 315 000 | 315 000 |  |  |
| AP EKOMBE | SDDARD MBONGE | STATIONERIES | 473057192861005 | 323,100 | 323,100 | 100% | Not sufficient with respect to workload |
|  |  | FUEL | 473057192861215 | 315 000 | 315 000 |  |  |
|  |  | MISSION ORDER | 473057192861715 | 315 000 | 315 000 |  |  |
| AP KWAKWA | ZAMBOU GABRIEL | STATIONERIES | 473057192861003 | 323,100 | 323,100 | 100% | Not sufficient with respect to workload |
|  |  | FUEL | 473057192861213 | 315 000 | 315 000 |  |  |
|  |  | MISSION ORDER | 473057192861713 | 315 000 | 315 000 |  |  |
| AP BAI GRASS | SDDARD | STATIONERIES | 473057192861001 | 323,100 | 323,100 | 100% | Not sufficient with respect to workload |
|  |  | FUEL | 473057192861211 | 315 000 | 315 000 |  |  |
|  |  | MISSION ORDER | 473057192861711 | 315 000 | 315 000 |  |  |
| AP BAI PANYA | MME FON FLORENCE | STATIONERIES | 473057192861002 | 323,100 | 323,100 | 100% | Not sufficient with respect to workload |
|  |  | FUEL | 473057192861212 | 315 000 | 315 000 |  |  |
|  |  | MISSION ORDER | 473057192861712 | 315 000 | 315 000 |  |  |
| AP MUNDONGO | NKENG MICHEAL | STATIONERIES | 473057192861000 | 323,100 | 323,100 | 100% | Not sufficient with respect to workload |
|  |  | FUEL | 473057192861210 | 315 000 | 315 000 |  |  |
|  |  | MISSION ORDER | 473057192861710 | 315 000 | 315 000 |  |  |
| AGRIC POST BUTU | RDARD Buea | STATIONERIES | 473057192861000 | 323,100 | 323,100 | 100% |  |
|  |  | FUEL | 473057192861210 | 315 000 | 315 000 | 100% |  |
|  |  | MISSION ORDER | 473057192861710 | 315 000 | 315 000 | 100% |  |
| AP PETE |  | NIL | NIL | NIL | NIL | NIL | NO RUNNING CREDIT |
| AP KOTTO BAROMBI |  | NIL | NIL | NIL | NIL | NIL | NO RUNNING CREDIT |
| AP BIG NGWANDI |  | NIL | NIL | NIL | NIL | NIL | NO RUNNING CREDIT |
| AP BIG BEKONDO |  | NIL | NIL | NIL | NIL | NIL | NO RUNNING CREDIT |
| CEAC MBONGE | ETONE LOVELINE | STATIONERIES |  | 5400.000 | 5400.000 | 100% | Not sufficient with respect to workload |
|  |  | FUEL |  | 3600.000 | 3600.000 |  |  |
|  |  | TRAINING |  | 900.000 | 900.000 |  |  |
| CEAC BIG BUTU | DDARD/SDDARD | STATIONERIES |  | NIL | NIL | NIL |  |
|  |  | FUEL |  | NIL | NIL | NIL |  |
|  |  | TRAINING |  | 900 000 | 900 000 | 100% |  |

2.2.6   STRUCTURE:  KONYE SUB DIVISION AND ITS AGRICULTURAL POSTS

| SRTRUCTURE | VOTE HOLDER | OBJECTIVE | BUDGETARY IMPUTATION | CREDIT ALLOCATED | AMOUNT EXECUTED | % LEVEL OF EXECUTION | OBSERVATIONS |
| --- | --- | --- | --- | --- | --- | --- | --- |
| SDDARD KONYE | NGEH HUMPHREY | STATIONERIES | 47304719286100 | 703,800 | 703,800 | 100% | Not sufficient with respect to workload |
|  |  | FUEL | 47304719286121 | 5400 000 | 5400 000 |  |  |
|  |  | MISSION ORDER | 46304719306171 | 630,000 | 630,000 |  |  |
| AGRIC POST KONYE | VISAS CHARLES | STATIONERIES | 463057193061212 | 323,100 | 323,100 | 100% | Not sufficient with respect to workload |
|  |  | FUEL | 463057193061002 | 315 000 | 315 000 |  |  |
|  |  | MISSION ORDER | 463057193061213 | 315 000 | 315 000 |  |  |
| AP IKILIWINDI | CABINDA JANE | STATIONERIES | 473057192861004 | 323,100 | 323,100 | 100% | Not sufficient with respect to workload |
|  |  | FUEL | 473057192861214 | 315 000 | 315 000 |  |  |
|  |  | MISSION ORDER | 473057192861714 | 315 000 | 315 000 |  |  |
| AP MATOH | NZIFACK JOHN | STATIONERIES | 473057192861005 | 323,100 | 323,100 | 100% | Not sufficient with respect to workload |
|  |  | FUEL | 473057192861215 | 315 000 | 315 000 |  |  |
|  |  | MISSION ORDER | 473057192861715 | 315 000 | 315 000 |  |  |
| AP MATONDOII | NGEY HUMPHREY | STATIONERIES | 473057192861003 | 323,100 | 323,100 | 100% | Not sufficient with respect to workload |
|  |  | FUEL | 473057192861213 | 315 000 | 315 000 |  |  |
|  |  | MISSION ORDER | 473057192861713 | 315 000 | 315 000 |  |  |
| AP KURUME | MBAH FELIX ACHA | STATIONERIES | 473057192861001 | 323,100 | 323,100 | 100% | Not sufficient with respect to workload |
|  |  | FUEL | 473057192861211 | 315 000 | 315 000 |  |  |
|  |  | MISSION ORDER | 473057192861711 | 315 000 | 315 000 |  |  |
| AP LOBANGE | TEZOH LAWRENCE | STATIONERIES | 473057192861002 | 323,100 | 323,100 | 100% | Not sufficient with respect to workload |
|  |  | FUEL | 473057192861212 | 315 000 | 315 000 |  |  |
|  |  | MISSION ORDER | 473057192861712 | 315 000 | 315 000 |  |  |
| AP KOKOBUMA | DANIEL MAMME NKWELLE | STATIONERIES | 473057192861000 | 323,100 | 323,100 | 100% | Not sufficient with respect to workload |
|  |  | FUEL | 473057192861210 | 315 000 | 315 000 |  |  |
|  |  | MISSION ORDER | 473057192861710 | 315 000 | 315 000 |  |  |
| AGRIC POST KONYE. | VISAS CHARLES | STATIONERIES | 473057192861006 | 323,100 | 323,100 | 100% | Not sufficient with respect to workload |
|  |  | FUEL | 473057192861216 | 315 000 | 315 000 |  |  |
|  |  | MISSION ORDER | 473057192861716 | 315 000 | 315 000 |  |  |
| CEAC MBAKWA SUPE | NJOZING PAULNE | STATIONERIES |  | 5400.000 | 5400.000 | 100% | Not sufficient with respect to workload |
|  |  | FUEL |  | 3600.000 | 3600.000 |  |  |
|  |  | TRAINING |  | 900.000 | 900.000 |  |  |

    - PUBLIC INVESTMENT BUDGET 2013

| N° | OBJECTIVE | IMPUTATION | CREDIT ALLOCATED | AMOUNT EXECUTED | % LEVEL OF EXECUTION | OBSERVATIONS |
| --- | --- | --- | --- | --- | --- | --- |
|  | RENOVATION OF DELEGATION | 47304519252220A | 4,500,000 | 4,500,000 | 100% | Office Renovated |
|  | RENOVATION OF SDDARD I | - | 3,500,000 | 3,500,00 | 100% | Office Renovated |
|  | EQUIPMENT OF SDDARD I | - | 10,000,000 | - | - | Credit card have not been seen |
|  | PAIJA IKILIWINDI | 46304519252842 | 30,000,000 | 21 000 000 | 50% | No more Imprest. All construction sent to MINMAP |
|  | CONSTRUCTION OF SDDARD KONYE | 47304519252220 | 25,000,000 | 25 000 000 | 95% | Contract awarded |

    - YOUNG FARMER SETTLEMENT PROGRAMME – IKILIWINDI

VOTE HOLDER: RICHARD MOLUA (DDARD MEME)

EXPENDITURE AUTORISATION FOR 2013

| No. | TASK | UNITES PHYSIQUES | SUB-TASK | QTE | UNIT COST (FCFA) | TOTAL COST (FCFA) | Technical Realisation | Financial Realisation | OBSERVATION |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 01 | Construction an equipped borehole | Capital transfer for works |  | 01 | 9,000,000 | 9,000,000 | 90% | 0% |  |
| 02 | Construction of a Warehouse |  |  | 01 | 11,000,000 | 11,000,000 | 60% | 0% |  |
| 03 | Support to the construction of a house |  |  | 01 | 4,500,000 | 4,500,000 | 100% | 0% |  |
|  | Total 1 |  |  |  |  | 24,500,000 |  |  |  |
| 04 | Monitoring and support to young farmers | Capital transfer for studies | Payment of output (performance) allowance for Site Coordinator | 12 | 150,000 FCFA/month | 1,800,000 | 100% | 0% |  |
|  |  |  | Payment for output allowance for support staff on site | 12 | 100,000 FCFA/month | 1,200,000 | 100% | 0% |  |
|  |  |  | Purchase of fuel and lubricant | 02 Sem. | 500,000 | 1,000,000 | 100% | 0% |  |
|  |  |  | Purchase of office stationeries | 01 | 500,000 | 500,000 | 100% | 0% |  |
|  |  |  | Follow-up of activities on site | 02 Sem. | 500,000 | 1,000,000 | 100% | 0% |  |
|  | Total 2 |  |  |  |  | 5,500,000 |  |  |  |
|  | TOTAL GENERAL |  |  |  |  | 30,000,000 |  |  |  |

  - INFRASTRUCTURE AND EQUIPMENT

    - BUILDINGS

| No | Delegation/Structure | Number of Sub Units | Buildings | State of Building | Remarks |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Constructed | Not constructed |  |  |
|  | DDARD | 07 | 05 | 02 | Good |  |
|  | SDDARD KUMBA I | 01 | 01 |  | fair | Vandalized in 2009. Need renovation |
|  | SDDARD MBONGE | 01 | 01 |  | fair | Rehabilitation done with BIP 2012 at the sum of 2400 000 FCFA |
|  | SDDARD KONYE | 01 | 01 |  | Good | Constructed by BIP 2013 |
|  | AGRIC POST, KWAKWA | 01 | 01 |  | Fair | Need repairs |
|  | AGRIC POST, KOTTO BAROMBI | 01 | 01 |  | Good | Constructed in 2011 |
|  | AGRIC POST, BAI GRASS | 01 | 01 |  | Bad | Need repairs |
|  | AGRIC POST, EKOMBE | 00 | 00 | 0 | 0 | Not yet constructed |
|  | CEAC MBAKWA SUPE | 01 | 01 |  | Good | Constructed in 2010 |
|  | AGRIC POST, PETE BAKUNDU | 00 | 00 | 0 | 0 | Not yet constructed |

The following structures have not been constructed:

| SDDARD (02): | KUMBA II, KUMBA III |
| --- | --- |
| AGRIC POSTS (17): | AGRIC POSTS EDIKI, BANGA BAKUNDU, BOA BAKUNDU, MUNDONGO, BIG NWANDI, BIG BEKONDO, PETE BAKUNDU, KOTTO BAROMBI, BIG BUTU, BAI GRASS, EKOMBE, KONYE, KURUME, LOBANGE, IKILIWINDI, MATOH, KOKOBUMA |
| CEACs (03): | MBONGE, KOTTO BAROMBI AND BIG BUTU |

      - EQUIPMENT

Vehicles and Motorcycles

|  | Mark | Reg. No | Chassis N° | Year in circulation | Source programme | User | Present state |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Mitsubishi | SW 3649 C |  | 1996 |  | Divisional Delegate | bad |
|  | Nissan | CA 3872 C |  | 2008 |  | DDARD | Manageable |
|  | Mitsubishi | CE 963 CL |  | 2010 |  | Tekombo ( CTU ACEFA) | Good |
|  |  | CA 3399 C | 103670 | 2008 |  | Tekombo JEAN CLAUDE | Fair |
|  | YAMAHA 100 | CE 4358 W | --- | 2004 |  | Kuefouet Benoit | Manageable |
|  | YAMAHA 100 | CEMT 832 BM | 3HA177321 | 2011 | ACEFA | Mbecha Grace | Good |
|  | YAMAHA 100 |  |  | 2011 | ACEFA | Keubou Jean | Good |
|  | YAMAHA AG100 | CE 836 BM | 3HA-177389 | MAR 2011 | ACEFA | KOME LEOPOLD (CGP) | Good |
|  | JAILING | CA 5057 C |  | AUG 2009 | NAERP | ZEW MALENDE | Good |
|  |  | IT 08471 RC |  | 1998 |  | Dubila Florence |  |
|  | YAMAHA AG 100 | CA 33342 C | 3HHA421261 | 2007 |  | Ndip Wison | Good |
|  | JAILING 125 | CA 5059 C |  | 2009 |  | Nzambo Gabriel | Manageable |
|  | YAMAHA AG 100 | CEMT 819 BM | 3HA177274 | 2011 | ACEFA | NKENG MICHEAL | Good |
|  | Yamaha AG 100 | CEMT 811BN | 3HA177368 | 2011 |  | Neba Samuel | good |
|  | AG YAMAHA 100 |  |  | 2011 |  | FON FLORENCE | good |
|  | JAILING 125 |  |  | 2011 |  | NGU TAMO | good |
|  | JAILING 125 |  |  | 2009 |  | AKWO MICHEAL | Manageable |
|  | JAILING 125 |  |  | 2011 |  | NENKEP FABIAN | good |
|  | JY 2 | MT CA 6932 C |  | 2011 |  | VINCENT FAWO | good |
|  | YAMAHA AG100 | CA 6069 CK TM | 103670 | 2010 |  | Etone Loveline | good |
|  | YAMAHA DT125 | SWMT 501 AH | DE02X038465 | AUG 2008 | RUMPI | NGEH HUMPHREY NGOLE | OLD |
|  | YAMAHA AG100 | CA 3332 C | 3HA-142128 | MAR 2008 | NAERP | NGEH HUMPHREY NGOLE | OLD |
|  | YAMAHA AG100 | CEMT 814 BM | 3HA-177398 | MAR 2011 | ACEFA | CABINDA NEE BASEBENG | GOOD |
|  | YAMAHA AG100 | CEMT 795 BM | 3HA-177402 | MAR 2011 | ACEFA | NZIFACK JOHN | GOOD |
|  | YAMAHA AG100 | CEMT 796 BM | 3HA-177277 | MAR 2011 | ACEFA | MBAH FELIX | GOOD |
|  | YAMAHA DT125 | CEMT 833 BM | 3HA-177337 | MAR 2011 | ACEFA | VISAS CHARLES | GOOD |
|  | YAMAHA DT125 | SWMT 451 AH | DE-084036216 | AUG 2008 | RUMPI | TEZOH LAWRENCE | GOOD |
|  | LIFANG 150 | CH-003381 | LT3PCK000AB003381 | JUN 2010 | GIZ-FBS | TEZOH LAWRENCE | GOOD |
|  | YAMAHA AG100 | CA 0406 RC | 3HA-0141409 | MAR 2008 | NAERP | MAMME DANIEL | POOR |
|  |  | CE 4352 W |  | 2004 |  | Asonkeng Raymond | Good |
|  | AG YAMAHA 100 | CEMT 814 BM | 2HA177398 | 2011 | ACEFA | Basebang Jane | Good |
|  | JAILING 125 | CA-5057-C |  | 08/2009 | PNVRA | GREGORY EZEAH | Good |
|  | LIFANG | CH003381 | LF3PCK000-AB003381 | 2010 | GIZ/FBS |  | Good |
|  | BOATAIN | CA 3719 C |  | 2008 |  | Moffo Barnarbe | Bad |
|  |  |  |  | 2011 | ACEFA | KAMGWA RICHARD | Good |

      - COMPUTER EQUIPMENT

| Category | Mark | Source | Date put into use | Present state | User | Age in Years |
| --- | --- | --- | --- | --- | --- | --- |
| Computer | RITEK PENTUM 4 | RUMPI | 2008 | Bad | DCS STATISTIC /SURVEYS | 04 |
| PRINTER | HP JET 5600 |  | 2008 | Bad |  | 04 |
| BACK UP | INTEX V 1050 |  | 2008 | Bad |  | 04 |
| CITY PHONE | HUAWEI |  | 2011 | Good |  | 01 |
| RAIN GAGE | 40mm/m2 |  | 2012 | Good |  | 03 months |
| Scale Balance | Balance25kg/100kg |  | 2006 | Good |  | 08 |
| Computer/ CPU | HP 8CM/20 INCH LED BACKLIT | AMO | 2012 |  | DDARD |  |
| Printer | Hp office jet | AMO | 2011 | Good | DDARD |  |
| Printer | Canon –K-D 440 | AMO | 2012 | Good | DDARD |  |
| Printer | HP LASSER JET P1102 | AMO | 2102 | Good | DDARD |  |
| Back up | E.T.N Nova AVR 635 | AMO | 2012 |  |  |  |
| Computer system | HP / INCH | RUMPI | 2008 | Monitor bad | CD/LD |  |
| Printer | HP LASSER JET P3005 | RUMPI | 2008 | FAIR | CD/LD |  |
| Back up | MGE Nova AVR1250 | RUMPI | 2008 | FAIR | CD/LD |  |
| COPMPUTER/CPU | HP 8CM/20 INCH LED BACKLIT | AMO | 2012 | Good | SDDARD KUMBA I |  |
| Pinter | Hp office jet |  |  |  |  |  |

The chapter the follows presents the realizations for the 2013 financial year in 4 major intervention programmes:

- Improve productivity and competitiveness in the agricultural sector

- Modernisation  of rural infrastructure and production

- Institutional development and capacity building

- Sustainable management of natural resources

TECHNICAL ACHIVEMENT FOR 2013

| Sector | PRODUCTION AND MARKETING |
| --- | --- |
| Objective of the Ministry | To make Cameroon an agricultural stronghold in the sub-region where agriculture is an engine of the national economy ensuring food security of the population in line with sustainable development and protection of the environment. |
| Intervention programme | Objectives | Priority action | Activities (as in Meme road map) | Baseline data | Expected results | Results indicators | Realisation (%) | observations |
| IMPROVE PRODUCTIVITY AND COMPETITIVENESS IN THE AGRICULTURAL SECTOR | Improve agricultural production and productivity | Improve farmers access to agricultural inputs | Creation and/or rehabilitation of multiplication farms | 01 | Increased availability of improved planting materials 01 multiplication farm rehabilitated | 05 Ha of cocoa created 10,000 cocoa pods, | 05 Ha of cocoa clonal seed garden created at CCSP 6 propagators of 12 compartments each including canopy and covering constructed at CCSP 0.5Ha cassava and 0.5Ha plantain multiplication plots created in KI |  |
|  |  |  | Establishment of nurseries for main crops | 12 nurseries for cocoa, 02 plantains nurseries 288,030 cocoa seedlings, 65000 plantlets, | Increased availability of improved planting materials Increased production of main food and cash crops | 12 cocoa, 01 Robusta coffee, 02 plantain nurseries 600000 cocoa seedlings, 40000 plantain plantlets | 13 cocoa nurseries established under FODECC (108.3%); 02 R.coffee nursery of capacity 10000 and 25000 established by KONAFCOOP. 2500/10000 cuttings surviving in the 1st nursery and in the 2nd bags filled but no cutting planted | Seedlings did not satisfy the requests. |
|  |  |  | Acquire and distribute improved planting materials (seeds) | 5.2 tons maize seeds (66 tons); 150kg foundation maize | Improved seeds are acquired and distributed Increased surface area under cultivation and increased production of perennial and annual crops | 100000 coffee cuttings, 7.5 tons seed maize (990 tons, 150000 cassava cuttings, 5000 plantain suckers, 990 tons of maize produced and 345 tons of cassava produced | 340 880 coffee cuttings, 99 340 and 340 citrus plants distributed by CCSP Kumba 469,733 cocoa seedlings distributed to 395 farmers. Approx 391Ha planted. 6850 kgs of improved maize seeds distributed (91.3%) 111 500 cassava cuttings distributed 875 suckers, harvested and distributed from multiplication plot K1 4350 oil palm seeds distributed to 22 farmers | Seeds supplied by SOWEDA at a subsidized price of 300F/Kg Sources include 1500 from IITA/GIZ, 10 000 FROM K1 and 100000 from Yaounde. The cuttings from Yaounde arrived in very late (Dec). Most were dry or rotten Each beneficiary paid 75000 FCFA for 150 seedlings |
|  |  |  | Acquire and distribute quality fertilizers to farmers | 25 tons of fertilizer (Presidents gift) | Fertilizers are acquired and distributed Increased in production of main annual and perennial crops | 55 tons mineral fertilizer and 13.5 tons of organic fertilizer for cocoa and coffee distributed to 24 cooperatives | 55 tons mineral fertilizer (1100 bags) and 13.5 (270 bags) tons of organic fertilizer distributed to 24 POs (100%) | 1,200,000 FCFA already deposited as revolving loan by 12 POs |
|  |  | Protection of major annual and perennial crops | Acquire and distribute pesticides and spray equipments Acquire necessary logistics (materials) for phyto-treatment Train phyto-brigade advisers and technicians | 0 | Pesticides and spray equipment purchased and distributed At least 5% of cocoa fields treated Logistics (Materials) for treatment are purchased Training workshops organised | Quantity of pesticide and spray equipment distributed; No of ha of crops treated; Reception forms for pesticides and spray equipment No of training workshops | 22 250 sachets contact fungicide (Golden Blue) and 43050 sachets of systemic fungicide (Forum) distributed 48 Cooperatives 07 atomisers, 09 knapsack sprayers and 23 protective kits distributed | Fungicide and equipment distributed under the framework of PALAF 2C |
|  | Improve competitiveness among farmers | Exhibit best farm product / produce | Prepare and participate in Regional APS | 10 farmers participate; 30 prizes won | Increased awareness among farmers Increased quantity and quality of farm produce & products presented | 20 farmers participate 60 prizes are won | 35 farmers participated winning 53 prizes recording an increase of___. 13 (1st prize); 14 (2nd prize); 13 (3rd prize); 9 (4th prize); 3 (5th prize); 1 (6th prize) |  |

| Intervention programme | Objectives | Priority action | Activities (as in Meme road map) | Baseline data | Expected results | Results indicators | Realisation | Observation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MODERNISATION OF RURAL INFRASTRUCTURE AND PRODUCTION | Improve farmers access to financing | Operation of an agricultural Bank | Recover 1st FIMAC generation loans | 0 | Increased rate of reimbursement | 200,000 FCFA recovered | No amount recovered (0%) |  |
|  |  |  | Follow-up the activities of 12 village barns and ensure their sustainability | 12 banks, 1431 members, savings : 47,554,000 FCFA and loans awarded: 18,744,000 FCFA | Increased in membership and volume of banking transactions | 12 banks, 2000 members, 60 millions saved and 25 million loaned out | Statistics for the 10 barns Total membership = 1550 Volume of savings = 40,286,870 F Volume of loans = 32,311,000 F | These figures are those of first semester. MIFED staff still to provide an update |
|  |  |  | Establish network amongst village banks | 0 | Transactions established among village banks | At least 5 banks in network | 0% | - |
|  |  | Financial support to PO micro-projects | Provide small loans to seed producers from the S.W. seed fund | 0 | Increased awareness on existence of seed fund Loans granted to seed producers | 03 seed producers receive loans and enter production | 0% | Manual on procedure not yet made available |
|  |  |  | Provide financial subsidies or grants to sustainable IGA | 48 subsidies granted to 48 POs | Project identified and selected Project financed | 55 micro-projects financed | 0% |  |
|  | Improvement in rural infrastructure and agricultural production | Des enclavement of agricultural production basins | Open and/or rehabilitate farm-to-market roads | 28 km of farm road rehabilitated and 01 small bridge constructed | Some major farm to market roads rehabilitated | 30 km of roads maintained | 10 out of 17km Dikome – Madie road rehabilitated (39%). 4km road at Banga mile 40-Moungo road rehabilitated | See Annex for works breakdown |
|  |  |  | Construct and/or rehabilitate culverts on farm roads | 0 | Culverts are constructed on farm results | 02 culverts constructed | - |  |
|  | Improvement in staff working environment | Constructing and Equipping services | Construct, rehabilitate and equip services | 01 SDDARD rehabilitated, DDARD and 01 AP equipped | DDARD and SDDARD K1 renovated SDDARD Konye constructed CEAC Mbonge equipped | 02 services rehabilitated and 01 constructed | Construction of SDDARD Konye (95%) Rehabilitation of DDARD (100%) Rehabilitation of SDDARD Kumba 1 (100%) Rehabilitation of Agric Post Bai grass (100%) | Credit card for purchase of equipment for SDDARD I not seen |
|  | Improve farmers access to agricultural equipments and infrastructures | Promote quality transformation storage and preservation of farm produce Increased access to markets | Support acquisition / installation or construction of small transformation units (ACEFA) | 13 units installed | Project selection Purchase, installation and functioning of unit Increase in value added and price of farm produce | 18 units installed | - | - |
|  |  |  | Support the purchase or construction of storage facilities (ACEFA) | 01 storage facility constructed | Project selection Warehouse and cold stores constructed and functioning | 02 units constructed | - | - |
|  |  |  | Construction of rural markets | 01 rural market constructed | Site selected and prepared Markets constructed | 02 markets constructed | - | - |
|  | Improve living conditions in rural areas | Promote use of quality drinking water sources | Construction /rehabilitation extension of village pipe borne water |  | Pipe borne water system Improve the living standards of the farmers in the Region | 03 water supply schemes rehabilitated | 22 point of use filters (bio-sand filters) constructed at the Lake Barombi Mbo water supply system | Project is funded and realised by students from the University of Dayton – the ETHOS |
|  |  | Promote participatory development | Construction / rehabilitation of community halls | 01 Community halls constructed | Site selected and prepared Halls constructed | 02 halls constructed | - | - |

| Intervention programme | Objectives | Priority action | Activities (as in Meme road map) | Baseline data | Expected results | Results indicators | Realisation | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CAPACITY BUILDING AND INSTITUTIONAL DEVELOPMENT | Promote entrepreneurship of youths in agriculture | Train and integrate youths in the agricultural domain | Support the installation of youths in the Ikiliwindi production site | 19 youths supported | Activities planned 19 youths supported Infrastructures for 2012 completed Site improved and farms developed | 19 youths supported 4 houses and 3km road (BIP 2012) constructed. 01 living house, 01 ware house and 01 borehole (BIP 2013) constructed | 12500 (50%) of improved cocoa and 1550 (78%) oil palm seedlings distributed Construction of 4 apartments (85%) Rehabilitation of 05km farm road (0%) Construction of house (100%) Construction borehole (90%) Construction warehouse (60%) | More than 61% of the young farmers are non-resident. Their farms are dirty. Contracts awarded very late. Poor nature of roads disturbed take off |
|  | To equip MINADER with planning and monitoring tools for some strategic sub-sector programmes | Relaunch and promote the cooperative movement | Organise sensitisation and orientation workshops on cooperative societies on the new dispensations, (distribute copies of the OHADA Uniform Act) Structure cooperative societies according to crop enterprise (sub-sectors) Build capacity of cooperative society members in administrative management and accounting | 0 | Cooperatives understand and implement the OHADA Law; The guide for the drafting of the status of Cooperative Societies is developed Staff concerned are trained on the use of the Act and coding of Cooperatives Cooperative societies have been structured according to sub-sectors Members of Cooperative Societies are trained in Administrative Management and accounting | The different workshop reports; the guide, the cooperative register | 29 Cooperatives under SOWEFCU restructured in compliance with OHADA uniform Act SOWEFCU restructured with a 13 member Board of Directors 01 workshop organised for 10 Cooperatives by SOWEDA | Reports are being collected from some cooperatives to determine their functionality |
|  |  | Carry out specific surveys on certain strategic annual and perennial crops | Train frontline staff on data collection and analysis | 01 training | Training sessions organised Increased capacity of staff in the data collection and treatment | 03 trainings workshop carried out Report on training | 01 workshop on annual agric surveys organized for 7 staffs (05 enumerators, 01 controller) | This workshop was for 2012. Results on survey awaited from DESA Yaounde |
|  |  |  | Collect production statistic and prices for major crops (MIS) | 02 | Production statistics and market prices collected, analysed and reported | 14 statistical reports produced | 11 reports produced (see table) Crop Prd/t Av.U.P Cocoa 47723 805 Coffee 227 690 Oil palm 53808 660 Rubber 22144.9 595 Citrus 7784 Cassava 205937 55 D. Maize 14397 260 Plantains 146542 115 Banana 63130 80 Cocoyam 38896 200 Cocoa price lowest this year as compared to the past 4 years. Field data collected from 8 markets |
|  |  | Elaborate a development plan for small-holders rubber plantations | Carry out a survey of all small rubber holdings | 0 | 01 survey carried out List of small holders available | A report (data bank) for small holders | 01 survey exercise carried out and 200 small holders identified. 01 sensitisation on formation of cooperatives by small holder rubber farmers organised in K1, K3 and Mbonge sub-divisions | Workshops were precisely organised at the DDARD, Mukonje and Bombe |
|  | Promote ICPM skills for cocoa farmers and certification (FFS Prog.) | Training and certify cocoa farmers in FFS | Organise FFS sessions and Training of trainers | 824 producers trained | Increased capacity for 500 farmers in cocoa certification Increased capacity for 500 farmers in cocoa certification | 500 cocoa farmers trained and certified in 29 FFS | 101 FFS created; 2523 farmers admitted and 2155 graduate |  |
|  | Promote agric business management (FBS Prog.) | Promote Farmer Business School | Training of cocoa farmers to develop entrepreneurial skills in cocoa production | 450 farmers trained | Increased capacity of staff and farmers in production of quality cocoa Increased capacity of staff and farmers in production of quality cocoa | 144 FBS trainings organised 4320 farmers trained 150 ZEWs trained | 07 FBS created and 188 farmers graduate 10 training session conducted and 281 farmers trained (245 men, 36 women) |  |
|  | Improve on the organisation and functioning of services (AMO/RDARD) | Capacity building of management staff | Organise training workshops | 03 workshops organised | Staffs are trained on specific themes Increased staff output (effectiveness and efficiency) | 05 workshops organised No of staff trained Workshop reports |  |  |
|  |  | Improve in personnel number | Re-deploy personnel to services vacant posts | 0 | 11 personnel are proposed for redeployment Staff are re-deployed | 11 staff are redeployed | 11 staff deployed according to competences to some vacant posts |  |
|  |  |  | Acquire and distribute vehicles, office and field equipment | 02 computers/ accessories provided and 02 rain gauges provided | Increased staff output Increased staff output | 01 vehicle and 04 desktop computers provided | 0% |  |
|  | Sustain the achievements of NAERP | Link research and extension | Build capacity of Producers Assoc. on identified themes | 129 /129 PAs comprising 2051 farmers (1073 males and 978 females) were trained on 18 different themes with an adoption rate of 87.3% | PAs are trained PAs are trained 2014 farming season prepared | 20 training sessions organised Report of training sessions | 81 training sessions carried out on 29 different topics involving 50 POs |  |
|  |  |  | Elaboration and follow-up of PPs for PAs | 129 /129 PPs developed and monitored for 18 speculations | PPs executed and monitored 162 PAs developed and monitored |  | 162 Production projects developed and monitored for 162 POs |  |
|  |  |  | Technical backstopping of extension staff | ZEWs = 1768 SS = 221 SMS = 162 DS = 98 | Increased capacity of NAERP staff in project implementation and monitoring | ZEWs = 2736 SS = 360 SMS = 288 DS = 96 | ZEWS = 1014/1622 SS = 231/396 SMS = 228/371 DS = 180/288 |  |
|  | Mastery of Advisory Support Device (ACEFA) | Review Counsellors and group performance on advisory support and project implementation | Organise sessions for LCG, DAG, CODAC, Counsellors, DPSC. Axis, Weekly Monitor beneficiary groups | 45 Management Committee trained on 4 themes (income and expenditure, bank account / book inventory) 287 session meetings held : LCG (196), DAG (1), CODAC (1), DPSC (1), DTU (11), AXIS (35) Weekly (42) 02 MINADER/MINEPIA project monitoring mission conducted | Sessions Meetings held; Increased performance by counsellors; 02 Field monitoring visits made and projects implemented with respect specification; | A total 322 Sessions meetings held LCG = 216 DAG = 02 CODAC = 04 DTU = 12 DPSC = 04 AXIS = 36 Weekly=48 02 field monitoring visits 05 training sessions held for LCGs on 4 topics | 126 group projects monitored carried out 15 control of effectiveness of groups and projects 97 diagnosis carried out 185 Local Committee and 01 CODAC, 01 ADOP meetings organized 05 projects received 02 field appraisal visit organized by DDARD and DDPIA | Many projects are incomplete as result of inadequate follow-up by CGPs, inadequate financing and mismanagement |
|  | Sustain the achievements of RUMPI Project and improvement in living conditions of rural population | Follow-up support to RUMPI sponsored projects | Follow – up use and impact of the RUMPI support to Local Development Initiative (SLDI) | - | Projects are sustained and impact felt among the population | At least 40 % of projects are self-perpetuating |  |  |
|  |  | Build /reinforce capacity of village institutions | Training and equipment of water management committee (WMC) | - | Improvement in the management of community water projects | No of WMC trained No equipped No created |  |  |
|  |  |  | Training and equipment of road maintenance committee (RMC) | - | Increased movement of persons and property | No of RMC trained No equipped No created |  |  |
|  |  |  | Follow-up implementation of village development plans | - | Village development plans are implemented | 10 projects from VDPs are implemented |  |  |
|  | Training for self-employment and Community Action | Building capacity for IGA and support to local entrepreneurship | Improvement on curriculum for CEACs |  |  | No of training sessions | A sensitisation brochure developed 35 sensitisation meetings on CEAC activities organised in 13 communities and 1023 member attend 06 workshops organised for 5 women and 6 youths groups | Total of 567 persons (158 men, 285 and123 youths women) attended |
|  |  |  | Organise training sessions for trainees |  |  | No of training sessions | 01 workshop organized for use of fertilizers and mycorrhiza on cocoa and coffee for 57 participants | Workshop organized by PAUEF2C |
|  | Ensure effective management of services (Improve effectiveness and efficiency) | Planning, organising, coordinating and controlling activities and resources | Organise /attend regular monthly meetings and field visits | 02 meetings | Increased staff output Enhanced collaboration with administration and other services | 14 meetings organised | 12 monthly review and planning meetings organized. 02 internal training sessions for carried out for planning and reporting | Meeting rotates in the sub-divisions Participants were DCS, SDDARDs and Support staffs |

| Intervention programme | Objectives | Priority action | Activities (as in Meme road map) | Baseline data | Expected results | Results indicators | Realisations | Observations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4. SUSTAINABLE MANAGEMENT OF NATURAL RESOURCES RELATED TO AGRICULTURE | Sustainably manage natural resources | Determining the fertility of arable land | Categorise the soils of Meme | - | Soils types are identified in the different production basins Soil fertility characteristic are determined | 01 study from secondary data carried out |  |  |
|  | Protection of water resources | Protection of water catchment areas | Protection of water catchment areas | - | Identification and appraisal of village water catchment areas Continuous supply of portable water | 10 catchment areas studied and recommendation for protections made |  |  |
|  | Valorise the water potential and maintain soil fertility | Promote irrigation agriculture (Farming) | Development and equipment of inland valleys | 05 sites equipped and zero developed | Sites are identified and studies carried out Sites are developed | 05 sites are developed | 02 POs (Final women Baduma, Dynamo farmers Matondo II) received each a subvention of 4800000 FCFA | Two groups that received subvention is still waiting for the service provider to buy the irrigation equipment and developed their sites. |
|  |  | Sustaining the fertility of arable land | Support the Development of Horticultural gardens | - | Site identified Site developed | At least 01 site is developed |  |  |

PARTNERS ACTIVITIES

| Partner | Planned activities | Realisation | Observations |
| --- | --- | --- | --- |
| ETHOS Students of the university of Dayton USA | Rehabilitation of Barombi Mbo water system and provision of point of used filters to house holds | Catchments rehabilitated 32 point of use filters completed and distributed to 32 house hold | Project was finance by the students and the Barombi Mbo community. |

| Partner | Planned action | realization | observations |
| --- | --- | --- | --- |
| CCSP Barombi kang | Production of maize seeds Production of cocoa pods Production of grafted citrus Production of coffee cuttings | 5 tons 99340 pods 340 plants 340880 cuttings | The demand of coffee cuttings is too low compared to cocoa pods |
| MUKETE ESTATE | Oil palm production Rubber production(cup lumps) Cocoa production | 168.89 tons of oil palm 428.02 tons 34.49 tons | The production of oil palm and rubber has reduce this year as compared to year (from 23.5% to13.5%) Cocoa production has increased by 111.5%. Reduction in rubber is as a result of ageing plantations and palm oil due to breakdown of the oil mill. |
| CDC MUKONJE | Estate rubber production Small holders rubber production | 809.6 tons 484.2 tons | Figure for the Estate has increased by 6.1%, while that of small holders has decreased by 51% compared to last year. This is because about 50 % of their production is sold to HEVECAM were payments are upfront . |
| CDC MBONGE | Estate rubber production Small holders rubber production | 850.38 tons 277.9 tons | Increment of 4.9% for estate and regression of 29.2% for small holders. |

|  | There are inadequate credits to run all the services. Very demotivating and a contributing factor to low output |
| --- | --- |
|  | Inadequate number of motorbikes resulting from frequent breakdowns. The JIALINGS are not adapted to field work |
|  | Inadequate basic working materials and equipment e.g. computers for all the technical services. Need for special credits to these services |
|  | No office space (buildings) for some Sub-Divisional Delegates and Chiefs of Agric Posts. This makes it difficult to monitor them their activities. Need for investment credits |
|  | Difficulties in getting production statistics (data) from LBAs despite several appeals |
|  | No weather station for the collection of climatic data at the level of the Delegation |
|  | No emergency stock of pesticide in stock to intervene in cases of emergency. There is need to equip the Phytobrigade with spray equipment and pesticides for rapid intervention |

ANNEXES

ANNEXE I: BIP projects for MINADER IN 2013

| No | Name of project | Sub Division | Amount (FCFA) | Observation |
| --- | --- | --- | --- | --- |
| 1 | Rehabilitation of DDARD Meme | Kumba I | 4,500,000 | Completed 100% |
| 2 | Construction of SDDARD Konye | Konye | 25,000,000 | 95% completed |
| 3 | Rehabilitation of SDDARD Kumba I | Kumba I | 3,500,000 | 100% completed |
| 4 | Rehabilitation of Bai Grass Agric Post | Mbonge | 2,000,000 | - |
| 5 | Construction of an apartment at Ikiliwindi young farmers site | Konye | 4,500,000 | 100% completed |
| 6 | Construction of Bore hole at Ikiliwindi young farmers site | Konye | 9,000,000 | - |
| 7 | Construction of warehouse at Ikiliwindi site | Konye | 11,000,000 | 5.00% |
| 8 | Rehabilitate farm to market roads Banga mile 40- moungo road (4km) | Mbonge | 28,000,000 | Mbonge council and MINTP carrying on with the works. |

Annex 2: Cocoa production form LBAs and some Producers organisations

| LBA/FO | Months | Total |
| --- | --- | --- |
|  | Jan. | Feb. | march | April | May | June | July | Aug | Sept | Oct | Nov | Dec |  |
| Achany & sons | 968.2 | 353.2 | 66.3 | 48.7 | 141.3 | 260.9 | 542.7 | 1308.4 | 1804.3 | 1001.2 | 1329.5 | NA | 7824.7 |
| Peter chi & son | 444.5 | 187 | 14.9 | 36 | 29.7 | 100 | 121.2 | 231.5 | 267.9 | 441.8 | 350.6 | NA | 1780.6 |
| Gongang Patrice | 0.7 | - | - | - | - | 187 | 77 | 530 | 1170 | 824 | 378 | NA | 3166.7 |
| Agro Research | 77.2 | 7.66 | 1.8 | - | 12.4 | 14 | 17 | 81 | 105 | 121 | 122 | NA | 559.06 |
| Telcar cocoa | 356.7 | 34.4 | 52.56 | 44.3 | 19.2 | 33.8 | 63.8 | 272.3 | 358.9 | 573.3 | 448.8 | NA | 2258 |
| CAMACO | 2673.2 | 1083 | 632.5 | 482.3 | 365.6 | 560 | 713.3 | 1733.4 | 2103.4 | 3016.6 | 4913.7 | NA | 18277 |
| Lake shore com. | 49 | - | - | - | - | 19.43 | 93 | 171 | 328 | 316 | 297 | NA | 1273.4 |
| UTI Cameroon | 13.5 | - | - | 3 | 5.54 | 10.4 | 16.1 | 105.9 | 371.5 | 359.2 | 300 | NA | 1185.1 |
| Okpu marketing | - | - | - | - | - | - | 12.4 | 20.4 | 38.5 | 42.2 | 42.6 | NA | 156.1 |
| Konafcoop | 49.3 | 14.5 | 6.64 | 5.7 | 8.3 | 17.1 | 19.5 | 90.6 | 133.14 | 148.2 | 70.2 | NA | 563.18 |
| ISEMEFCOOP | - | - | - | - | - | 2.5 | 3.2 | 10.8 | 15.1 | 23.7 | 13.4 | NA | 68.7 |
| BELLAFCOOP | 1.3 | 3 | 4.5 | 5.8 | 8.5 | 12.5 | 20 | 18 | 14 | 18 | 26 | NA | 131.6 |
| VIFCOOP | 3.5 | 4 | 3.2 | 4 | 6.4 | 7.4 | 9 | 11 | 24 | 35 | 48 | NA | 155.5 |
| KAFA CIG | 13.5 | 5 | - | - | 4.5 | 12 | 24 | 25 | 26 | 25 | 22.4 | NA | 157.4 |
| DUFA CIG | - | - | - | - | 2.1 | 4.1 | 7.6 | 9.2 | 11.5 | 20.1 | 18.1 | NA | 72.7 |
| IKILIFCOOP | - | - | - | - | - | - | - | - | - | - | - | - |  |
| PELENA HOLDINGS | Refusal |  |
| NGOUNFOUE & SON | Refusal |  |
| SONA EPOKE | Refusal |  |
| COCAFCAM | Refusal and abuser |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  |  | 37629.74 |

PRODUCTION FIGURES FOR SOME CASH AND FOOD CROPS AS PER SUB- DIVISIONS

Annex 3: Production figures for perennial crops

| Cocoa | Production (tons) | 561 | 390 | 5287 | 24895 | 16590 | 47723 | Dried beans |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Cultivated area (ha) | 802 | 558 | 7050 | 38300 | 23700 | 60410 |  |
|  | Farming population | 4258 | 4050 | 9245 | 52423 | 28911 | 98887 |  |
| Robusta coffee | Production (tons) | ne | ne | 12 | 133 | 82 | 227 | Dry grains |
|  | Cultivated area (ha) |  |  | 15 | 178 | 97 | 290 |  |
|  | Farming population |  |  | 45 | 115 | 82 | 242 |  |
| Oil palm | Production (tons) | 2866 | 2635 | 5814 | 28800 | 13693 | 53808 | Tons of Fresh fruit bunch(FFB) |
|  | Cultivated area (ha) | 455 | 382 | 765 | 3840 | 2123 | 7565 |  |
|  | Farming population | 1240 | 1167 | 2935 | 8060 | 6612 | 20014 |  |
| Rubber | Production (tons) | ne | ne | 8736.4 | 9112.5 | 4296 | 22144.9 | Cup lump |
|  | Cultivated area (ha) |  |  | 3763 | 4267 | 1820 | 9850 |  |
|  | Farming population |  |  | 115 | 255 | 185 | 555 |  |
| Citrus | Production (tons) | 180 | 144 | 329 | 4884 | 2247 | 7784 | fruits |
|  | Cultivated area (ha) | 12 | 8.5 | 20.6 | 296 | 145 | 482.1 |  |
|  | Farming population | 305 | 246 | 465 | 1093 | 862 | 2971 |  |
| Plum | Production (tons) | 10 | 10 | 19 | 58 | 34 | 131 | Very poor production in 2013 |
|  | Cultivated area (ha) | 18.4 | 16.7 | 38 | 116 | 68 | 257.1 |  |
|  | Farming population | 97 | 88 | 190 | 583 | 343 | 1301 |  |
| Cola nuts | Production (tons) | 5.2 | 6 | 8.03 | 9 | 8.25 | 27.48 |  |
|  | Cultivated area (ha) | 6.5 | 8 | 11 | 15 | 12.5 | 53 |  |
|  | Farming population | 130 | 205 | 450 | 823 | 605 | 2213 |  |

Source: interview with farmers by MINADER staffs Remarks:

Annex 4: Production figures for food crops

| Crop | indicators | Kumba I | Kumba II | Kumba III | Mbonge | Konye | Total division | Remark |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cassava | Production (tons) | 5850 | 5590 | 9580 | 110102 | 74815 | 205937 |  |
|  | Cultivated area (ha) | 305 | 285 | 588 | 8469 | 5267 | 14914 |  |
|  | Farming population | 6258 | 4833 | 9035 | 42624 | 19911 | 82661 |  |
| Maize | Production (tons) | 352 | 370 | 657 | 7566 | 5452 | 14397 |  |
|  | Cultivated area (ha) | 235 | 185 | 365 | 5820 | 3635 | 10240 |  |
|  | Farming population | 4150 | 3540 | 7920 | 38345 | 16890 | 70845 |  |
| Plantain | Production (tons) | 1515 | 1842 | 12035 | 77140 | 54010 | 146542 |  |
|  | Cultivated area (ha) | 135 | 205 | 1150 | 7460 | 4890 | 13840 |  |
|  | Farming population | 2325 | 3250 | 5081 | 22812 | 9955 | 43423 |  |
| Banana | Production (tons) | 1430 | 1900 | 8900 | 28300 | 22600 | 63130 |  |
|  | Cultivated area (ha) | 143 | 172 | 847 | 2509 | 2194 | 5865 |  |
|  | Farming population | 1002 | 1800 | 2600 | 10400 | 5100 | 20902 |  |
| Cocoyam | Production (tons) | 928 | 1037 | 3599 | 17577 | 15755 | 38896 |  |
|  | Cultivated area (ha) | 160 | 170 | 610 | 2450 | 2270 | 5660 |  |
|  | Farming population | 1200 | 700 | 2100 | 15500 | 12300 | 31800 |  |
| White yam | Production (tons) | 1750 | 1730 | 1990 | 17000 | 760 | 23230 |  |
|  | Cultivated area (ha) | 250 | 210 | 275 | 2000 | 120 | 2855 |  |
|  | Farming population | 200 | 185 | 250 | 1000 | 105 | 1740 |  |
| Sweet potatoes | Production (tons) | 79.75 | 111.8 | 954 | 1072.5 | 851 | 3069 |  |
|  | Cultivated area (ha) | 14.5 | 21.5 | 180 | 195 | 154.5 | 565.5 |  |
|  | Farming population | 98 | 125 | 500 | 650 | 515 | 1888 |  |
| Leafy vegetable | Production (tons) | 506 | 462 | 1192 | 4158 | 2632.5 | 8951 |  |
|  | Cultivated area (ha) | 23 | 21 | 53 | 189 | 117 | 403 |  |
|  | Farming population | 425 | 350 | 850 | 2800 | 1950 | 6375 |  |
| Pineapple | Production (tons) |  |  | 3930 | 1276 | 233 | 5439 | fruits |
|  | Cultivated area (ha) | Ne | Ne | 131 | 58 | 10.6 | 199.6 |  |
|  | Farming population |  |  | 785 | 1935 | 355 | 3075 |  |
| Pepper | Production (tons) | 52.5 | 57.7 | 82 | 263 | 180 | 635.2 | Fresh fruits |
|  | Cultivated area (ha) | 10 | 11.5 | 14.9 | 47 | 40 | 123.4 |  |
|  | Farming population | 350 | 385 | 499 | 2355 | 2011 | 5600 |  |
| Egusi | Production (tons) | Ne | Ne | 395 | 1156 | 48 | 1599 | Dried grains |
|  | Cultivated area (ha) |  |  | 330 | 1198 | 53 | 1581 |  |
|  | Farming population |  |  | 1320 | 4793 | 245 | 6358 |  |
| Groundnuts | Production (tons) | 110.7 | 134 | 344 | 1460 | 594 | 2642.7 | Fresh groundnuts |
|  | Cultivated area (ha) | 73.8 | 86 | 215 | 913 | 381 | 1668.8 |  |
|  | Farming population | 369 | 410 | 898 | 3652 | 1733 | 7062 |  |
| Okro | Production (tons) | 6.6 | 6 | 17.85 | 122.5 | 56 | 208.9 | Fresh fruits |
|  | Cultivated area (ha) | 3.3 | 3 | 8.5 | 57 | 28 | 99.8 |  |
|  | Farming population | 165 | 149 | 388 | 2750 | 1405 | 4857 |  |
| Sweet yam | Production (tons) | 32 | 77.4 | 108 | 313 | 162 | 692.4 |  |
|  | Cultivated area (ha) | 2 | 4.3 | 6.4 | 17.4 | 9 | 39.1 |  |
|  | Farming population | 197 | 398 | 643 | 1583 | 777 | 3598 |  |

Remarks

Ne: Negligible: All production below 05 tons for a sub division is considered as negligible.

Annex 5: Comparative food crop production figures for the past 4 year

| Speculation | 2010 | 2011 | 2012 | 2013 |
| --- | --- | --- | --- | --- |
|  | Area (ha) | Production (ton) | Area (ha) | Production (ton) | Area (ha) | Production (ton) | Area (ha) | Production (ton) |
| Cassava | 12295 | 186183.4 | 12448 | 198318.6 | 12481 | 173360.3 | 14914 | 205937 |
| Maize | 7107 | 10660.5 | 7412 | 16888.54 | 7458.5 | 13465.5 | 10240 | 14397 |
| Plantain | 16376 | 151396 | 17420 | 175597 | 17420 | 164051.6 | 13840 | 146542 |
| Banana | 4897 | 59988.8 | 4790 | 62373.8 | 4803 | 62512.8 | 5865 | 63130 |
| Cocoyam | 4706 | 39719 | 4719.45 | 44950.7 | 4585.4 | 44192.2 | 5660 | 38896 |
| Yam | 2140 | 17334.7 | 2151.5 | 17344.5 | 2311.2 | 18004 | 2855 | 23230 |
| Sweet potatoes | 331.1 | 1060.6 | 428 | 1973.8 | 431 | 2517.2 | 565.5 | 3069 |
| Leafly vegetables | 87.5 | 271 | 123.5 | 670.8 | 134.1 | 677.7 | 806 | 8951 |
| pepper | 168 | 260.1 | 156.3 | 144.2 | 158.45 | 120.3 | 123.4 | 635.2 |

Annex 6: Comparative cash crop production figures for the past 4 year

| Speculation | 2010 | 2011 | 2012 | 2013 |
| --- | --- | --- | --- | --- |
|  | Area (ha) | Productions (ton) | Area (ha) | Production (ton) | Area (ha) | Production (ton) | Area (ha) | Production (ton) |
| Cocoa | 49089 | 40895.5 | 55318 | 45142.5 | 55683 | 43612.8 | 60410 | 47723 |
| Robusta coffee | 402.7 | 240.48 | 320.7 | 242.05 | 280.5 | 227.3 | 290 | 227 |
| Oil palm | 6824.3 | 8680.4 | 6867 | 16150.3 | 6867 | 13205.2 | 7565 | 53808 |
| Rubber | 3832 | 14960 | 5098 | 25641.6 | 5223 | 26157.2 | 9850 | 22144.9 |
| citrus | 219 | 2664.1 | 239.1 | 3112.5 | 283.6 | 3706.2 | 482.1 | 7784 |

Annex 7: Prices of Agricultural Inputs in Kumba Main Market

| TYPE OF INPUT | COMMERCIAL NAME | MEASUREMENT UNIT | UNIT PRICE IN FCFA |
| --- | --- | --- | --- |
| FERTILIZER | 20-10-10 | 50 kg bag | 20500 |
|  | urea | 50 kg bag | 20000 |
|  | kiesserite | 50 kg bag | 24000 |
|  | Folivert | 1 kg | 2500 |
|  | Agrovert | 1kg | 2500 |
|  | solupotasse | 1 kg | 3000 |
|  | folicao | 1 liter | 5000 |
|  | Bio 20-10-10 | 1l | 4000 |
|  | supercharge | 0.5 l | 3500 |
|  | Topcop soufre | 0.5 l | 5500 |
|  | Capsidor 50 EC | 0.25 l | 2000 |
|  |  | 1 l | 6000 |
|  | Cyperclean 50 Ec | 1l | 4500 |
|  |  | 5 l | 18000 |
|  | eagrowisl | 1 l | 7500 |
| FONGICIDE | Nordox | Sachet 40 g | 400 |
|  | Hydrox | Sachet 60 g | 300 |
|  | Ok mil | Sachet 50 g | 600 |
|  | Plantineb | Sachet 1 kg | 3500 |
|  | Golden blue | Sachet 60 g | 300 |
|  | Callomil | Sachet 50 g | 600 |
|  | Metalm | Sachet 50 g | 600 |
|  | Mancozan super | Sachet 60 g | 300 |
|  | Forum | Sachet 50 g | 500 |
|  | Fongex twp | Sachet 50 g | 500 |
|  | Trimaneb | Sachet 500 g | 2500 |
|  | Unilax | Sachet 100 g | 1000 |
|  | Mancolax 72 wp | Sachet 50 g | 400 |
| NEMATICIDES | Bastion | Sachet 1 kg | 2500 |
|  | Mocap | Sachet 1 kg | 2000 |
|  | Counter | Sachet 1 kg | 2000 |
|  | Furaplant 10G | Sachet 1 kg | 2500 |
| HERBICIDES | Roundup | 5 L | 19000 |
|  |  | 1 L | 3800 |
|  | Roundup biosec | Sachet 50 g | 500 |
|  | Glyphader | 5 L | 17000 |
|  |  | 1 L | 3800 |
|  | Gramoxone | 5 L | 18000 |
|  |  | 1 L | 4000 |
|  | Decaplant | 1 L | 3500 |
|  | Kalach | 1 L | - |
|  |  | Sachet 250 g | 2000 |
|  | Plantop 360 | 1 L | 3500 |
|  |  | 5 L | 18500 |
|  | Garion | 5 L | - |
|  | Herbistar | 5 L | 18000 |
|  |  | 1 L | 4000 |
|  | Calloxone | 5 L | 18000 |
|  |  | 1 L | 3500 |
|  | Supraxone | 5 L | 17500 |
|  |  | 1 L | 3500 |
|  | Roundup turbo | 1 L | 5000 |
|  | Super killer 480 | 1l | 4000 |
|  | Finish 360 | 1L | 3800 |
|  | Glyphosalm 360 | 1L | 3800 |
|  | Glyphalm | Sachet 250 g | 2000 |
|  | Glycot | 1 L | 2800 |
| INSECTICIDES | Gawa | 5 L | 30000 |
|  |  | 1 L | 5500 |
|  | Parastar | 5 L | 27500 |
|  |  | 1 L | 6000 |
|  | Callidim 400 ec | 5 L | - |
|  |  | 1 L | - |
|  | Cypercal 12 EC | 5 L | 18000 |
|  |  | 1 L | 3000 |
|  | Cypercal 50 EC | 5 L | 18500 |
|  |  | 1 L | 4500 |
|  | Kunfu 5% wp | 1 L | 4000 |
|  |  | sachet | 250 |
|  | Dursban | 1 L | 8000 |
|  | Cyperdim 220 EC | 1 L | 5500 |
|  | Pyriforce | 1 L | 8000 |
|  | Poudrox (conservation) | Sachet 50 g | 500 |
|  | Malagrain | Sachet 50 g | 500 |
|  | Cypalm 200 | 1 L | 6000 |
|  | Kart 500 sp | Sachet 50 g | 300 |
|  | Cigogne 50 EC | 5 L | 11000 |
|  | Actara | Sachet 4g | 450 |
|  |  | Tin 250 g | 10000 |
|  | Iron | Sachet 4g | 300 |
|  |  | 1 L | 4500 |
|  |  | 5 L | 22500 |
|  | Malathane | 0.5L | 3500 |
|  |  | 1 L | 5000 |
|  |  | 5 L | 22500 |
|  | Dinacoco | 1 L | 5500 |
|  |  | 5 L | 25000 |
|  | Chlocot 480 EC | 1 L | 6500 |
|  | Gongfut | 1 L | 4500 |
|  |  | 5 L | 22500 |
| TREE KILLER | Corta 480 | 5 L | 75000 |
|  |  | 1L | 15000 |
|  | caviar | 1 L | 10000 |

Annex 8: Prices of Agricultural tools/equipment in Kumba Main Market

| TYPE | NAME | MEASUREMENT UNIT/qty | UNIT PRICE |
| --- | --- | --- | --- |
| Knapsack sprayer | matabi | 15 L | 35000 |
| Atomizer | Solo | 10 L | 350000 |
|  | Agropo | 10 L | 200000 |
| Raincoat | raincoat | set | 5000 |
| Rainboat | rainboat | pair | 4500 |
| cutlass | caiman | 1 | 3500 |
|  | long | 1 | 3500 |
| Hoe | tropic | 1 | 2500 |
|  | banwa | 1 | 3500 |
| file | Taper/matinga | 1 | 600 |
| spade | - | 1 | 5000 |
| Wheel barrow | - | 1 | 18000 |
| Watering can | Plastic 11 L | 1 | 4500 |
| Engine saw | Stilh | 1 | 250000 |
| Push truck | Maison cycle | 1 | 80000 |
|  | Local made | 1 | 50000 |
| Digger | tropic | 1 | 3500 |
| Axe | - | 1 | 3500 |

Annex : Breakdown of road works between Dikome Balue and Madie

| Investment | Realization |
| --- | --- |
| Opening of new road section | 40% |
| Profile Road and shape site drain | 58.33% |
| Metallic culvert dai.1000mm | 80% |
| metallic culvert dai.1500mm | 80% |
| Masonry Inlet Dai.1000mm | 80% |
| Masonry Inlet Dai.1500mm | 80% |
| Bridge 12m spanCH10+500 H=4m |  |
| 4IPE 500 on bridge site | 75% |
| Excavation of trench on one side(Dikome Balue side) | 100% |
| Lean concrete on one side | 100% |
| Installation of rain gate | 0% |
| Site installation | 60% |

# Text boxes

###### TECHNICAL REPORT

###### FOR 2013