Community College of Rhode Island

CCRIBIT

Project Definition

| Prepared by: | CCRI Banner Steering Committee |
| --- | --- |
| Version: | 1.4 |
| Last Revision Date: | June 9, 2003 |
| Create Date: | April 15, 2003 |

Table of Contents

Executive Summary	4

1	Introduction	7

1.1	Mission	7

1.2	Objectives	7

1.3	Benefits	7

1.4	Benefits History and/or Background	8

1.4.1	Feasibility Recommendations	8

2	Project Scope	10

2.1	Exclusions	11

2.2	Planned Process Improvements	12

3	Project Milestones	12

4	Project Budget	13

4.1	Introduction	13

4.2	Budget Assumptions	13

4.3	Budget Details	13

5	Assumptions/Dependencies	13

5.1	Assumptions	13

5.2	Dependencies	15

5.2.1	Dependent Projects	15

5.2.2	Dependent Products	15

5.2.3	Dependent Resources	16

5.2.4	Dependent Interfaces	16

6	Project Constraints	16

6.1	Project Dimension Grid	16

6.2	Constraint Details	17

7	Risks	17

8	Project Organization	21

8.1	CCRIBIT Steering Committee, Project Teams, Work Teams	21

8.2	Roles and Responsibilities	22

8.3	Change Control Board(s)	24

9	Project Approach	24

9.1	Define	24

9.2	Plan	24

9.3	Implement	25

9.4	Close-Out	25

9.5	Change Management	25

9.6	Documentation	26

9.7	Communication	27

9.8	Measurement	27

9.9	Project Environment	27

9.10	Quality Assurance	28

9.11	Tracking	28

9.12	Risk Management	28

10	System Requirements	28

10.1	Database Server Requirements	29

10.2	PC Requirements	29

10.3	SCT and 3rd Party Product Requirements	29

10.4	Developer Requirements	29

11	Project Deliverables	29

12	Project Success Criteria	30

13	Approval to Proceed	31

14	Acronyms	33

15	Definitions	33

16	CCRI Banner Implementation Project Organization	34

17	Budget Details	35

Executive Summary

On December 20, 2002 the Community College of Rhode Island signed a contract for software licenses and a three year services agreement with SCT to migrate from our current SCT Plus management information systems to the SCT Banner Student, Financial Aid, Human Resources and Finance suite of information systems.  With participation from SCT, the Steering Committee prepared this Project Organization and Planning document. The document defines the scope of the migration and will serve as CCRI’s guide for the implementation. The Steering Committee requests the approval of the project definition from the President’s Council after appropriate review.

- Mission

The mission of this project is to ensure that the SCT Banner suite of information systems is implemented in a timely and cost effective manner within the framework of the College’s efforts to better serve its constituents.

- Goals

The primary goal of the initial phase of the project is to implement the core modules within a 3 year time frame with as much of the existing functionality as possible.  New features and the Banner add-on modules that were purchased must be prioritized considering this goal as well as financial and human resource constraints.  Many of us will be excited by the possibilities of the new system; however we need to temper that excitement with the reality of what it will take just to migrate to the core Banner modules.

- Recommendations

  - SCT and the Steering Committee strongly recommend that CCRI commit to implement all modules without making any changes to the software to accommodate “the way we have always done things”.   The Banner systems have been designed using best practices in higher education.  Implementing a “vanilla” (unchanged) system will allow CCRI to leverage those best practices to achieve process improvements.

  - Limit new initiatives that would require resources from the key functional areas or the IT MIS group during the project.  If policy changes are required, the feasibility should be assessed by the relevant project team to ensure that the Banner software can support the policy and that implementing it would not affect the project timeline.  Recent new initiatives that are impacting areas involved in the project include drivers education, the new late registration policy, and the late starting courses to be offered in fall 2003 at CCE in Providence.

  - Only regulatory or emergency updates and/or changes should be applied to the old SCT Plus systems during the project.  It will be very difficult for the technical staff to maintain the existing system while implementing the new system.  Changes to the old system must be minimized.

  - A training room should be identified and allocated to the project.  Beginning this summer, full-day training sessions for the project team will be scheduled for 1-2 weeks per month over the next 2 ½ years.  Additionally, team members should have a place to work on the project away from the demands of their offices.  Recommendations for facilities include: 2106 in Warwick (IBPF lab), a shared facility with Lifelong Learning in 4212 (new machines will have to be allocated), sharing 4100 (Center for Instructional Technology) with IT training and faculty use.

- Benefits

CCRI will reap a number of benefits from the move to the Banner products including the following:

- A more fully integrated information system to support decision making will be achieved.

- End-users will be able to generate ad-hoc reports.

- CCRI will be in a position to provide improved services to its constituents including enhanced personalized opportunities for access to relevant information.

- The College will be positioned to more easily take advantage of the features of current and future technology.

- An opportunity for current process evaluation and re-design will provide the chance to develop more efficient and effective operations.

- 24x7 system availability will be provided to the College Community.

- Challenges

Project teams and the Steering Committee will be faced with many challenges during the course of the implementation.  For example CCRI currently has two computerized data storage areas for student transcript data, one is SIS Plus the other is a home grown ancillary system.  The task of combining these student transcripts into one data storage area, SIS Plus, in preparation for the Banner migration will require considerable time, effort and planning.

Implementing the Curriculum, Advising and Program Planning component of the Student module (Degree Audit in SIS Plus), will require that some members of the Student team take on the additional task of re-constructing academic programs in Banner while working on the conversion to the Banner Student module.

Finally, given the multitude of other initiatives currently underway at the College, such as NEASC Accreditation, OHE Data Warehouse, and the Little Big Audit, just to name a few, we may find that the Banner project is competing with these and other projects for the same financial and human resources.

- Timetable

The timetable for the project was developed by the CCRI Banner Steering Committee in conjunction with SCT at the project planning session held in April.  Finance will be the first module to go live with a target date of July 2004 followed by Admissions and Recruiting in September of 2004.  Financial Aid is scheduled for a January 2005 rollout with Student and the self-service modules for faculty and students going online in March of 2005.  And finally Human Resources is targeted for January 2006.

- Council Role

Steering Committee priorities and project plans will be submitted to the President’s Council for approval.  The Steering Committee will look to the President’s Council for decisions regarding project budget and any policy changes that may be deemed necessary.  The Project Manager will provide bi-monthly updates on the project at Presidents Council Meetings.  Also, CCRI’s Banner implementation project will benefit greatly from the on-going support of the President’s Council with their constituents.

As the President’s Council is presented with opportunities for new initiatives they will be submitted to the Steering Committee for review.  The Steering Committee will assess the impact of the initiative on the Banner implementation budget and timeline and forward the assessment to the President’s Council for consideration.  After reviewing the report from the Steering Committee and considering the risks to the Banner implementation the President’s Council will decide if the new initiative should be undertaken.

# Introduction

## Mission

The mission of this project is to ensure that SCT Banner Student, Financial Aid, Human Resources and Finance suite of administrative software is implemented in a timely and cost effective manner within the framework of the College’s efforts to better serve its constituents.

## Objectives

The primary goal of the initial phase of the project is to implement the core modules within a 2 ½ year time frame with as much of the existing functionality as possible.  New features and the Banner add-on modules that we purchased must be prioritized considering this goal as well as financial and human resource constraints.  Many of us will be excited by the possibilities of the new system; however we need to temper that excitement with the reality of what it will take to just to migrate to the core Banner modules.

## Benefits

- To develop processes from a student-centered point of view.

- To provide more fully integrated information systems to support decision making.

- To enable end-users to generate ad-hoc reports.

- To improve services to CCRI constituents including enhanced personalized opportunities for access to relevant information.

- To take advantage of the features of current and future technology.

- To provide an opportunity for current process evaluation, re-design and continuous improvement.

- To extend information management responsibilities and access to the College Community.

- To provide 24x7 system availability to the College Community.

- More efficient and effective operations.

- Professional growth of individuals.

- Standardization of data.

- More data and information for planning and effective communication.

- Improved understanding of project management methodologies.

- Consistent information system documentation.

- A culture of continuous improvement.

## Benefits History and/or Background

The MIS Assessment Committee was established in May, 2001 and charged with “evaluating our present core administrative systems (SCT), assessing our various options, and recommending to the President’s Council the solution that would best meets the long term goals of CCRI”.  The committee was made up of the following members:

- Alice Aguiar, Assistant Director, Computer Resources

- Tammy Anderson, Associate Director, Computer Resources

- Mike Kelly, Assistant Professor of Computer Studies

- William LeBlanc, Director, Institutional Research

- Sheri Norton, Assistant Director, Personnel

- John Panzica, Lead Information Technologist, Enrollment Services

- Mark Vigorito, Associate Director, Financial Aid

- Pat White, Assistant Controller

### Feasibility Recommendations

The committee began meeting in early June and immediately assessed our existing systems, the SCT Plus products.  All agreed that the Plus systems are based on old technology, difficult to maintain, provide limited reporting capability, and should be replaced as soon as possible.  We discussed potential options for replacing these systems and decided to narrow the focus of our evaluation to SCT Banner and PeopleSoft.  SCT Banner was evaluated because: we have many years of experience with SCT; we could easily maintain our investment in Campus Pipeline, the Web for Student and Faculty products, the Touchnet web credit card Payment Gateway, and the EPOS voice response system; and we qualify for SCT’s newly available LEAP program which provides Banner software to Plus clients at no additional cost for licenses.  PeopleSoft was evaluated because CCRI owns licenses to its software as a result of a system wide purchase in 1998.  These vendors are also the market leaders in the Higher Education space and the majority of comparable colleges choosing new administrative systems select one of them.

The committee completed the following tasks during the course of our evaluation.

- Each committee member developed a list of system requirements representing the core functional users of the administrative system.

- Two committee members attended a Version 8 Roadshow that previewed the new release of the PeopleSoft Student Administration system.  (The vendor limited our attendance to 2.)

- We scheduled full day presentations from each vendor and invited 8 key system users in addition to the committee members.  The committee sought feedback from the system users that attended the presentations.

- We collected and assessed documentation for each of the systems.  The documentation included detailed comparisons of the SCT Plus and Banner systems.

- We contacted many people from a variety of colleges and universities that had implemented or planned to implement either SCT Banner or PeopleSoft.  We interviewed these contacts about their implementation projects, costs, and overall experiences with their particular system.

- We prepared estimated budgets for the implementation of each system.  The information was gathered from vendor salespeople, consulting firms, and costs incurred by other colleges.

- We assessed the advantages and disadvantages of each system based on the information gathered.

The result of our evaluation process was the recommendation that CCRI begin the conversion from the SCT Plus software to SCT Banner as soon as possible.  The following points support this recommendation.

- Implementation costs will be significantly lower with Banner.  Our conservative estimate is $1.5 million less.  RIC has spent over $5 million on their implementation, thus far, and their PeopleSoft system has far less functionality than our existing system.  The OHE expenditure for PeopleSoft licenses is considered a sunk cost in this evaluation, as we cannot reverse the expenditure.  Only future project costs are considered in this decision.

- Colleges with PeopleSoft systems require more people with more sophisticated skill sets, both functional users and technical staff, than those with Banner.

- The Banner system provides the most stable and robust functionality, particularly in the Student and Financial Aid systems, which were identified as the key systems in our decision process.  For the majority of our end users, students and faculty, the transition for Campus Pipeline and Web for Students and Faculty will be transparent.  An implementation of PeopleSoft would result in lost functionality for some period of time because of the immaturity and complexity of the product.

- The data conversion will be simpler and more accurate as SCT provides predefined tools to map Plus data to Banner.  Third party tools would be required to convert to PeopleSoft.  CCRI staff and external consultants would have to map Plus data to PeopleSoft.

- SCT has a long history of commitment to higher education and understands what we do.  Their customer service and support are excellent.  PeopleSoft is new to higher education, is complicated to deal with, and is struggling to provide customer service and support.

- The Banner architecture is built on the industry leading Oracle database and uses Oracle’s state of the art development tools.  SCT is able to fully exploit the technology that Oracle provides.  PeopleSoft is written to support several databases, including MS SQL Server, Oracle, and Informix, requiring them to design to the lowest common denominator of database technology.  PeopleSoft utilizes their proprietary toolset, PeopleTools, for application development.  PeopleSoft Version 8 is marketed as completely web enabled, however, the Banner application utilizes Oracle to provide access to the application from a web browser.

- Most community colleges in Massachusetts and Connecticut use Banner providing easy access to experienced users from similar institutions.

# Project Scope

Banner Student, Financial Aid, Financials, and Human Resources will replace the equivalent SCT Plus products. The implementation will include the following:

Install Software (Including Oracle)

Technical Training

Engagement Management

Project Management

On-site Oracle training

Relational Database Administration

Student

Technical Training

Functional Training for Project Teams

Admissions/Recruiting

Catalog/Schedule

Registration

Prerequisite Checking

Faculty Load

Academic History

CAPP

Transfer Articulation

Accounts Receivable

End of Term Processing

Graduation

Enrollment Certification

Student and Faculty and Advisors Self Service

Satisfactory Academic Progress

1098 Processing

Interface to Resource 25

Clearinghouse

Letter Generation Population Selection

Custom Report Development (CCRI responsibility)

Financial Aid

Technical Training

Functional Training for Project Teams

EDE COD processing

Need Analysis/INAS

Budgets

Tracking

Packaging Awarding Disbursements

Title IV

Student Employment

Funds Management

Enrollment Verification

Satisfactory Academic Progress

Letter Generation Population Selection

Custom Report Development (CCRI responsibility)

Finance

Technical Training

Functional Training for Project Teams

Chart of Accounts

Purchasing

Accounts Payable

Requisitioning

General Ledger

Bids & Commodities

Budgeting

Reconciliation

Accounts Receivable

Grants Accounting

Fixed Assets

1099 processing

Stores Inventory

Year End Processing

Custom Report Development (CCRI responsibility)

Human Resources

Technical Training

Functional Training for Project Teams

Payroll (2 in-house, 1 interface from State of RI)

Position Control

Budgeting

Benefits Deductions/COBRA

Time Entry (1 interface from State of RI)

Attendance Reporting

Labor Distribution

Employee Self Services

Web Time Entry

Applicant Tracking

Letter Generation Population Selection

Custom Report Development (CCRI responsibility)

Conversion Toolkit Training & Consulting & Planning

Campus Pipeline Integration Consulting

## Exclusions

These are the scope and the tasks that will not be done and why.

The following are not included in the scope of the project but will be prioritized and implemented once we have gone live with Student, Financial Aid, Financials, and Human Resources:

- Executive Self Service

- e-Print

- WebCT Interface

- Workflow

- CommonLine Student Loan Processing

CCRI will be responsible for the following:

- Conversion of data from Plus systems to Banner

- Custom Report Development

- End User Training

## Planned Process Improvements

Review elimination of duplicate state payroll process

One registration system for credit/non-credit

Billing and financial aid reports/bills more user friendly

Expand the number of staff trained to construct and deliver custom reports

All data in a single database

# Project Milestones

| Milestones | Date |
| --- | --- |
| Project Start | April 2003 |
| Install Hardware | July 2003 |
| Install Software | July 2003 |
| Finance | July 2004 |
| Admissions/Recuriting | September 2004 |
| Financial Aid | January 2005 |
| Student | March 2005 |
| Bursar | March 2005 |
| Human Resources/Payroll | January 2006 |
| Post Implementation – Phase II |  |
| Executive Self Service |  |
| Worklfow |  |
| e-Print |  |
| WebCT Interface |  |

# Project Budget

## Introduction

The project budget includes commitments that have been made so far for the project for SCT software and services, HP hardware, and Oracle database software.  Additional project needs for hardware; software and training have also been detailed.  Estimated costs for implementing the add-on modules that were purchased in conjunction with the SCT contract are included.  A budget for labor costs, such as overtime and temporary personnel costs will be created by the end of August after the detailed project plan has been established.

## Budget Assumptions

Adequate funding will be available to complete the implementation

## Budget Details

Refer to:  Section 17 of this document.

# Assumptions/Dependencies

Assumptions and Dependencies are items that are being presumed and are potentially out of our control.

## Assumptions

Legacy Systems:

- Legacy systems will be maintained for three months after the data conversions.

- Legacy system development will halt as of May 1, 2003.  Any exceptions must be mission critical requests and be approved by the President’s Council.

- Sources of legacy system data corruption will be identified and immediate solutions developed and deployed.

- Transcript History data must be converted from non-Plus “Archive” system

- Admissions data corruption problem must be resolved

- Clean up of legacy data will be completed before conversion of data into Banner.

- A systematic approach will be used to identify what data to convert into Banner and what data to archive.

- The current voice registration system, EPOS, will no longer be operational.

Governance:

- The Banner implementation process will be performed in an open and participatory manner.

- Decision-making will be delegated to the lowest level possible.

- Timely communication will occur between all committees and work groups as well as the college community.

Training:

- Appropriate and timely skill set development and training will be provided and sustained.  Individual work team members will be responsible to provide training to the college community.

- A Banner training curriculum will be developed and all Banner users will be required to learn the skills necessary to ensure project success.  Accounts will be issued to users upon demonstration of competency based on assessment.

- Every effort will be made by the college to designate training space for the Banner implementation and ongoing training.

Modifications:

- SCT Banner will be implemented with as few changes as possible, also known as a “vanilla implementation”.  The software has been designed utilizing best practices within higher education.  We should modify our business practices whenever feasible and should never change the software “because that’s the way we do it”.  Some state rules may require software changes, but those should be evaluated and prioritized by the Steering Committee.

Resources:

- The SCT Banner implementation will take priority over other job responsibilities for the CCRIBIT Team and all project team members.

- The SCT Banner implementation schedule will be strictly adhered to.

- Assignment of project personnel will remain intact until completion of the project.

- All necessary resources will be provided to ensure project success such as staff training, overtime, temporary staff, and additional required software and hardware.

Other:

- Agendas and issues/resolution documents for all team meetings will be prepared.

- Reporting and documentation strategies will be identified and developed concurrently with each Banner module.

- Standard reporting tool(s) for SCT Banner will be selected.  Access to the tool will be provided to CCRI personnel.

## Dependencies

### Dependent Projects

| Project Name | Expected Completion Date | Reason for Dependency |
| --- | --- | --- |
| Installation of server hardware (HP Alpha), operating system (Tru64 Unix), and database (Oracle) | July 2003 | Competing use of resources – entire project is dependent on this |
| Conversion to UNIX operating system | July 2003 | Competing use of resources, staff training. |
| NEASC Accreditation | Spring 2004 | Competing use of resources |
| Resource 25 Implementation | Fall 2003 | Room scheduling for courses and events. Competing use of resources |
| Desktop Replacement Project | Ongoing | Competing use of resources |
| Newport Campus Development | Fall 2005 | Competing use of resources |
| Providence Campus Expansion | Fall 2004 | Competing use of resources |
| City Campus | Undetermined | Competing use of resources |
| Data Warehouse Project – OHE | Ongoing | Competing use of resources |
| Transfer Articulation – OHE initiative between CCRI, URI, and RIC | Ongoing | Impact CAPP, competing use of resources. |
| Developmental Education Project | Fall 2004 | Competing use of resources |
| Little Big Audit | Spring 2004 | Competing use of resources |
| Strategic Planning Initiative | Ongoing | Competing use of resources |
| Pipeline Upgrades | Ongoing | Student Portal, access to academic record. Competing use of resources. |
| Telephone Upgrade Project | Spring 2004 | Competing use of resources |
| Parking System | Spring 2005 | Current system provides for information but Banner will not. |

### Dependent Products

Products (whether produced by SCT or a third party) that will provide the deliverables that are required to enable this project to meet its objectives.

| Product Name | Release Number | Release Dependency is Higher | Reason for Dependency |
| --- | --- | --- | --- |
| WebCT |  |  | Teaching resources |
| Pipeline/Luminus (SCT) |  |  | Student Portal |
| Resource 25 (CollegeNET) |  |  | Room Scheduling |
| Payment Gateway (Touchnet) |  |  | Credit Card payment |
| One Step (CORE) |  |  | Cashiering |

### Dependent Resources

People and material resources required for which the project is dependent upon.

| Resource | Reason for Dependency |
| --- | --- |
| Servers and Software | Necessary for installation of Banner software |
| Training facilities | Required for training on the implementation |
| Staff Training | Additional technical and other training required by personnel involved in or affected by system implementation |
| Campus Community | Knowledge base of current processes & users of new system |
| Public Relations | Communicating of new processes and products to the campus community and to the college constituency |

### Dependent Interfaces

The following interfaces will need to be assessed and the impact on the project measured:

| Interface | Interface to Banner |
| --- | --- |
| Student ID System/Employee ID | Download Student/Employee information to create student/employee ID card |
| Bookstore System | Batch interface from Student Interface back to A/R for bookstore charges |
| RIHEAA | Data transfer for State Grant Processing |
| AMS | Interface for Deferred Payment |
| Clearinghouse | Transfer Cohorts |
| Moore Business Systems | Download to business form processing and mailing |
| RI State Payroll | Employee payroll records |
| 1099 State Interface | Income Tax information |
| 1098T State Interface | Income Tax information |
| Accuplacer | Assessment testing for entering students |
| Library System | Download Student/Employee information to Helin |
| W2s State Interface | Income Tax information |
| TIAA Disability | Employee Salary feed for disability processing |

| Field-by-Field Descriptions for Project Dependency Table |
| --- |
| Project Name | Specify the name of the project upon which this project depends as it is defined in the “Project Definition Name” field for that project’s Project Definition record in the Project Tracking System. |
| Expected Completion Date | Specify the date, in MM/DD/YYYY format, upon which the particular project is expected to complete. Obtain this date from the “Current Targeted Date” field or, if blank, the “Planned Completion Date” field of the project’s Project Definition record in the Project Tracking System. |
| Reason for Dependency | Specify the reason(s) for which this project is dependent upon the particular project listed. What are the particular deliverables of the listed project that are needed by this project in order for it to meet its objectives? Be specific, as the reason stated here would be a factor in determining whether any issues that are identified with respect to the listed project justifies the removal of the dependency. |

| Field-by-Field Descriptions for Product Dependency Table |
| --- |
| Product Name | Specify the name of the product upon which this project depends. You can review the products listed in the Scope section of any project’s Project Definition record in the Project Tracking System for a list of valid product names. This list, though, is not exhaustive. Third party product names, for example, may not be found there. |
| Release Number | Specify the particular release of the product upon which this project depends. If the product deliverables for this project will be deployed at multiple release levels and this project has dependencies with a product at those different levels, list each product release dependency in a separate row. |
| Release Dependency is Higher | Specify ‘Yes’ or ‘No’ depending upon whether the particular release of the product upon which this project depends is higher than what was required for previous projects. For example, if the last project for a particular product area only required Adobe Acrobat 3.0, but this project requires Adobe Acrobat 4.0, specify ‘Yes’ here. |
| Reason for Dependency | Specify the reason(s) for which this project is dependent upon the product listed. What are the particular deliverables from the listed product that are needed by this project in order for it to meet its objectives? Is there a data structure change implemented in the product upon which this project relies? Are their regulatory changes in one product that your product assumes are in place? Be specific, as the reason stated here would be a factor in determining whether any issues that are identified with respect to the listed product justifies the removal of the dependency. The only instance in which the value for this field can be set to ‘Not applicable’ is where the value of the “Release Dependency is Higher” field is explicitly ‘No’ for a listed product. |

# Project Constraints

Project Constraints are aspects about the project that cannot be changed and are limiting in nature. Constraints generally surround four major areas: Scope, Cost, Schedule (Time), and Quality.

## Project Dimension Grid

The grid below prioritizes the critical project dimensions and is used to negotiate changes during the course of the project. First step is to specify the constraining dimension. Is the critical project driver scope, cost, quality, or time? The second step is to specify the accept dimension. If change is required, in which area are the key stakeholders most willing to accept change–scope, cost, schedule, or quality? Change must be accepted in at least one dimension. This is specified in the Vary column below. Remaining dimensions are then minimized or maximized. These dimensions will be utilized for all aspects of the project, unless explicitly stated in a sub-project definition.

Specify the project dimensions below. Constrain at least one dimension and vary at least one dimension.

| Project Dimension | Minimize/Maximize | Constrain | Vary |
| --- | --- | --- | --- |
| Scope |  | X |  |
| Cost |  | X |  |
| Schedule | Minimize |  | X |
| Quality | Maximize | X |  |

## Constraint Details

Project Constraints are as follows:

- Limited CCRI staff

- Staff turnover

- Limited temporary employee pool for backfill/assistance

- Limited Budget

- State system requirements; Payroll, Purchasing, Personnel, and Budgeting

- Federal requirements

- NEASC accreditation needs

- Defined contract timeframe

- Limited functional and technological skill sets

# Risks

Identify the risks (or use the Risk Report) to the project with respect to the environment, user expectations, competing projects, project assumptions, resources or any other relevant matter or refer to the work products database. Examples of risk include potential loss of a critical resource, technology changes, regulatory changes, dependence on a third party, scope changes, project sponsorship or management changes legal issues. For high-probability and high-impact risks, specify a plan for reducing the likelihood/impact of the risk (mitigation).

Approaches to responding to risks include:

Retention	the risk is acceptable; retain it and accept the consequences

Deflection	transfer the risk to another party

Preventive	take action in advance of the risk event to reduce its likelihood or its impact

Contingent	specify action that will be taken in response to a risk event, to mitigate its consequences

Avoidance	reject the risk; do nothing

Risks identified during the project should be added to this section as well as the work products database. Anticipated project issues at the beginning of the project should be logged as risks. Risks can be escalated to Project Issues or Jeopardies after the project is initiated (See Identify and Resolve Issues and Identify and Resolve Jeopardies activities). If a risk becomes an issue or jeopardy, it must be designated as such below.

| Issue or Jeopardy Control No. | Risk (If...) | Consequences (Then...) | Probability | Impact | Weight | Response |
| --- | --- | --- | --- | --- | --- | --- |
| Budget and Funding |
| 1 | Lack of detail in the budget | Costs may be overlooked, leading to insufficient funds when project is already in progress | 2 | 2 | 3 | Preventive. Produce a detailed budget before project is far along. |
| 2 | Fixed, limited budget | Limited reserve to respond to unexpected problems | 2 | 2 | 3 | Preventive. Find additional/alternative funding sources. |
| 3 | Funds may not be available when needed | Project completion is delayed | 2 | 2 | 3 | Preventive. VP Henderson will establish mechanism to assure funds are available when needed. |
| Software Functionality |
| 4 | The SCT Banner software may not be able to fully accommodate institutional policies, procedures or current functionality without modification. | SCT Banner modifications are required, leading to cost & maintenance issues; or, overwhelming process changes | 2 | 2 | 3 | Retention. CCRI will first attempt to modify policies and procedures, rather than modify SCT Banner. Modifications are subject to approval by the Steering Committee. |
| Culture and Morale |
| 5 | Empowerment of teams may not be respected or accepted | Project delayed due to slow decision making; team decisions second-guessed, criticized, harming morale | 2 | 2 | 3 | Contingent. If risk materializes, revise schedule to reflect slower decision process. |
| 6 | Resistance to change, lack of understanding and support by the campus community of the demands of a project of this scope; | Lack of cooperation, apathy, lower morale | 2 | 2 | 3 | Preventive. Educate the campus by developing a Communication Plan. |
| 7 | Lack of timely and open communication | Lack of cooperation, apathy, lower morale | 1 | 1 | 1 | Preventive. Open communications, including emails, web site etc. See #6 above. |
| 8 | Insufficient cross-departmental communication and problem solving | Poor integration of functions | 2 | 2 | 3 | Preventive. Represent key departments on CCRIBIT Implementation Team and appropriate Project Teams, especially Student. |
| 9 | Decrease in morale | Tasks incomplete or completed late | 2 | 2 | 3 | Preventive. Communication, visibility, empowerment, recognize achievements, team building events, etc. |
| 10 | Stress associated with maintenance of existing system. | People will be consumed with PLUS activities | 3 | 2 | 4 | Preventative. Priorities will be established for required service issues. |
| 11 | Supervisors not realizing that this project is a priority, and supporting this daily. | Project is delayed. | 2 | 2 | 3 | Deflection. President’s Council must establish and enforce this priority. |
| Resources and Skills |
| 12 | Loss of staff critical to the project | System or module implementation delayed | 2 | 3 | 4 | Contingent. Critical positions will be filled as a priority. Preventive. Improve morale as noted above. |
| 13 | Knowledge of legacy system dependant on a few individuals | Resource availability is limited | 3 | 2 | 4 | Retention. |
| 14 | Limited time to develop skill sets, especially Oracle and Unix | Conversion delayed or poor quality | 3 | 2 | 4 | Retention. Preventative. Ensure appropriate training is available and staff have time to develop skills. |
| 15 | Heavy workload of Project Team, who also participate on CCRIBIT Team | Institutional functions are delayed or SCT Banner Module implementation delayed | 3 | 2 | 4 | Deflection. President’s Council must resolve this issue. |
| 16 | Domains (pre-Legacy) data conversion | Conversion is delayed or poor quality converted data | 3 | 2 | 4 | Preventative. Look at Domains data issues early in project. |
| 17 | May not have the staff to complete CAPP (student degree audit) build before registration cut-over | Degree Audit not available for “go live” plus Advising will be burdened with manual advisement for every student (16,000) | 2 | 3 | 4 | Preventative. Identify necessary human resources early and create specific work team. |
| Schedule and Priorities |
| 18 | Timeline may be unrealistic if CCRI is forced to have other responsibilities take top priority. Banner project MUST be the #1 priority for the campus. | Late implementation and cost overruns | 2 | 2 | 3 | Deflection. President’s Council must enforce institutional priorities. |
| 19 | Decision making occurs too slowly (e.g., in CCRIBIT Team, Project teams or President’s Council) | System or module implementation delayed, potential cost overruns | 2 | 2 | 3 | Contingent. Communicate to determine reason for delay, educate or otherwise rectify. Preventive. Make project schedule visible to enhance self-motivation. Encourage reporting of potential schedule slips. |
| Contract |
| 20 | Committed Services | The contract states that implementation services from SCT will be provided until June 30, 2006. What happens if this is not the case and project is delayed? | 1 | 1 | 1 | Preventive. Provide SCT with sufficient advanced notice of scheduling issues to allow work-around. Perform CCRI's project obligations in a timely fashion. Contingent. Pay additional charges to SCT for work performed after the expiration date. Attempt to negotiate such charges; such a resolution is solely at SCT's discretion. |
| Technology Infrastructure |
| 21 | Hardware not delivered in a timely manner | Delayed implementation | 1 | 2 | 2 | Preventative. Coordinate decision- making and scheduling of resources. |

Probability of Occurrence, Estimated Project Impact, and Weight (described below) are one method of classifying risks. Other methods can be used.

Probability guidelines:

- Very Likely		70-100%	A = 3

- Probable		40-70%		A = 2

- Unlikely		0-40%		A = 1

Impact guidelines for scope, cost, schedule, or quality

- Catastrophic	B = 3

- Critical		B = 2

- Marginal		B = 1

# Project Organization

## CCRIBIT Steering Committee, Project Teams, Work Teams

Statement of Purpose (Mission & Objectives)

The CCRI Banner implementation will be accomplished by; the President’s Council, the Steering Committee, Project Teams, the CCRI community, and SCT technical experts and consultants, who are all responsible for the success of the SCT information systems at the Community College of Rhode Island. They will all work from a constituent-centered view to ensure that the system is implemented in a timely and cost-effective manner, integrated with other software applications, and well-trained users are able to use the system effectively.

## Roles and Responsibilities

Roles and responsibilities are as follows:

President’s Council

| Member Name | Position |
| --- | --- |
| Dr. Thomas D. Sepe | President |
| Nancy Abood | Assistant to the President/Director of Public Relations and Publications |
| Joseph DiMaria | Vice President for Student Affairs |
| Robert Henderson | Executive Vice President/Vice President for Business Affairs and Treasurer |
| Dr. Ruth Sherman | Vice President for Academic Affairs |
| Philip Sisson | Dean of the Division for Lifelong Learning |

The President’s Council will:

- Make budget decisions

- Make policy decisions

- Approve steering committee priorities and plans

- Garner support for the project from their constituents

- Submit new initiatives to the Steering Committee for review of budget and timeline impact on the Banner implementation.

CCRIBIT Steering Committee

| Member Name | Position |
| --- | --- |
| Alice Aguiar | Project Manager, Assistant Director for MIS, Department of Information Technology |
| Deborah Aiken | Project Lead, Assistant to the Commissioner for Student Systems for the Office of Higher Education |
| Tammy Anderson | Associate Director, Department of Information Technology |
| Barry Emmert | SCT Project Manager |
| Dr. William LeBlanc | Director of Institutional Research |
| Sheri Norton | Assistant Director of Personnel |
| Philip Sisson | Dean of the Division of Lifelong Learning |
| Mark Vigorito | Associate Director of Financial Aid |
| Pat White | Assistant Controller |
| Dr. Peter Woodberry | Dean of Business & Technology Programs |

The Steering Committee will:

- Develop implementation plans

- Monitor the progress of all project teams

- Provide status reports to the President’s Council

- Formulate and present policy change requests to the President’s Council

- Request resources to ensure adequate support to meet implementation goals

- Evaluate, prioritize and manage system change requests

- Review the budget and timeline impact of proposed new initiatives on the Banner implementation and report the findings back to The President’s Council.

Project Teams will:

- Attend SCT training

- Make decisions by consensus

- Recommend policy changes or system changes to Steering Committee

- Ensures completion of major tasks

- Form functional work teams as needed and assigns tasks and responsibilities

- Provide status reports to Steering Committee

Finance Project Team

| Member Name | Position |
| --- | --- |
| Pat White | Project Lead, Assistant Controller |
| Ruth Barrington | Business Manager |
| Ray DeAngelis | Purchasing Officer |
| John Horodysky | Assistant Controller |
| Sharon Picard | Chief Accountant |
| Albert Sevigny | Controller |
| Sandra Sokoll | Supervisor, Accounts Payable |
| Terry LeFebvre | Programmer/Analysts |

Student Project Team

| Member Name | Position |
| --- | --- |
| Deborah Aiken | Project Lead, Assistant to the Commissioner for Student Systems for the Office of Higher Education |
| Robert Cipolla | Director of Advising and Counseling |
| Stacey Flowers | Staff Assistant |
| Dennis Grassini | Bursar |
| Christine Jenkins | Associate Dean of Enrollment Services |
| Dr. William LeBlanc | Director of Institutional Research |
| Michelle O’Brien | Service Development Manager |
| John Panzica | Assistant Dean of Enrollment Services |
| Irene Russo | Technical Staff Assistant |
| Bortie Teh | Programmer/Analyst |
| Brian Cini | Programmer/Analyst |
| Additional MIS staff as needed |  |

Financial Aid Project Team

| Member Name | Position |
| --- | --- |
| Mark Vigorito | Project Lead, Associate Director of Financial Aid |
| Christine Jenkins | Associate Dean of Enrollment Services |
| Patricia Moore | Sr. Financial Aid Officer |
| Patricia O’Brien | Eligibility Technician |
| Glen Wolczak | Programmer/Analysts |

Human Resources Project Team

| Member Name | Position |
| --- | --- |
| Sheri Norton | Project Lead, Assistant Director of Personnel |
| Sandra Casali | Payroll Manager |
| Robin Donnelly | Administrative Assistant |
| Linda Greenwood | Personnel Officer |
| John Horodysky | Assistant Controller |
| Programmer/Analyst to be determined at a later date |  |

## Change Control Board(s)

The CCRIBIT Steering Committee will serve as the Change Control Board.

Responsibilities of the change Control Board are defined in the Change Management section 9.5.

# Project Approach

The project approach section deals with how the project will be completed.

## Define

SCT's Project Organization and Planning Session (POPS) is a key activity of this phase.

For the software implementation approach, the Definition Phase activities of SCT's Enterprise Process Model will be followed.  Responsibilities will be assigned according to the Banner Implementation Methodology.

## Plan

For the project management approach, the Planning Phase activities of SCT's Common Service Methodology (CSM) will be followed.  This Project Definition Document, the project schedule, and all the supporting plans are key deliverables of this phase.

For the software implementation approach, the Planning Phase activities of SCT's Enterprise Process Model will be followed.  Responsibilities will be assigned according to the Standard Implementation Model.

## Implement

Project tracking, risk management, and change management are key project management activities of this phase.

For the software implementation approach, the Implementation Phase activities of SCT's Enterprise Process Model will be followed.  Responsibilities will be assigned according to the Standard Implementation Model.  Key tasks are:

- process analysis

- hardware / software installation

- system education

- system development

- system testing

- system validation

- reporting

- conversion

- end-user training

- on-site functional training

- deployment ("go live")

## Close-Out

Leaping to Banner and documenting lessons learned are key activities of this phase.

For the software implementation approach, the Closeout Phase activities of SCT's Enterprise Process Model will be followed.  Responsibilities will be assigned according to the Standard Implementation model.  Evaluation of the implementation, recommendations, and final approvals are key activities.

## Change Management

Change management will be the responsibility of the Steering Committee.  None of the implementation teams will make the decision to modify the base software on their own. As the implementation teams uncover instances where College policies can not be accommodated by the Banner software, a workaround can’t be developed, or a change of procedure isn’t an option they will bring the issue to the Steering Committee.  The Steering Committee will review the issue and decide either to authorize the software modification or recommend a change in policy to the President’s Council.

A Configuration Management Plan (CM) will be created.  Major elements of the plan are as follows:

Items in Scope

The following items are in the scope of the CM Plan:

- Project Definition Document

- Project Schedule

- Configuration Management Plan

- Organizational Readiness Plan

- Process Analysis Plan

- Training Plan

- Conversion Plan

- Strategy & Reporting Plan

- Fit-Gap Report

- Training Evaluations

- Risk, Issue, and Jeopardy Reports

- All Status Reports

- Lessons Learned Reports

- Final Project Evaluation

- All Related Documents in Section 1.5 above.

## Documentation

Library

Definitive copies of electronic documents will be stored in SCT's GES Professional Services Project Tracking System database.  All such documents will also be distributed via email to CCRI's Project Manager for this project.  Appropriate documents will be made available to the College community via the CCRI web site.

Where documents exist only in hard copy, SCT’s Project Manager will retain definitive copies, except those documents specifically indicated by CCRI.

Configuration Identification

To identify documents as work products of this project, and to distinguish various versions of a document as it changes over time, the following naming scheme will be adapted for all project-related electronic documents:

CCRI Banner document_name vx.x.ext

## Communication

The CCRIBIT Steering Committee will meet bi-weekly.  They will report status in writing to the President’s Council as needed.  The Project Manager will attend President’s Council meetings on a regular basis.

While each product is being implemented in Banner, the corresponding Project Team will meet at least bi-weekly.  They will report status to the Steering Committee after each meeting.

The official channel for communications within the Steering Committee will be email.  Meeting invitations, status reports, etc. will be communicated by email.  All members will access email with sufficient frequency to acknowledge invitations in a timely way.

To ensure continuity in the exchange of information, any communication between CCRI and SCT will be copied to the Project Managers:

| CCRI Project Manager Alice Aguiar aaguiar@ccri.edu Community College of Rhode Island 400 East Avenue Warwick, RI 02886 | SCT Project Manager Barry Emmert bemmert@sctcorp.com SCT 3000 Ridge Road East Rochester, NY 14622 |
| --- | --- |

## Measurement

The following metrics will be captured and reported:

- variance from timeline

- variance from budget

- milestones met/deliverables received

- number of people trained

- assessment of Banner proficiency (logons delivered)

- user satisfaction surveys (student, faculty, staff, community)

## Project Environment

Project Management will be performed using Microsoft Project and Microsoft Office tools.

CCRIBIT and Team meetings will often entail group review and revision of electronic documents, and will be greatly facilitated by the availability of PC video projector equipment.

## Quality Assurance

Quality Assurance will follow the approach spelled out in SCT's CSM.  CSM process documentation will be made available to the CCRI Project Manager by SCT upon request.  Highlights of the approach are documented below.

An SCT Quality Assurance Analyst has been assigned to the project. S/he will create a separate QA Plan.  CCRI will receive all QA Audit reports.  These reports will follow the CSM template, which can be found in the CSM process documentation mentioned above.

CCRI will compare SCT's QA Audit reports against CCRI satisfaction surveys to validate the results.

## Tracking

Project review will occur at the periodic Steering Committee meetings whose timing is described in the Communications section above.  The SCT or CCRI Project Manager will call a review meeting at major project milestones or whenever a schedule, cost or scope variance has occurred or is imminent.  Review meetings may also occur as a result of Risk Management, Quality Assurance, or other activities whose approach is described in this document.

## Risk Management

The general approach to risk management will be as follows.

Risks are identified at the beginning of the project and throughout the project. When a Risk is identified, it is documented in the project repository.  Preventive and/or contingent responses are identified in the Risk Matrix (Section 7).

The Project Managers manage the Risks by executing mitigation actions, which may include how the contingency plans will be implemented.

If a Risk materializes, it is escalated to a Project Issue or Jeopardy according to CSM protocol.  The Issue or Jeopardy is then accepted or resolved according to the Risk Matrix (Section 7).

Risk, Issue, and Jeopardy reports will follow the CSM template, which can be found in the CSM process documentation mentioned above.

# System Requirements

System Requirements are items that are necessary in order to run any related software required for the practices/methodologies at a client site. This includes hardware and software needs.

## Database Server Requirements

| ALPHA SERVER | ES80 MODEL6 with True64 Unix based operating system |
| --- | --- |
| Application Server | Dell server/ Windows 2000 server OS |
| Web Server | Dell server/ Windows 2000 server OS |

## PC Requirements

PCs running web browser

## SCT and 3rd Party Product Requirements

COBOL compiler

## Developer Requirements

Banner 6.0 will require a minimum of Oracle 9i, Release 2 database.
It will be utilizing Oracle Developer 6i (Forms and Reports 6i) 
and also will use Oracle 9iAS Release 1.  It will require a minimum of Oracle Developer 6i Patch 13.

# Project Deliverables

The Project Deliverables for this project will include:

Item	Responsibility

Project Definition document	SCT/CCRI

Project Administration Document	SCT/CCRI

Project Plan	SCT

Project Budget	CCRI

Fit-Gap Document	SCT/CCRI

Pre and Post Installation Documents	SCT

Security Plan	CCRI

User Procedure Documents	CCRI

Test Plan	SCT/CCRI

Conversion Plan	SCT/CCRI

Verification Plan	CCRI

Reports Design	CCRI

End User Training	CCRI

User Training Plan	CCRI

User Training Materials	CCRI

Operations Manual	CCRI

System Review Document	CCRI

Required Interfaces for Each Product	CCRI

# Project Success Criteria

The project is considered successfully complete when the project objectives have been met.

Success criteria are as follows:

- All issues and action items have been completed and signed off

- All required work products have been produced

- All deficiencies have been logged and signed off

- Verification that the project has met project and CCRI standards

- Validation that the product meets the requirements

- Successfully complete the functional and physical configuration audits

- Existence of a mutually accepted cancellation of scheduled services statement in the Software License & Services Agreement (SLSA)

# Approval to Proceed

The approvers of this document are:

| Dr. Thomas D. Sepe |  | Robert Henderson |
| --- | --- | --- |
| President |  | Executive Vice President/Vice President for Business Affairs and Treasurer |
| Date |  | Date |

| Nancy Abood |  | Dr. Ruth Sherman |
| --- | --- | --- |
| Assistant to the President/Director of Public Relations and Publications |  | Vice President for Academic Affairs |
| Date |  | Date |

| Joseph DiMaria |  | Philip Sisson |
| --- | --- | --- |
| Vice President for Student Affairs |  | Dean of the Division for Lifelong Learning CCRIBIT Steering Committee Member |
| Date |  | Date |

CCRIBIT Steering Committee

| Alice Aguiar |  | Sheri Norton |
| --- | --- | --- |
| Project Manager |  | Assistant Director of Personnel |
| Date |  | Date |

| Deborah Aiken |  | Mark Vigorito |
| --- | --- | --- |
| Project Lead, Assistant to the Commissioner for Student Systems for the Office of Higher Education |  | Associate Director of Financial Aid |
| Date |  | Date |

| Tammy Anderson |  | Pat White |
| --- | --- | --- |
| Associate Director, Information Technology |  | Assistant Controller |
| Date |  | Date |

| Dr. William LeBlanc |  | Dr. Peter Woodberry |
| --- | --- | --- |
| Director of Institutional Research |  | Dean of Business & Technology Programs |
| Date |  | Date |

Document History

Revision Record

| Number | Date and Sections | Author | Notes |
| --- | --- | --- | --- |
| 1.0 | All | CCRIBIT | Planning Session – April 15-17 |
| 1.1 | All | Alice Aguiar | Revisions after planning session |
| 1.2 | All | Alice Aguiar | Revisions after 5/15/03 Steering Committee meeting. |
| 1.3 | All | Alice Aguiar | Revisions after 6/02/03 Steering Committee meeting; addition of executive summary and budget |
| 1.4 | All | Alice Aguiar | Revisions after 6/04/03 meeting with President’s Council. Addition of new initiatives review process. |

# Acronyms

| Acronym | Description |
| --- | --- |
| A/R | Accounts Receivable |
| CAPP | Curriculum, Advising and Program Planning |
| CCRI | Community College of Rhode Island |
| CCRIBIT | CCRI Banner Implementation Team |
| CM | Configuration Management |
| CSM | SCT's Common Service Methodology |
| INAS | Institutional Needs Analysis System of the College Entrance Examination Board |
| OHE | Office of Higher Education |
| OR | Organizational Readiness |
| PDD | Project Definition Document |
| POPS | SCT's Project Organization and Planning Session |
| RIHEAA | Rhode Island Higher Education Assistance Authority |
| SCT | Systems & Computer Technology Corporation |
| SLSA | Software License & Services Agreement |
| QA | Quality Assurance |

# Definitions

| Term | Definition |
| --- | --- |
| Legacy System | SCT PLUS |
| Pre-Legacy | Domains |

# CCRI Banner Implementation Project Organization

# Budget Details

|  | FY2003 | FY2004 | FY2005 | FY2006 | Total |
| --- | --- | --- | --- | --- | --- |
| Committed expenses |  |  |  |  |  |
| Oracle Licenses | 208,800 |  |  |  | 208,800 |
| maintenance/support | 46,056 | 47,438 | 48,861 | 50,326 | 192,680 |
| Database Server (HP Alpha/incl 4 yrs maint) | 233,636 |  |  |  | 233,636 |
| SCT Software | 160,480 | 160,480 |  |  | 320,960 |
| additional annual maintenance | 54,138 | 99,992 | 102,992 | 106,082 | 363,203 |
| SCT Committed Services (for base project) | 68,747 | 274,987 | 274,987 | 206,240 | 824,960 |
| SCT Conversion toolkit and training |  | 86,400 |  |  | 86,400 |
| SCT Travel reimbursement | 5,000 | 95,000 | 87,500 | 62,500 | 250,000 |
| SCT additional consulting (1000 hours) |  | 32,000 | 64,000 | 64,000 | 160,000 |
| Additional expenses |  |  |  |  |  |
| Cobol compiler and developer tool |  | 6,200 |  |  | 6,200 |
| Application/forms server |  | 10,000 |  |  | 10,000 |
| AppWorx (job scheduling software) and maintenance |  | 26,250 | 5,250 | 5,250 | 36,750 |
| Envisions (laser form creation software) and maintenance |  |  | 20,000 | 4,000 | 24,000 |
| Reporting software |  | 30,000 |  |  | 30,000 |
| Additional costs for WebCT institutional edition |  |  | 16,000 | 16,000 | 32,000 |
| Printers (IT and depts) |  | 40,000 | 20,000 | 10,000 | 70,000 |
| Additional training (Unix, systems, etc) |  | 10,000 | 5,000 |  | 15,000 |
| Network Firewall |  | 35,000 |  |  |  |
| Additional for implementation of Add-on Modules |  |  |  |  |  |
| WebCT integration training |  |  | 7,040 |  | 7,040 |
| Executive Self Service training |  |  |  | 14,080 | 14,080 |
| Oracle License (database and ap server) |  |  |  | 60,000 | 60,000 |
| Maint/Support |  |  |  | 13,200 | 13,200 |
| Server |  |  |  | 7,500 | 7,500 |
| E-Print report distribution |  |  |  |  |  |
| Install and training |  |  | 5,500 |  | 5,500 |
| Server |  |  | 5,000 |  | 5,000 |
| Workflow training |  |  |  | 14,080 | 14,080 |
| Server (4 processors) |  |  |  | 25,000 | 25,000 |
| Total | 776,856 | 953,746 | 662,129 | 658,258 | 3,015,989 |

# Text boxes

Work  Teams

Formed as needed

Institutional Technology

Advisory Committee

Human Resources Project Team

Sheri Norton, Project Lead

Financial Aid Project Team

Mark Vigorito, Project Lead

Student Project Team

Deb Aiken, Project Lead

Finance Project Team

Pat White, Project Lead

Banner Steering Committee

Alice Aguiar, Project Manage

President’s Council