2016-17 NAE4-HA Team Plan of Work

Team: 	State Relations

Team: 	Cheryl Newberry- State Relations Team Chair

Committee/Task Force Chair-Elect: 	TBD

Date Submitted: 	11/17/2016					Submitted by: 	Cheryl Newberry

NAE4-HA Strategic Goals:

- Provide a means of effective communication between the NAE4HA Board and membership.

- Facilitate networking throughout the association and with 4-H partners.

- Meet the needs of youth development professionals by maximizing the use of technology.

- Provide progressive levels of professional development

- Elevate the quality of youth development work through scholarship, research and practice.

- Advocate for the 4-H youth development profession.

Team Goals for 2016-17:

- Begin to address items on the Strategic Plan that pertain to tasks of the State Relations Team

- Engage a representative cross-section of members through a variety of ways such as webinars, email, news, etc.

- Effectively represent the membership while serving in Team and Board responsibilities

- Serve as the voice of the membership and the Board of Trustees

| Objective(s) | Action Steps | Position/Person Responsible | Target Date | Status Report | Budget Amount |
| --- | --- | --- | --- | --- | --- |
| Provide a means of effective communication between the NAE4-HA Board and its membership through State Visits | Each RD will plan to make at least two state visits, not including their home states. State Associations will be asked to complete a State Visit Request on the nae4ha.com website by December 31, 2016. RD’s will arrange their own travel consistent with NAE4-HA travel policy. RD team will support the Strategic Planning process by gathering timely input and feedback. Connections via technology or other means will also be offered to State Associations when a physical visit is not an option. | Communication RD’s are primary point of contact for a region. Regional Teams | October 15, 2017 |  | $1,750 per RD x 9 RD’s $15,750 Total |
| Facilitate networking throughout the association AND Provide a means of effective communication between the NAE4-HA Board and its membership through State Officer Workshop @ NAE4-HA Annual Conference | Discuss topics and make assignments during the monthly RD Conference Calls Promote participation by membership through the Quarterly Newsletter, social media, monthly eNews and Conference web page Develop agenda, PPT presentation and make copies of handouts | The State Relations Chair will develop and submit the Proposal. RDs will be responsible for hosting the workshop. eNews/Newsletter – Rebecca Thomas to coordinate Social media posts – Jamie Davis and Joan Grott Jamie Davis to Chair the development of presentation/PPT, etc. | Proposal: December 2016 Workshop: November 2017 |  | $250 for small hospitality type items or snacks |
| Facilitate networking throughout the association AND Provide a means of effective communication between the NAE4-HA Board and its membership through member engagement sessions at the JCEP Leadership Conference | Promote the event to membership through the Quarterly Newsletter and monthly eNews Dec.2016 – discuss, develop, plan and make job assignments during the monthly RD Conference Call Jan. 2017 – finalize plans during the monthly RD Conference Call Feb. 2017 – Travel to JCEP on Monday, meet as a team on Tuesday prior to conference start; implement the workshops and Finance RDs manage expense vouchers for participant reimbursement March 2017– evaluation and follow-up | Regional Directors | February 8-9, 2017 |  | State Leader Travel and Expensed including Registration =$47,800 Regional Directors Travel and Expenses including Registration =$11,200 Total= $59,000 |
| Advocate for the 4-H youth development profession through PILD Scholarship | Promote the event to membership through the Quarterly Newsletter and monthly eNews March 2017 – Finance RDs will compose a list of state representatives from each region that are designated to receive a scholarship stipend of $250 each, and provide to the national office. | Regional Directors |  |  | $8,000 |
| Provide a means of effective communication between the NAE4-HA Board and its membership through three Quarterly Newsletters | Assignments will be made during the monthly RD Conference Calls in Nov. 2016, March 2017 and August 2017 The newsletter will be e-mailed to membership in Dec. 2016, April 2017 and Sept. 2017, along with being uploaded onto the NAE4-HA Website RD’s will focus on highlighting members’ programming in each issue. Regions will rotate monthly to provide recognition from across the country throughout the year. RD’s will also provide reports from State Visits when timely. | Rebecca Thomas, Southern Region Communications Director, will manage, in conjunction with the Executive Director. All regional directors responsible for assisting with submissions. | Dec. 2016, April 2017 and September 2017 |  | N/A |
| Provide a means of effective communication between the NAE4-HA Board and its membership through Monthly E-News | The eNews will be e-mailed to membership in Jan., Feb., March, May, June, July, Aug. and Oct. 2017. RD’s will focus on highlighting members’ programming in each issue. RD’s will also provide reports from State Visits when timely. The NAE4-HA Board will submit timely articles, information on upcoming webinars, and other materials throughout the year. Some have already signed up for specific months to submit. | Rebecca Thomas, Southern Region Communications Director, will manage, in conjunction with the Executive Director. All regional directors responsible for assisting with submissions. | Jan., Feb., March, May, June, July, Aug. and Oct.) 2017 |  | N/A |
| Provide a means of effective communication between the NAE4-HA Board and its membership through regular social media posts. | Utilize information from newsletters, eNews, or other timely information and reminders to schedule weekly posts on NAE4-HA social media accounts. | Jamie Davis, Western Region RD, and Joan Grott, North Central RD, will take leadership in collaboration with the Executive Director. | Ongoing |  | N/A |
| Provide progressive levels of professional development by offering First Timer Scholarship | November: Edit application and work with Awards and Recognition Chair to integrate application process with the online awards system. Make available to membership at the same time National Awards information is published. RDs Receive and review applications in April 2017 from Awards and Recognition Chair. Regional winners notified in April 2017 by Communication RDs. Finance RDs responsible for expense vouchers in November 2017 @ National Meeting. | Southern Region Communications Director, will be responsible for editing the scholarship guidelines and application on an annual basis and submitting information to the awards and recognition chair. | Submit information to Awards and Recognition Chair: November 11, 2016. Judge Regional Awards: April 2017 Select and notify winners from each region: April 2017 Process vouchers/payments: November 2017 following National Meeting. |  | $2000 |
| Provide a means of effective communication between the NAE4-HA Board and membership through State Officer and Regional Director Handbooks | The Handbooks will be updated and submitted to the President for review by June 2017 who will forward to the Chair of the Policy & Resolution Committee The accepted handbooks should be provided to the Executive Director to be uploaded on the NAE4-HA website for membership access by October 2017 | The Western Region Communications RD is responsible for updating the State Officer’s Handbook. The North Central Communications RD is responsible for updating the Regional Director’s Handbook. Appoint a committee to assist the assigned RD in reviewing and updating handbook. |  |  | N/A |
| Elevate the quality of youth development work through scholarship, research and practice by providing recognition at Regional Meeting/Awards Program – NAE4-HA Conference | RDs will begin development of the Program agenda by August 2017: program, auctions, room set up, technology needs, awards, scholarship funds, public relations, etc. The Communication RDs will promote the event via the Quarterly Newsletter, eNews, and possibly email with state leadership/registrants from Aug.-Nov. 2017. | Each Regional Director team will be responsible for planning and conducting their own Regional Meeting/Awards Program in conjunction with the annual association conference. RDs will work with the following to complete specific tasks: Regional Member Recognition Chair to coordinate the awards program; Executive Director for First Timer Scholarship payment, printing of the award certificates and programs, and credit card forms/change for auctions; Conference Planner for room set up and technology needs; Past RDs/state leadership to assist with the silent and live auctions and parts on the program. | Begin preparations by August 2017; Complete at Annual Conference in November 2017. |  | N/A |